## 1.4.2 - Overall Rice Tracker_rb
RICE ID | RICE Type | Pre Fix - Workstream | SEQ | Track Duplicate SEQ | Scrums | Sub Entity | Release | Go-Live | Deloitte Phase II RICE ID | Object Name | Object Description | Priority | Module | Workstream | Accountable Org | SIT Readiness | Object Status | Operation System | Scope Origin | In Scope | Method | Interface Direction | Source System | Target System | Design Sprint | Dev - Sprint | Tech Spec Owner | Dev Team (Oracle) | Dev Team (Boundary System) | Boundary System - Build Completion Date | % Boundary System Build | RICE Owner | RICE Status | Complexity | EPIC URL | Spec Completion Date - Planned | Spec Completion Date - Revised | Spec Start Date - Actual | Spec Completion Date - Actual | Spec - Approval Date | Functional Owner | Spec % Complete | Functional Spec Status | Technical Owner | Dev Start Date - Planned | Dev Start Date - Actual | Dev + UT Completion Date - Planned | Dev + UT Completion Date - Revised | Dev+ UT Completion Date - DO NOT USE | Dev + UT Completion Date - Actual | Dev % | Dev Status | FUT Start Date - Actual | FUT Completion Date - Planned | FUT Completion Date - Actual | FUT Status | FUT Required? | Frequency | Comments | Modified By | Modified | SCRUM | Hide (Columns not in use) -----> | Build hours | Build + Unit Testing Start Date - Planned | Build + Unit Testing Start Date - Actual | Build Status | Spec Completion Date (Do not edit) | Pre-Fix - RICE Type | Sprint : F-Spec | Week : F-Spec | Sprint : F-Spec Review with Dev | Week : F-Spec Review with Dev | Sprint : T-Spec | Week : T-Spec | Sprint : Build and UT | Week : Build and UT | Sprint : FUT | Week : FUT | System (Formula Column)
SCM-CNV-1001 | Conversion | SCM | 1001 |  |  | RB, IP/Mascus & Others |  |  |  | Vendor Master Data | Convert Vendor Master |  | Procurement | Procurement | RBG |  | Delayed | Yes | SOW | Duplicate | FBDI | NA | EBS | Oracle Cloud ERP | Sprint 1 |  | Oracle Team 1 | Oracle Team 1 | [5 empty] | Medium |  | 2025-11-18 | [6 empty] | Delayed |  | 2025-11-24 |  | 2025-12-10 |  | 2025-12-10 |  | 0% - Not Started | Delayed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 117 | 2025-11-24 |  | Delayed | 2025-11-18 | CNV | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Procurement : Sprint 1 | Week 1
FIN-INT-1001 | Integration | FIN | 1001 |  |  | RB & IAA | RB Non-Auction | IAA | INT-001 | ADP (International) - JE Import | ADP (International) - Manual Payroll File | 2 | GL | Finance | Deloitte |  | Delayed | No | SOW | Yes |  | Inbound | Payroll | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Deloitte |  |  |  | Sharjeel |  | Complex |  | 2026-05-08 | 2026-08-28 |  |  |  | Deepankar Gera | 0% - Not Started | Delayed | Suchitra Sahoo | 2026-08-31 |  | 2026-09-22 |  | 2026-09-22 |  | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Mar 24:Vikranth to validate the future state and confirm the scope. Geo - EU¦¦ Need deep dive on the approach and if at all we need the automated integration/or continue manual ops. Intl. payroll system - ST worx | suchisahoo@deloitte.com | 2026-08-30 22:44 |  |  | 153 | 2026-05-25 |  | Not Started | 2026-08-28 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-EXT-1001 | Extension | FIN | 1001 |  | DPP | RBA, IAA & IP | RB DPP | Core - DPP |  | COA Form | RBG_COA_MAPPING_FRAMEWORK |  | GL/AR/AP | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | NA | DPP/ASAP/Vision/Frontier/IPWeb | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 | Oracle Team 2 | Oracle Team 2 | Oracle Team | 2026-08-31 | 25% - Drafted | Sharjeel | WIP | Complex | https://ritchiebros.atlassian.net/browse/OP2-1955 | 2026-08-14 | 2026-09-18 | 2026-07-22 |  |  | hganasuni@ritchiebros.com | 25% - Drafted | In Progress | Yan Pang | 2026-07-20 | 2026-06-22 | 2026-07-17 |  | 2026-06-19 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  | May have some blockers. Need to follow-up. | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Delayed | 2026-09-18 | EXT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 2 | Week 1 | DPP
SCM-CNV-1002 | Conversion | SCM | 1002 |  |  | IAA (US & Non US) |  |  |  | Vendor Master Data | Convert Vendor Master (Auction) |  | Procurement | Procurement | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | Duplicate | FBDI | NA | GP | Oracle Cloud ERP | Sprint 2 |  | Oracle Team 1 | Oracle Team 1 | [5 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1002 | Integration | FIN | 1002 |  |  | RB & IAA, JMW & B&B | IAA - ASAP 1 RB DPP RB Non-Auction | Core - DPP | INT-002 | Kyriba Treasury - Payments | Send Payments to Kyriba |  | AP | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes |  | Outbound | Oracle Cloud ERP | Kyriba | Sprint 1 | Sprint 2 | Deloitte | Deloitte |  |  |  | Eric/Gurpreet |  | Medium |  | 2026-01-30 | 2026-04-30 |  | 2026-04-23 |  | Lara Chalak | 100% - Approved | Completed | Suchitra Sahoo | 2026-02-02 |  | 2026-02-16 |  | 2026-02-16 | 2026-04-23 | 100% - Complete | Completed |  |  | 2026-04-23 | Completed |  |  | Deployed for Small Entities. May need tweaks for the Large Entities | dipriverma@deloitte.ca | 2026-09-10 12:15 |  |  | 99 | 2026-02-02 |  | Completed | 2026-04-30 | INT | Finance : Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
SCM-CNV-1003 | Conversion | SCM | 1003 |  |  | IAA (US & Non US) - Vision |  |  |  | Convert Vendor Master Data - Vision | Convert Vendor Master (Auction) |  | Procurement | Procurement | RBG |  | #INVALID OPERATION |  |  | No |  | NA | Vision(CAN) | Oracle Cloud ERP | Sprint 1 | Sprint 2 | Oracle Team 1 | Oracle Team 1 | [5 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1003 | Integration | FIN | 1003 |  |  | RB & IAA, JMW & B&B | RB Non-Auction | Core Modules | INT-003 | Kyriba Treasury - Cash Management | Import Bank Statements from Kyriba and Run Bank Statement Reconciliation |  | CM | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes |  | Inbound | Kyriba | Oracle Cloud ERP | Sprint 1 | Sprint 2 | Deloitte | Deloitte |  |  |  | Eric/Gurpreet |  | Complex |  | 2026-01-30 | 2026-04-30 |  | 2026-04-23 |  | Deepankar Gera | 100% - Approved | Completed | Suchitra Sahoo | 2026-02-16 |  | 2026-03-10 |  | 2026-03-10 | 2026-04-23 | 100% - Complete | Completed |  |  | 2026-04-23 | Completed |  |  | March 24: Kyriba to fix the bug with the connector and tweak it for large entities. Kyriba to also provide the list of banks for the large entities. Deployed for Small Entities. May need tweaks for the Large Entities | dipriverma@deloitte.ca | 2026-09-10 12:15 |  |  | 153 | 2026-02-16 |  | Completed | 2026-04-30 | INT | Finance : Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-EXT-1003 | Extension | FIN | 1003 |  | IP | IP | IronPlanet | IP |  | IP Inspector Invoices | IP web i-Inspector Invoices(Users generate Manual files and upload files to ADF Page EBS ) |  | AP | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Inbound | IP Web | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 2 | Oracle Team 2 | IP Web Team | 2026-09-30 | 25% - Drafted | Sharjeel | Not Started | Complex | https://ritchiebros.atlassian.net/jira/software/projects/IOCM/summary https://ritchiebros.atlassian.net/wiki/spaces/~712020f2d6811a620a4640845080fe8faab33a/pages/3785162822/IronPlanet+Oracle+Cloud+Migration | 2026-10-02 | 2026-10-02 | 2026-07-22 |  |  | Sharjeel | 25% - Drafted | In Progress | Yan Pang | 2026-10-02 |  | 2026-10-01 |  | 2026-10-01 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-12-02 |  | Not Started |  |  | Interface_FIN349. Jenn FP&A - RAID in Progress (3rd July) - New Approach. Risk at business process level. | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-10-02 | EXT | Finance : SIT 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : SIT 2 | Week 1
FIN-INT-1004 | Integration | FIN | 1004 |  | Mascus | Mascus | Mascus | Mascus | INT-004 | Authorization Token validation request and Fund capture request to Ayden for Receipts and update response back to Oracle | Integration from Adyen - By Country(Mascus) |  | AR | Finance | Deloitte |  | Delayed | Yes | SOW | Yes |  | Inbound | Adyen | Oracle Cloud ERP | Sprint 3 | Sprint 3 | Deloitte | Oracle IFS Team | Jun, Martijn |  |  | Jun/Gurpreet | WIP | Medium |  | 2026-06-26 | 2026-09-04 |  |  |  | Venkata Kiran Kumar Pallantla | 50% - Reviewed | Delayed | Suchitra Sahoo | 2026-09-14 |  | 2026-09-28 |  | 2026-09-28 |  | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Mar 24: Will be dependent on Mascus’s Future State design workshops (Vikranth, Kavitha). Adyen will be required in future state. Currently a servlet is being invoked by concurrent. Program. | nivnath@deloitte.com | 2026-09-06 22:40 |  |  | 99 | 2026-06-01 |  | Not Started | 2026-09-04 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : SIT 2 | Week 1
FIN-EXT-1004 | Extension | FIN | 1004 |  | DPP | RB & IP | All | Core - DPP IP |  | CL: RB Populate Customer Risk Profile [Collections] | CL: RB Populate Customer Risk Profile | 1 | CL | Finance | Deloitte |  | Not Started | Yes | Imagine Sessions | Yes |  | Inbound | Oracle Cloud ERP | Oracle Cloud ERP | Sprint 3 | Sprint 4 | Deloitte | Deloitte | Oracle Team 2 |  |  | Sharjeel | Not Started | Medium |  | 2026-07-10 | 2026-09-18 |  |  |  | Harsh Rawal | 0% - Not Started | Not Started | Suchitra Sahoo | 2026-11-02 |  | 2026-11-23 |  | 2026-11-23 |  | 0% - Not Started | Not Started |  | 2026-10-06 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-31 14:09 |  |  | 144 |  |  | Not Started | 2026-09-18 | EXT
FIN-CNV-1005 | Conversion | FIN | 1005 |  |  | RB & IAA |  |  |  | Bank master data - bank,brach | Bank master data - bank,branch |  | CM | Finance | RBG |  | #INVALID OPERATION |  |  | Duplicate | FBDI | NA | EBS | Oracle Cloud ERP |  |  | Deloitte | Oracle Team 1 | [5 empty] | Simple | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1005 | Integration | FIN | 1005 |  | DPP | RB, IP | RB DPP | Core - DPP | INT-005 | Collection System - Integrate Acqueon Dialer [Collections] | Send Collection System required details to Acqueon Dialer | 1 | AR | Finance | Deloitte | SIT 1 - Wk 3 | Delayed | Yes | SOW | Yes |  | Inbound & Outbound | Oracle Cloud ERP | Acqueon Dialer | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Deloitte | Oracle Team |  |  | Sharjeel |  | Complex |  | 2026-06-26 | 2026-09-04 |  |  |  | Harsh Rawal | 75% - Feedback Incorporated | Delayed | Diprish Verma | 2026-08-31 |  | 2026-09-22 |  | 2026-09-22 |  |  | Not Started |  | 2026-10-06 |  | Not Started |  |  | Apr 17 - Total number of integration with EBS and Acqueon Dialer is 5 Mar 24: Imran to discuss in the workshop Advanced collection. Deep dive is needed on the process. | dipriverma@deloitte.ca | 2026-09-10 12:15 |  |  | 153 | 2026-06-15 |  | Not Started | 2026-09-04 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-EXT-1005 | Extension | FIN | 1005 |  | DPP | RB & IP | All | Core - DPP IP |  | CL : Custom Views for Scoring & Strategies [Collections] | CL : Custom Views for Scoring & Strategies IEX_F_XXRBA_DLN_ALL_CUST_V, IEX_F_XXRBA_FIRST_TIME_V & IEX_F_XXRBA_REPEATBUYER_V | 1 | CL | Finance | Deloitte |  | Not Started | Yes | Imagine Sessions | Yes |  | Inbound | Oracle Cloud ERP | Oracle Cloud ERP | Sprint 3 | Sprint 4 | Deloitte | Deloitte | Oracle Team 2 |  |  | Sharjeel | Not Started |  |  | 2026-07-10 | 2026-09-18 |  |  |  | Harsh Rawal | 0% - Not Started | Not Started | Suchitra Sahoo | 2026-11-02 |  | 2026-11-23 |  | 2026-11-23 |  | 0% - Not Started | Not Started |  | 2026-10-06 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-31 14:09 |  |  | 144 |  |  | Not Started | 2026-09-18 | EXT
FIN-CNV-1006 | Conversion | FIN | 1006 |  |  | RB, IP/Mascus & Others |  |  |  | Suppliers Banks and Accounts (external bank accounts) | Convert Supplier Banks and their Bank Accounts (External Bank Accounts) (Auction) |  | AP | Finance | RBG |  | Delayed | Yes | SOW | Duplicate | FBDI | NA | EBS | Oracle Cloud ERP |  |  | Oracle Team 1 | Oracle Team 1 | [5 empty] | Simple |  | 2025-11-18 | [6 empty] | Delayed |  | 2025-11-24 |  | 2025-12-05 |  | 2025-12-05 |  |  | Delayed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 90 | 2025-11-24 |  | Delayed | 2025-11-18 | CNV | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-INT-1006 | Integration | FIN | 1006 |  | CDW | RB & IAA | All | Core - DPP | INT-006 | Send Customer Extract to CDW | Send Customer Extract to CDW |  | AR | Finance | RBG |  | Dev-In Progress | Yes | SOW | Yes |  | Outbound | Unknown | CDW (Big Data -> Snowflake) | Sprint 2 | Sprint 3 Sprint 4 Sprint 5 | CDW | Oracle Team 1 | CDW Team |  |  | Khaleel | WIP | Complex |  | 2026-07-03 | 2026-09-18 | 2026-05-29 |  |  | TUHIN BERA | 25% - Drafted | In Progress | [7 empty] | 25% - Tech Spec - In Progress | In Progress |  |  |  | Not Started |  |  | Apr : 28: This is required for future state , Technical Design need to consider if branding is required for RB vs IAA Mar 26: This may be required to be sent to MDM (S3 Bucket). To be confirmed by May 1st. Mar 24: Will be dependent on future state CDMS design. target is Snowflake(Poc- Shaun) | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 153 | 2026-05-18 |  | Not Started | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-EXT-1006 | Extension | FIN | 1006 |  | DPP | RB & IP | All | Core - DPP IP |  | CL : RB Cancel First Time Buyer Strategy [Collections] | CL : RB Cancel First Time Buyer Strategy | 1 | CL | Finance | Deloitte |  | F-Spec-In Progress | Yes | Imagine Sessions | Yes |  | Inbound | Oracle Cloud ERP | Oracle Cloud ERP | Sprint 3 | Sprint 4 | Deloitte | Deloitte | Oracle Team 2 |  |  | Sharjeel | Not Started |  |  | 2026-07-10 | 2026-09-11 |  |  |  | Harsh Rawal | 25% - Drafted | In Progress | Suchitra Sahoo | 2026-11-23 |  | 2026-12-14 |  | 2026-12-14 |  | 0% - Not Started | Not Started |  | 2026-10-06 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-09 07:30 |  |  | 144 |  |  | Not Started | 2026-09-11 | EXT
FIN-CNV-1007 | Conversion | FIN | 1007 |  |  | IAA (US & Non US) |  |  |  | Convert Supplier Banks and their Bank Accounts (External Bank Accounts) (Auction) | Convert Supplier Banks and their Bank Accounts (External Bank Accounts) (Auction) |  | AP | Finance | RBG |  | #INVALID OPERATION |  |  | Duplicate | FBDI | NA | GP | Oracle Cloud ERP |  |  | Oracle Team 1 | Oracle Team 1 | [5 empty] | Simple | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1007 | Integration | FIN | 1007 |  | DPP | RB |  | Core - DPP | INT-007 | Import GL Journals from DPP | RBG_DPP_GL_Journals_Integration |  | GL | Finance | RBG |  | Completed | Yes | SOW | Yes |  | Inbound | DPP | Oracle Cloud ERP | Sprint 1 | Sprint 1 Sprint 2 | Oracle Team 2 | Oracle Team 2 | DPP Team | 2026-07-10 | 75% - Feedback Incorporated | Sharjeel | DONE | Complex | https://ritchiebros.atlassian.net/browse/DIG-3243 | 2026-07-17 | 2026-09-18 | 2026-07-17 | 2026-07-17 |  | hganasuni@ritchiebros.com | 75% - Feedback Incorporated | Completed | Yan Pang | 2026-04-20 | 2026-07-20 | 2026-05-20 |  | 2026-08-19 | 2026-05-20 | 100% - Complete | Completed | 2026-05-20 | 2026-07-20 | 2026-05-20 | Completed |  |  | April 22 - Naming convention updated Mar 24: Imran is addressing this in the Workshops. | dipriverma@deloitte.ca | 2026-08-28 08:06 |  |  | 207 | 2026-04-20 |  | Completed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1 | DPP
FIN-EXT-1007 | Extension | FIN | 1007 |  | DPP | RB & IP | All | Core - DPP IP |  | CL : RB Customer Collection & Dunning Contact Management Program [Collections] | CL : RB Customer Collection & Dunning Contact Management Program | 1 | CL | Finance | Deloitte |  | Not Started | Yes | Imagine Sessions | Yes |  | Inbound | Oracle Cloud ERP | Oracle Cloud ERP | Sprint 3 | Sprint 4 | Deloitte | Deloitte | Oracle Team 2 |  |  | Sharjeel | Not Started |  |  | 2026-07-10 | 2026-09-18 |  |  |  | Harsh Rawal | 0% - Not Started | Not Started | Suchitra Sahoo | 2026-09-28 |  | 2026-10-29 |  | 2026-10-29 |  | 0% - Not Started | Not Started |  | 2026-10-06 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-31 14:09 |  |  | 216 |  |  | Not Started | 2026-09-18 | EXT | [8 empty] | Finance : SIT 2
FIN-CNV-1008 | Conversion | FIN | 1008 |  |  | IAA (US & Non US) - Vision |  |  |  | Convert Supplier Banks and their Bank Accounts (External Bank Accounts) (Auction) | Convert Supplier Banks and their Bank Accounts (External Bank Accounts) (Auction) |  | AP | Finance | RBG |  | #INVALID OPERATION |  |  | No | FBDI | NA | Vision(CAN) | Oracle Cloud ERP |  |  | Oracle Team 1 | Oracle Team 1 | [5 empty] | Simple | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
SCM-INT-1008 | Integration | SCM | 1008 |  | DPP | RB & IAA, MARS | RB Non-Auction | Core - DPP | INT-008 | Process Receipts from Mars | Process Receipts from Mars |  | Procurement | Procurement | RBG |  | Dev-In Progress | Yes | SOW | Yes |  | Inbound | MARS | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Oracle Team 1 | MARS Team | 2026-09-04 | 25% - Drafted | Khaleel | WIP | Medium |  | 2026-08-07 | 2026-09-18 | 2026-07-17 |  |  | Ben Koch | 25% - Drafted | In Progress | Ben Koch | 2026-08-10 | 2026-08-10 | 2026-08-24 |  | 2026-08-24 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  | Mar 24: Integration to be built to receive Receipts from MARS into Fusion. Supplier will exist April 6: RAID-111 | dipriverma@deloitte.ca | 2026-08-28 08:06 |  |  | 99 | 2025-12-08 |  | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-EXT-1008 | Extension | FIN | 1008 |  | DPP | RB & IP | All | Core - DPP IP |  | CL : RB Strategy On Hold [Collections] | CL : RB Strategy On Hold | 1 | CL | Finance | Deloitte |  | F-Spec-In Progress | Yes | Imagine Sessions | Yes |  | Inbound | Oracle Cloud ERP | Oracle Cloud ERP | Sprint 3 | Sprint 4 | Deloitte | Deloitte | Oracle Team 2 |  |  | Sharjeel | Not Started |  |  | 2026-07-10 | 2026-09-11 |  |  |  | Harsh Rawal | 25% - Drafted | In Progress | Suchitra Sahoo | 2026-09-28 |  | 2026-10-29 |  | 2026-10-29 |  | 0% - Not Started | Not Started |  | 2026-10-06 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-09 07:30 |  |  | 216 |  |  | Not Started | 2026-09-11 | EXT | [8 empty] | Finance : SIT 2
SCM-INT-1009 | Integration | SCM | 1009 |  | DPP | RB & IAA, MARS | RB Non-Auction | Core - DPP | INT-009 | Mars - Purchase Order Integration (Create/Update Purchase Orders) & Send PO Status to MARS | Receive & Update Purhase Orders from MARS and sent back the Status/Update Purchase Order. |  | Procurement | Procurement | RBG |  | Dev-In Progress | Yes | SOW | Yes |  | Outbound | Oracle Cloud ERP | MARS | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Oracle Team 1 | MARS Team | 2026-09-04 | 25% - Drafted | Khaleel | WIP | Medium |  | 2026-08-07 | 2026-09-18 | 2026-07-28 |  |  | Ben Koch | 50% - Reviewed | In Progress | Ben Koch | 2026-08-10 | 2026-08-10 | 2026-08-24 |  | 2026-08-24 |  | 50% - Build - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  | Mar 24: Sync Purchase Orders b/w Mars & Fusion April 6: RAID-111 | dipriverma@deloitte.ca | 2026-08-28 08:06 |  |  | 99 | 2025-11-17 |  | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-EXT-1009 | Extension | FIN | 1009 |  | DPP | RB & IP | All | Core - DPP IP |  | CL : RB Collection Strategy to Email Sync Program [Collections] | CL : RB Collection Strategy to Email Sync Program | 1 | CL | Finance | Deloitte |  | Delayed | Yes | Imagine Sessions | No |  | Inbound | Oracle Cloud ERP | Oracle Cloud ERP | Sprint 3 | Sprint 4 | Deloitte | Deloitte | Oracle Team 2 |  |  | Sharjeel | Not Started |  |  | 2026-07-10 | 2026-09-04 |  |  |  | Harsh Rawal | 0% - Not Started | Delayed | Suchitra Sahoo | 2026-09-28 |  | 2026-10-29 |  | 2026-10-29 |  | 0% - Not Started | Not Started |  | 2026-10-06 |  | Not Started |  |  |  | nivnath@deloitte.com | 2026-09-06 22:40 |  |  | 216 |  |  | Not Started | 2026-09-04 | EXT | [8 empty] | Finance : SIT 2
SCM-CNV-1010 | Conversion | SCM | 1010 |  |  | RB, IP/Mascus & Others |  |  |  | Suppliers, sites,addresses and contacts | Convert Supplier's Addresses, Sites and Contacts (Auction) |  | Procurement | Procurement | RBG |  | Delayed | Yes | SOW | Duplicate | FBDI | NA | EBS | Oracle Cloud ERP |  |  | Oracle Team 1 | Oracle Team 1 | [5 empty] | Medium |  | 2025-11-18 | [6 empty] | Delayed |  | 2025-11-24 |  | 2025-12-05 |  | 2025-12-05 |  |  | Delayed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 90 | 2025-11-24 |  | Delayed | 2025-11-18 | CNV | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Procurement : Sprint 1 | Week 1
FIN-INT-1010 | Integration | FIN | 1010 |  |  | RB, MARS |  |  |  | Mars - send POs | Lot transfer |  | GL | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | No |  | Inbound | MARS | Oracle ERP Cloud | Sprint 2 | Sprint 2 Sprint 3 | Deloitte | Oracle Team 1 | MARS Team |  |  | Khaleel | WIP | Medium | [6 empty] | Ben Koch | 0% - Not Started | #INVALID OPERATION | Ben Koch | [6 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | April 22 - Need a confirmation if this solution is still required for Cloud, current solution used in EBS Need deeper dive to solution this. | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-EXT-1010 | Extension | FIN | 1010 |  | DPP | RB & IP | All | Core - DPP IP |  | CL : RB Work Item Sync to Invoice Age [Collections] | CL : RB Work Item Sync to Invoice Age | 1 | CL | Finance | Deloitte |  | F-Spec-In Progress | Yes | Imagine Sessions | Yes |  | Inbound | Oracle Cloud ERP | Oracle Cloud ERP | Sprint 3 | Sprint 4 | Deloitte | Deloitte | Oracle Team 2 |  |  | Sharjeel | Not Started |  |  | 2026-07-10 | 2026-09-11 |  |  |  | Harsh Rawal | 25% - Drafted | In Progress | Suchitra Sahoo | 2026-08-10 |  | 2026-09-24 |  | 2026-09-24 |  | 0% - Not Started | Not Started |  | 2026-10-06 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-09 07:30 |  |  | 306 |  |  | Not Started | 2026-09-11 | EXT
SCM-CNV-1011 | Conversion | SCM | 1011 |  |  | IAA (US & Non US) |  |  |  | Convert Supplier's Addresses, Sites and Contacts (Auction) | Convert Supplier's Addresses, Sites and Contacts (Auction) |  | Procurement | Procurement | RBG |  | #INVALID OPERATION | Yes |  | Duplicate | FBDI | NA | GP | Oracle Cloud ERP |  |  | Oracle Team 1 | Oracle Team 1 | [5 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1011 | Integration | FIN | 1011 |  |  | RB & IAA |  |  | INT-010 (SOW: INT-011) | MasterCard Transactions Status back to JPMC | Send MasterCard Expenses Status |  | Expenses | Finance | Deloitte |  | Delayed | No | SOW | No |  | Outbound | Oracle Cloud ERP | MasterCard |  |  | Deloitte | [6 empty] | Medium |  | 2026-01-16 |  |  |  |  | Noshin Ali Barnagarwala |  | Delayed |  | 2026-03-23 |  | 2026-04-06 |  | 2026-04-06 |  |  | Delayed |  |  |  | Not Started |  |  | Mar 24: No requirement to send any status back to JPMC. To be logged in RAID. May not be required | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 99 | 2026-03-23 |  | Delayed | 2026-01-16 | INT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Gap Sprint | Week 1
FIN-EXT-1011 | Extension | FIN | 1011 |  | DPP | RB & IP | All | Core - DPP IP |  | CL : Custom OAF Page to Maintain Customer Contact phone number and DND details [Collections] | CL : Custom OAF Page to Maintain Customer Contact phone number and DND details | 1 | CL | Finance | Deloitte |  | Not Started | Yes | Imagine Sessions | Yes |  | Inbound | Oracle Cloud ERP | Oracle Cloud ERP | Sprint 3 | Sprint 4 | Deloitte | Deloitte | Oracle Team 2 |  |  | Sharjeel | Not Started |  |  | 2026-07-10 | 2026-09-18 |  |  |  | Harsh Rawal | 0% - Not Started | Not Started | Suchitra Sahoo | 2026-08-10 |  | 2026-09-24 |  | 2026-09-24 |  | 0% - Not Started | Not Started |  | 2026-10-06 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-31 14:09 |  |  | 306 |  |  | Not Started | 2026-09-18 | EXT
SCM-CNV-1012 | Conversion | SCM | 1012 |  |  | IAA (US & Non US) - Vision |  |  |  | Convert Supplier's Addresses, Sites and Contacts (Auction) | Convert Supplier's Addresses, Sites and Contacts (Auction) |  | Procurement | Procurement | RBG |  | #INVALID OPERATION | Yes |  | No | FBDI | NA | Vision(CAN) | Oracle Cloud ERP |  |  | Oracle Team 1 | Oracle Team 1 | [5 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1012 | Integration | FIN | 1012 |  |  | RB & IAA |  |  | INT-011 (SOW: INT-0XX) | WEX (MasterCard) Transactions Status back to WEX | Send WEX Expenses Status |  | Expenses | Finance | Deloitte |  | Delayed | No | SOW | No |  | Outbound | Oracle Cloud ERP | MasterCard |  |  | Deloitte | [6 empty] | Medium |  | 2026-01-21 |  |  |  |  | Noshin Ali Barnagarwala |  | Delayed |  | 2026-03-30 |  | 2026-04-13 |  | 2026-04-13 |  |  | Delayed |  |  |  | Not Started |  |  | Mar 24: No requirement to send any status back to WEX. To be logged in RAID. May not be required | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 99 | 2026-03-30 |  | Delayed | 2026-01-21 | INT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Gap Sprint | Week 1
FIN-EXT-1012 | Extension | FIN | 1012 |  | DPP | RB & IP | All | Core - DPP IP |  | CL : Predelinquent Custom Node (Extension_FIN411) [Collections] | CL : Predelinquent Custom Node (Extension_FIN411) | 1 | CL | Finance | Deloitte |  | F-Spec-In Progress | Yes | Imagine Sessions | Yes |  | Inbound | Oracle Cloud ERP | Oracle Cloud ERP | Sprint 3 | Sprint 4 | Deloitte | Deloitte | Oracle Team 2 |  |  | Sharjeel | Not Started |  |  | 2026-07-10 | 2026-09-11 |  |  |  | Harsh Rawal | 25% - Drafted | In Progress | Suchitra Sahoo | 2026-08-10 |  | 2026-09-24 |  | 2026-09-24 |  | 0% - Not Started | Not Started |  | 2026-10-06 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-09 07:30 |  |  | 306 |  |  | Not Started | 2026-09-11 | EXT
FIN-INT-1013 | Integration | FIN | 1013 |  |  | RB & IAA, JMW & B&B | RB Non-Auction | Already Live | INT-012 | Import MasterCard Transactions (Expenses) | Import MasterCard Transactions (Expenses) |  | Expenses | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes |  | Inbound | MasterCard | Oracle Cloud ERP | Sprint 1 | Sprint 1 | Deloitte | Deloitte |  |  |  | Khaleel |  | Complex |  | 2026-01-23 | 2026-04-17 |  | 2026-04-27 | 2026-04-27 | Noshin Ali Barnagarwala | 100% - Approved | Completed | [7 empty] | Not Applicable | Not Applicable |  |  | 2026-05-04 | Completed |  |  | Mar 24: No Tech effort required. Deployed for Small Entities. May need tweaks for the Large Entities | dipriverma@deloitte.ca | 2026-09-10 12:15 |  |  | 153 | 2026-03-09 |  | Not Started | 2026-04-17 | INT | Finance : Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1014 | Conversion | FIN | 1014 |  |  | RB, IP/Mascus & Others |  |  |  | AP Invoices (Open) | Convert Open AP Invoices (RB auction) |  | AP | Finance | RBG |  | Delayed | Yes | SOW | No | FBDI | NA | EBS | Oracle Cloud ERP |  |  | Oracle Team 2 | Oracle Team 2 | [5 empty] | Complex |  | 2026-01-30 | [6 empty] | Delayed |  | 2026-02-02 |  | 2026-02-27 |  | 2026-02-27 |  |  | Delayed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 180 | 2026-02-02 |  | Delayed | 2026-01-30 | CNV | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-INT-1014 | Integration | FIN | 1014 |  |  | RB & IAA | RB Non-Auction | Core Modules | INT-013 (SOW: INT-XX) | Import WEX Transactions (Expenses) | Import WEX Transactions (Expenses) |  | Expenses | Finance | Deloitte | Before SIT 1 | FUT-Pending | No | SOW | Yes |  | Inbound | MasterCard | Oracle Cloud ERP | Sprint 1 | Sprint 2 | Deloitte | Deloitte |  |  |  | Khaleel |  | Complex |  | 2026-01-30 | 2026-06-15 |  | 2026-04-27 | 2026-04-27 | Noshin Ali Barnagarwala | 100% - Approved | Completed | Suchitra Sahoo | 2026-02-02 |  | 2026-02-24 |  | 2026-02-24 |  | Not Applicable | Not Applicable |  |  |  | Not Started |  |  | Mar 24: Scope to be finalized by April 10th. Need deeper dive on business process and future state operation | dipriverma@deloitte.ca | 2026-09-10 12:15 |  |  | 153 | 2026-02-02 |  | Delayed | 2026-06-15 | INT | Finance : Gap Sprint | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-CNV-1015 | Conversion | FIN | 1015 |  |  | IAA (US & Non US) |  |  |  | AP Invoices (Open) | Convert Open AP Invoices (Auction) |  | AP | Finance | RBG |  | #INVALID OPERATION |  |  | Duplicate | FBDI | NA | GP |  |  |  | Oracle Team 2 | Oracle Team 2 | [5 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 180 |  |  | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1015 | Integration | FIN | 1015 |  |  | RB & IAA |  |  | INT-014 (SOW: INT-013) | EFT Payment | Send EFT Payments to Banks |  | AP | Finance | Deloitte |  | Delayed | No | SOW | No |  | Outbound | Oracle Cloud ERP | Banks |  |  | Deloitte | [6 empty] | Medium |  | 2026-01-30 |  |  |  |  | Lara Chalak |  | Delayed |  | 2026-04-06 |  | 2026-04-20 |  | 2026-04-20 |  |  | Delayed |  |  |  | Not Started |  |  | Mar 24: Not required. Kyriba | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 99 | 2026-04-06 |  | Delayed | 2026-01-30 | INT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Gap Sprint | Week 1
FIN-CNV-1016 | Conversion | FIN | 1016 |  |  | IAA (US & Non US) - Vision |  |  |  | Convert Open AP Invoices - Vision | Convert Open AP Invoices (Auction) |  | AP | Finance | RBG |  | #INVALID OPERATION |  |  | No | FBDI | NA | Vision(CAN) |  |  |  | Oracle Team 2 | Oracle Team 2 | [5 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 180 |  |  | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1016 | Integration | FIN | 1016 |  |  | RB & IAA |  |  | INT-015 (SOW: INT-014) | Wire Payments | Send WIRE Payments to Banks |  | AP | Finance | Deloitte |  | Delayed | No | SOW | No |  | Outbound | Oracle Cloud ERP | Banks |  |  | Deloitte | [6 empty] | Medium |  | 2026-01-30 |  |  |  |  | Lara Chalak |  | Delayed |  | 2026-03-16 |  | 2026-03-30 |  | 2026-03-30 |  |  | Delayed |  |  |  | Not Started |  |  | Mar 24: Not required. Kyriba | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 99 | 2026-03-16 |  | Delayed | 2026-01-30 | INT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-CNV-1017 | Conversion | FIN | 1017 |  |  | RB, IAA (US & Non US), IP/Mascus & Others |  |  | CNV-004 | Convert Open AP Invoices | Convert Open AP Invoices |  | AP | Finance | Deloitte |  | Delayed | No | SOW | No | FBDI | NA | EBS, GP | Oracle Cloud ERP |  | Sprint 2 | Deloitte | Oracle Team 2 | [5 empty] | Complex |  | 2026-01-30 | 2026-04-30 |  |  |  | Lara Chalak |  | Delayed |  | 2026-05-04 |  | 2026-05-29 |  | 2026-05-29 |  |  | Delayed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 180 | 2026-05-04 |  | Delayed | 2026-04-30 | CNV | Finance : Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 2 | Week 1
FIN-INT-1017 | Integration | FIN | 1017 |  |  | RB & IAA |  |  | INT-016 (SOW: INT-015) | ACH Payments | Send ACH Payments to Banks |  | AP | Finance | Deloitte |  | Delayed | No | SOW | No |  | Outbound | Oracle Cloud ERP | Banks |  |  | Deloitte | [6 empty] | Simple |  | 2026-01-30 |  |  |  |  | Lara Chalak |  | Delayed |  | 2026-03-23 |  | 2026-04-01 |  | 2026-04-01 |  |  | Delayed |  |  |  | Not Started |  |  | Mar 24: Not required. Kyriba | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 72 | 2026-03-23 |  | Delayed | 2026-01-30 | INT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-CNV-1018 | Conversion | FIN | 1018 |  |  | RB, IP/Mascus & Others |  |  |  | Customer Master Data and Contacts | Convert Customer Master (Auction) |  | AR | Finance | RBG |  | Delayed | Yes | SOW | Duplicate | FBDI | NA | EBS | Oracle Cloud ERP |  |  | Oracle Team 1 | Oracle Team 1 | [5 empty] | Medium |  | 2026-01-30 | [6 empty] | Delayed |  | 2026-02-02 |  | 2026-02-18 |  | 2026-02-18 |  |  | Delayed |  |  |  | Not Started |  |  | Customers, Sites, Accounts, Locations, Account Sites, Contacts ¦¦ Note - MACUS open subscription Contracts recs | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 117 | 2026-02-02 |  | Delayed | 2026-01-30 | CNV | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-INT-1018 | Integration | FIN | 1018 |  |  | RB & IAA, JMW & B&B | RB Non-Auction | Already Live | INT-017 (SOW: INT-016) | Positive Pay Template for BofA | Customize Positive Pay Template for BofA |  | AP | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes |  | Outbound | Oracle Cloud ERP | Banks | Sprint 1 | Sprint 1 | Deloitte | Deloitte |  |  |  | Sharjeel |  | Medium |  | 2025-12-05 | 2025-12-05 |  | 2025-12-05 | 2025-12-16 | Lara Chalak | 100% - Approved | Completed | Suchitra Sahoo | 2025-12-19 |  | 2026-01-02 |  | 2026-01-02 | 2025-12-19 | 100% - Complete | Completed |  |  | 2025-12-22 | Completed |  |  | Multiple Positive Pay files will be need based on the Banks's list, pending review to lean spec and inputs from RBG | dipriverma@deloitte.ca | 2026-09-10 12:15 |  |  | 99 | 2026-04-06 |  | Completed | 2025-12-05 | INT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-CNV-1019 | Conversion | FIN | 1019 |  |  | IAA (US & Non US) |  |  |  | Convert Customer Master (Auction) | Convert Customer Master (Auction) |  | AR | Finance | RBG |  | #INVALID OPERATION | Yes |  | Duplicate | FBDI | NA | GP | Oracle Cloud ERP |  |  | Oracle Team 1 | Oracle Team 1 | [5 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1019 | Integration | FIN | 1019 |  |  | RB & IAA |  |  | INT-018 (SOW: INT-017) | Bank Statements | Import Bank Statements |  | CM | Finance | Deloitte |  | Delayed | No | SOW | No |  | Inbound | Bank | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Simple |  | 2026-01-30 |  |  | 2026-02-27 |  | Deepankar Gera | 100% - Approved | Completed |  | 2026-03-02 |  | 2026-03-11 |  | 2026-03-11 |  |  | Delayed |  |  |  | Not Started |  |  | Mar 24: Kyriba to provide the list of banks for the large entities. Automated through Kyriba. May not be required. | dipriverma@deloitte.ca | 2026-08-28 08:06 |  |  | 72 | 2026-03-02 |  | Delayed | 2026-01-30 | INT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-CNV-1020 | Conversion | FIN | 1020 |  |  | IAA (US & Non US) - Vision |  |  |  | Convert Customer Master (Auction) | Convert Customer Master (Auction) |  | AR | Finance | RBG |  | #INVALID OPERATION | Yes |  | Duplicate | FBDI | NA | Vision(CAN) | Oracle Cloud ERP |  |  | Oracle Team 1 | Oracle Team 1 | [5 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1020 | Integration | FIN | 1020 |  | IP | IP | IronPlanet | IP | INT-019 | Import AR Receipts from IP Web | Import AR Receipts from IP Web |  | AR | Finance | RBG |  | Dev-In Progress | Yes | SOW | Yes |  | Inbound | IP Web | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 2 | Oracle Team 2 | IP Web Team | 2026-09-30 | 25% - Drafted | Sharjeel | Not Started | Complex | https://ritchiebros.atlassian.net/jira/software/projects/IOCM/summary https://ritchiebros.atlassian.net/wiki/spaces/~712020f2d6811a620a4640845080fe8faab33a/pages/3785162822/IronPlanet+Oracle+Cloud+Migration | 2026-09-25 | 2026-09-25 | 2026-07-13 |  |  | Sharjeel | 25% - Drafted | In Progress | Yan Pang | 2026-09-25 |  | 2026-10-19 |  | 2026-10-19 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-11-25 |  | Not Started |  |  | Mar 26: Needs to be discussed with PMO to assign the ownership. Mar 24: RAID to be logged, assumed to be owned by RBG (confirm) | dipriverma@deloitte.ca | 2026-08-28 08:06 |  |  | 153 |  |  | Not Started | 2026-09-25 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : SIT 2 | Week 1
FIN-CNV-1021 | Conversion | FIN | 1021 | TRUE |  | IP and Mascus | All |  | CNV-005 | Customer Master Data and Contacts | Customer Master Data and Contacts |  | AR | Finance | RBG |  | Delayed | Yes | SOW | No | FBDI | NA | EBS | Oracle Cloud ERP | Sprint 2 | Sprint 3 |  | RBG Oracle Team 1 | RBG Oracle Team 1 |  |  |  |  | Medium |  | 2026-05-29 | 2026-07-17 |  |  |  | Sahana Srinivas | 0% - Not Started | Delayed | Khaleel Shaik | 2026-06-12 |  | 2026-06-30 |  | 2026-06-30 |  | 0% - Not Started | Delayed |  |  |  | Not Started |  |  | April 15: Accountability changed to RBG | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 117 | 2026-02-02 |  | Delayed | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-CNV-1021 | Conversion | FIN | 1021 | TRUE |  | IAA (US & Non US) | All | IAA | CNV-005 | Customer Master Data and Contacts | Customer Master Data and Contacts |  | AR | Finance | RBG |  | Delayed | Yes | SOW | Yes | FBDI | NA | GP | Oracle Cloud ERP | Sprint 2 | Sprint 3 | Khaleel Shaik | RBG Oracle Team 1 | RBG Oracle Team 1 |  |  |  |  | Medium |  | 2026-05-29 | 2026-07-17 |  |  |  | Sahana Srinivas | 25% - Drafted | Delayed | Khaleel Shaik | 2026-06-12 |  | 2026-06-30 |  | 2026-06-30 |  | 25% - Tech Spec - In Progress | In Progress |  |  |  | Not Started |  |  | April 15: Accountability changed to RBG | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 117 | 2026-02-02 |  | Delayed | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-INT-1021 | Integration | FIN | 1021 |  | DPP | RB, IAA & IP | All | Core - DPP | INT-020 (SOW: INT-XX) | Import Customers from TE | Import Customers from TE |  | AR | Finance | RBG |  | Dev-In Progress | Yes | SOW | Yes |  | Inbound | TE | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 | RBG Oracle Team 1 | Oracle Team 1 | TE | 2026-09-04 | 25% - Drafted | Khaleel/John Russ | WIP | Complex |  | 2026-08-14 | 2026-09-18 | 2026-06-15 |  |  | Wayne | 50% - Reviewed | In Progress | Kyle Boon | 2026-08-10 | 2026-08-10 | 2026-09-01 |  | 2026-09-01 |  | 50% - Build - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  | Mar 26: Needs to be discussed with PMO to assign the ownership Mar 24: RAID to be logged, assumed to be owned by RBG (confirm) | nivnath@deloitte.com | 2026-09-02 00:02 |  |  | 153 | 2026-05-04 |  | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1022 | Conversion | FIN | 1022 |  |  | RB, IP/Mascus & Others |  |  |  | Customer Banks and Accounts (external bank accounts) | Convert Customer Banks and External Bank Accounts (Auction) |  | AR | Finance | RBG |  | Delayed | Yes | SOW | Duplicate | FBDI | NA | EBS | Oracle Cloud ERP |  |  | Oracle Team 1 | Oracle Team 1 | [5 empty] | Simple |  | 2026-01-30 | [6 empty] | Delayed |  | 2026-02-23 |  | 2026-03-06 |  | 2026-03-06 |  |  | Delayed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 90 | 2026-02-23 |  | Delayed | 2026-01-30 | CNV | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-INT-1022 | Integration | FIN | 1022 |  | DPP | RB, IAA & IP | All | Core - DPP | INT-021 (SOW: INT-XX) | Import Vendors from TE | Import Vendors from TE |  | AP | Finance | RBG |  | Dev-In Progress | Yes | SOW | Yes |  | Inbound | TE | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 | RBG Oracle Team 1 | Oracle Team 1 | TE | 2026-09-04 | 25% - Drafted | Khaleel/John Russ | WIP | Complex |  | 2026-08-14 | 2026-09-18 | 2026-06-15 |  |  | Wayne | 50% - Reviewed | In Progress | Kyle Boon | 2026-08-10 | 2026-08-10 | 2026-09-01 |  | 2026-09-01 |  | 50% - Build - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  | Mar 26: Needs to be discussed with PMO to assign the ownership Mar 24: RAID to be logged, assumed to be owned by RBG (confirm) | nivnath@deloitte.com | 2026-09-02 00:02 |  |  | 153 | 2026-06-01 |  | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1023 | Conversion | FIN | 1023 |  |  | IAA (US & Non US) |  |  |  | Convert Customer Banks and External Bank Accounts (Auction) | Convert Customer Banks and External Bank Accounts (Auction) |  | AR | Finance | RBG |  | #INVALID OPERATION | Yes |  | Duplicate | FBDI | NA | GP |  |  |  | Oracle Team 1 | Oracle Team 1 | [5 empty] | Simple | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1023 | Integration | FIN | 1023 |  | DPP | RB & IAA | RB Non-Auction | Core - DPP | INT-022 (SOW: INT-XX) | Send Vendor Details to TE | Send Vendor Details to TE |  | AP | Finance | RBG |  | Dev-In Progress | Yes | SOW | Yes |  | Outbound | Oracle Cloud ERP | TE | Sprint 3 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 1 | Oracle Team 1 | TE | 2026-09-04 | 25% - Drafted | Khaleel | WIP | Medium |  | 2026-08-21 | 2026-09-18 | 2026-06-15 |  |  | Wayne | 50% - Reviewed | In Progress | Kyle Boon | 2026-08-10 | 2026-08-10 | 2026-08-24 |  | 2026-08-24 |  | 50% - Build - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  | Mar 26: Vendor Master data to be sent to MDM.Mar 24: Needs to be re-routed to CDMS. Diprish to validate with Gavin. target is Snowflake(Poc- Shaun) | dipriverma@deloitte.ca | 2026-08-28 08:06 |  |  | 99 | 2026-06-22 |  | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1024 | Conversion | FIN | 1024 |  |  | IAA (US & Non US) - Vision |  |  |  | Convert Customer Banks and External Bank Accounts (Auction) | Convert Customer Banks and External Bank Accounts (Auction) |  | AR | Finance | RBG |  | #INVALID OPERATION | Yes |  | Duplicate | FBDI | NA | Vision(CAN) |  |  |  | Oracle Team 1 | Oracle Team 1 | [5 empty] | Simple | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1024 | Integration | FIN | 1024 |  | IP | RB & IAA | IronPlanet | IP | INT-023 (SOW: INT-021) | Import AP Invoices from IP Web | Import AP Invoices from IP Web |  | AP |  | RBG |  | Dev-In Progress | Yes | SOW | Yes |  | Inbound | IP Web | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 2 | Oracle Team 2 | IP Web Team | 2026-09-30 | 25% - Drafted | Sharjeel | Not Started | Complex | https://ritchiebros.atlassian.net/jira/software/projects/IOCM/summary https://ritchiebros.atlassian.net/wiki/spaces/~712020f2d6811a620a4640845080fe8faab33a/pages/3785162822/IronPlanet+Oracle+Cloud+Migration | 2026-09-25 | 2026-09-25 | 2026-07-13 |  |  | Sharjeel | 25% - Drafted | In Progress | Yan Pang | 2026-09-25 |  | 2026-10-19 |  | 2026-10-19 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-11-25 |  | Not Started |  |  | Mar 26: Needs to be discussed with PMO to assign the ownership Mar 24: RAID to be logged, assumed to be owned by RBG (confirm) - Jenn FP&A - RAID in Progress (3rd July) - New Approach. Risk at business process level. | dipriverma@deloitte.ca | 2026-08-28 08:06 |  |  | 153 |  |  | Not Started | 2026-09-25 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1025 | Conversion | FIN | 1025 | TRUE |  | IP and Mascus | All |  | CNV-006 | Customer Banks and Accounts (external bank accounts) | Convert Customer Banks and External Bank Accounts |  | AR | Finance | RBG |  | Delayed | Yes | SOW | No | FBDI | NA | EBS | Oracle Cloud ERP | Sprint 2 | Sprint 3 |  | RBG Oracle Team 1 | RBG Oracle Team 1 |  |  |  |  | Simple |  | 2026-05-29 | 2026-07-17 |  |  |  | Sahana Srinivas | 0% - Not Started | Delayed | Khaleel Shaik | 2026-06-12 |  | 2026-06-25 |  | 2026-06-25 |  | 0% - Not Started | Delayed |  |  |  | Not Started |  |  | April 15: Accountability changed to RBG | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 90 | 2026-02-23 |  | Delayed | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-CNV-1025 | Conversion | FIN | 1025 | TRUE |  | IAA (US & Non US) | All | IAA | CNV-006 | Customer Banks and Accounts (external bank accounts) | Convert Customer Banks and External Bank Accounts |  | AR | Finance | RBG |  | Delayed | Yes | SOW | Yes | FBDI | NA | GP | Oracle Cloud ERP | Sprint 2 | Sprint 3 |  | RBG Oracle Team 1 | RBG Oracle Team 1 |  |  |  |  | Simple |  | 2026-05-29 | 2026-07-17 |  |  |  | Sahana Srinivas | 25% - Drafted | Delayed | Khaleel Shaik | 2026-06-12 |  | 2026-06-25 |  | 2026-06-25 |  | 25% - Tech Spec - In Progress | In Progress |  |  |  | Not Started |  |  | April 15: Accountability changed to RBG | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 90 | 2026-02-23 |  | Delayed | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-INT-1025 | Integration | FIN | 1025 |  |  | RB & IAA |  | ARCS | INT-024 (SOW: INT-022) | GL Balances to ARCS | Send GL Balances to ARCS |  | ARCS | Finance | Deloitte |  | Completed | No | SOW | Yes |  | Outbound | Oracle Cloud ERP | ARCS |  |  | Deloitte (ARCS) | Deloitte (ARCS) |  |  |  | Markus |  | Simple |  |  |  |  | 2026-04-03 |  | David Koter | 100% - Approved | Completed |  |  | 2026-04-06 |  |  | 2026-04-03 | 2026-04-07 | 100% - Complete | Completed |  |  | 2026-04-08 | Completed |  |  | April 15: integration built, scheduling of integration would need to be built using OIC | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Completed |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-CNV-1026 | Conversion | FIN | 1026 |  |  | RB, IP/Mascus & Others |  |  |  | AR Invoices (Open) | Convert Open AR Invoices (Auction) |  | AR | Finance | RBG |  | Delayed | Yes | SOW | No | FBDI | NA | EBS | Oracle Cloud ERP | Sprint 1 | Sprint 2 | Oracle Team 2 | Oracle Team 2 | [5 empty] | Complex |  | 2026-01-30 | 2026-07-17 | [5 empty] | Delayed |  | 2026-03-09 |  | 2026-04-03 |  | 2026-04-03 |  |  | Delayed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 180 | 2026-03-09 |  | Delayed | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-INT-1026 | Integration | FIN | 1026 |  |  | RB & IAA |  | ARCS | INT-025 (SOW: INT-023) | Currency Rates - to ARCS | Send Current Rates to ARCS |  | ARCS | Finance | Deloitte |  | Delayed | No | SOW | Yes |  | Outbound | Oracle Cloud ERP | ARCS |  |  | Deloitte (ARCS) | Deloitte (ARCS) |  |  |  | Markus |  | Simple |  |  | 2026-09-30 |  |  |  | David Koter | 0% - Not Started | Not Started | Aiden Lee | [6 empty] | 0% - Not Started | Not Started |  | 2026-09-04 |  | Delayed |  |  | April 15: Need to speak with Markus/Monika to determine if integration of currency rates is required to be built. | nivnath@deloitte.com | 2026-09-06 22:40 | [5 empty] | Not Started | 2026-09-30 | INT | Finance : SIT 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1027 | Conversion | FIN | 1027 |  |  | IAA (US & Non US) |  |  |  | Convert Open AR Invoices (Auction) | Convert Open AR Invoices (Auction) |  | AR | Finance | RBG |  | Delayed | Yes |  | No | FBDI | NA | GP |  | Sprint 1 | Sprint 2 | Oracle Team 2 | Oracle Team 2 | [5 empty] | Complex |  |  | 2026-07-17 | [5 empty] | Delayed | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 180 |  |  | Not Started | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1027 | Integration | FIN | 1027 |  |  | RB & IAA |  |  | INT-026 (SOW: INT-024) | GL Transactions | Send GL Transactions to ARCS |  | ARCS | Finance | Deloitte |  | #INVALID OPERATION | No | SOW | No |  | Outbound | Oracle Cloud ERP | ARCS |  |  | Deloitte (ARCS) | Deloitte (ARCS) |  |  |  | Markus |  | Simple | [8 empty] | #INVALID OPERATION | Aiden Lee | [6 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | April 15: to-be planned, sending GL bank transactions to ARCS for reconciliation with Kyriba | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1028 | Conversion | FIN | 1028 |  |  | IAA (US & Non US) - Vision |  |  |  | Convert Open AR Invoices (Auction) | Convert Open AR Invoices (Auction) |  | AR | Finance | RBG |  | Delayed | Yes |  | No | FBDI | NA | Vision(CAN) |  | Sprint 1 | Sprint 2 | Oracle Team 2 | Oracle Team 2 | [5 empty] | Complex |  |  | 2026-07-17 | [5 empty] | Delayed | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 180 |  |  | Not Started | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1028 | Integration | FIN | 1028 |  |  | RB & IAA |  | ARCS | INT-027 (SOW: INT-025) | Bank Transactions - to ARCS | Send Bank Transactions (ARCS -> Bank) |  | ARCS | Finance | Deloitte |  | Delayed | No | SOW | Yes |  | Outbound | Bank | ARCS |  |  | Deloitte (ARCS) | Deloitte (ARCS) |  |  |  | Markus |  | Medium |  |  | 2026-08-21 |  |  |  | David Koter | Blocked | Delayed | [7 empty] | Not Applicable | Not Applicable |  |  |  | Not Started |  |  | April 15: to-be planned, sending Kyriba transactions to ARCS for reconciliation | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-08-21 | INT | Finance : Sprint 3 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1029 | Conversion | FIN | 1029 |  |  | RB & IAA |  |  | CNV-007 | AR Invoices (Open) | Convert Open AR Invoices (Non-Auction) |  | AR | Finance | RBG |  | Delayed | No | SOW | No | FBDI | NA | EBS, GP | Oracle Cloud ERP |  |  | Deloitte | [6 empty] | Complex |  | 2026-01-30 | 2026-04-29 | [5 empty] | Delayed |  | 2026-03-09 |  | 2026-04-03 |  | 2026-04-03 |  |  | Delayed |  |  |  | Not Started |  |  | April 15: Accountability changed to RBG | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 180 | 2026-03-09 |  | Delayed | 2026-04-29 | CNV | Finance : Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-INT-1029 | Integration | FIN | 1029 |  |  | JMW | Small Entities (JMW, B&B) | Core Modules |  | Bank Statements feed from Kyriba to Oracle CM | Import Bank Statements (JMW) from Kyriba and Run Bank Statement Reconciliation |  | CM | Finance | Deloitte | Before SIT 1 | Completed | No | Discovery | Yes |  | Inbound | Kyriba | Oracle Cloud ERP |  |  | Deloitte |  |  |  |  | Eric/Gurpreet |  | Complex |  | 2025-09-24 |  |  | 2025-10-31 |  | Deepankar Gera | 100% - Approved | Completed |  | 2025-10-13 |  | 2025-11-04 |  | 2025-11-04 | 2025-11-07 | 100% - Complete | Completed |  |  | 2025-11-14 | Completed |  |  | Captured in the overall Kyriba to Oracle Integration | raramesh@deloitte.ca | 2026-09-10 13:52 |  |  | 153 | 2025-10-13 |  | Completed | 2025-09-24 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-CNV-1030 | Conversion | FIN | 1030 |  |  | RB, IP/Mascus & Others |  |  |  | AR Receipts (unapplied) | Convert Unapplied AR Receipts (Auction) |  | AR | Finance | RBG |  | Delayed | Yes | SOW | No |  | NA | EBS | Oracle Cloud ERP | Sprint 1 | Sprint 2 | Oracle Team 2 | Oracle Team 2 | [5 empty] | Complex |  | 2026-01-30 | 2026-07-17 | [5 empty] | Delayed |  | 2026-03-09 |  | 2026-04-03 |  | 2026-04-03 |  |  | Delayed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 180 | 2026-03-09 |  | Delayed | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-INT-1030 | Integration | FIN | 1030 |  |  | JMW |  |  |  | Consignor/Vendor feed from AMS to Oracle | Import Consignor Vendor feed from AMS |  | AP | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Inbound | Auction Management System* | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | NA | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1031 | Conversion | FIN | 1031 |  |  | IAA (US & Non US) |  |  |  | Convert Unapplied AR Receipts (Auction) | Convert Unapplied AR Receipts (Auction) |  | AR | Finance | RBG |  | Delayed |  |  | No | TBD | NA | GP |  | Sprint 1 | Sprint 2 | Oracle Team 2 | Oracle Team 2 | [5 empty] | Complex |  |  | 2026-07-17 | [5 empty] | Delayed | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 180 |  |  | Not Started | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1031 | Integration | FIN | 1031 |  |  | JMW |  |  |  | Consignor Check disbursement feed from AMS to Oracle | Import Consignor Check disbursement feed from AMS |  | AP | Finance | Deloitte |  | Delayed |  | Discovery | No |  | Inbound | Auction Management System* | Oracle ERP Cloud | [9 empty] | Complex |  | 2025-09-19 | [6 empty] | Delayed |  | 2025-09-29 |  | 2025-10-21 |  | 2025-10-21 |  |  | Delayed |  |  |  | Not Started |  |  | NA | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 153 | 2025-09-29 |  | Delayed | 2025-09-19 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1032 | Conversion | FIN | 1032 |  |  | IAA (US & Non US) - Vision |  |  |  | Convert Unapplied AR Receipts - Vision (Auction) | Convert Unapplied AR Receipts (Auction) |  | AR | Finance | RBG |  | #INVALID OPERATION |  |  | No | TBD | NA | Vision(CAN) |  |  |  | Oracle Team 2 | Oracle Team 2 | [5 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 180 |  |  | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1032 | Integration | FIN | 1032 |  |  | B&B |  |  |  | JE (Payments) from Mercury to Oracle | Import Journal Entries (Payments) from Mercury |  | GL | Finance | Deloitte |  | Delayed |  | Discovery | No |  | Inbound | Mercury | Oracle ERP Cloud | [9 empty] | Complex |  | 2025-09-23 | [6 empty] | Delayed |  | 2025-10-27 |  | 2025-11-18 |  | 2025-11-18 |  |  | Delayed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 153 | 2025-10-27 |  | Delayed | 2025-09-23 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-CNV-1033 | Conversion | FIN | 1033 |  |  | RB & IAA |  |  | CNV-008 | AR Receipts (unapplied) | Convert Unapplied AR Receipts (Non-Auction) |  | AR | Finance | RBG |  | Delayed | No | SOW | No | FBDI | NA | EBS, GP | Oracle Cloud ERP |  |  | Deloitte | [6 empty] | Complex |  | 2026-01-30 | 2026-04-29 | [5 empty] | Delayed |  | 2026-03-09 |  | 2026-04-03 |  | 2026-04-03 |  |  | Delayed |  |  |  | Not Started |  |  | April 15: Accountability changed to RBG | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 180 | 2026-03-09 |  | Delayed | 2026-04-29 | CNV | Finance : Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-INT-1033 | Integration | FIN | 1033 |  |  | JMW |  |  |  | Seller Payments for Purchasing Inventory from Oracle Cloud to Kyriba (confirm Payment mode) | Send Electronic Payments to Kyriba (Seller Payments for Purchasing Inventory) |  | AP | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Outbound | Oracle Cloud ERP | Kyriba | [9 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 99 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1034 | Integration | FIN | 1034 |  |  | B&B, JMW | Small Entities (JMW, B&B) | Small Entities |  | Corporate Card Integration for Boom and Bucket, JM Woods through JPMC | Import Corporate Card Transactions for B&B, JMW (JPMC) |  | Expenses | Finance | Deloitte |  | Completed | No | Discovery | Yes |  | Inbound | JPMC | Oracle Cloud ERP |  |  | Deloitte |  |  |  |  | Khaleel |  | Medium |  | 2025-09-23 |  |  | 2025-09-23 |  | Noshin Ali Barnagarwala | 100% - Approved | Completed | No Tech effort | [5 empty] | 2025-11-07 | 100% - Complete | Completed |  |  | 2025-11-14 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Completed | 2025-09-23 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1035 | Conversion | FIN | 1035 |  |  | IAA (US & Non US) |  |  |  | IAA Internal bank account | IAA internal bank account |  | CM | Finance | RBG |  | #INVALID OPERATION | No |  | Duplicate | TBD | NA | GP |  |  |  | Oracle Team 1 | Oracle Team 1 | [5 empty] | Simple | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1035 | Integration | FIN | 1035 |  |  | B&B, JMW |  |  |  | P-Card Integration | Import PCard Transactions for B&B, JMW (JPMC) |  | Expenses | Finance | Deloitte |  | FUT-Pending | No | Discovery | No |  | Inbound |  | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Medium |  |  |  |  | 2025-09-23 |  | Noshin Ali Barnagarwala | 100% - Approved | Completed | No Tech effort | [6 empty] | 100% - Complete | Completed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1036 | Integration | FIN | 1036 |  |  | JMW |  |  | INT-001 | Auction Management System – AR Data* | Import AR Transactions as Journal Entries from AMS |  | GL | Finance | Deloitte |  | #INVALID OPERATION | No | SOW | No |  | Inbound | AMS | Oracle ERP Cloud | [9 empty] | High | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Mar 24: Provide the RAID. (JMW SOW) | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1037 | Conversion | FIN | 1037 |  |  | IAA (US & Non US) - Sage |  |  |  | Fixed Assets - IAA (Sage) | Convert Fixed Assets |  | FA | Finance | Deloitte |  | #INVALID OPERATION |  |  | Duplicate | TBD | NA | Sage accounting | Oracle Cloud ERP |  |  | Deloitte | [6 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Need to figure out the future state of SAGE for IAA . Need discussion with Leads. | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1037 | Integration | FIN | 1037 |  |  | JMW |  |  | INT-002 | Customer Master Data – TBC** | Import Customers from JMW(AMS) |  | AR | Finance | Deloitte |  | Delayed | No | SOW | No |  | Outbound | Oracle Cloud ERP | Auction Management System* | [9 empty] | Complex |  | 2026-01-30 | [6 empty] | Delayed |  | 2026-02-02 |  | 2026-01-30 |  | 2026-01-30 |  |  | Delayed |  |  |  | Not Started |  |  | Mar 24: Provide the RAID. (JMW SOW) | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  |  | 2026-02-02 |  | Delayed | 2026-01-30 | INT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-CNV-1038 | Conversion | FIN | 1038 |  |  | RB & IAA |  |  | CNV-011 | Historical Budget | Convert Historical Budget |  | EPM | Finance | Deloitte |  | #INVALID OPERATION | No | SOW | No |  | NA | TBD | Oracle Cloud ERP |  |  | Deloitte | [6 empty] | Simple | [6 empty] | Vikranth Medury |  | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Need deeper dive for future process | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 90 |  |  | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1038 | Integration | FIN | 1038 |  |  | JMW |  |  | INT-003 | COA – TBC** | COA – TBC** |  | GL | Finance | Deloitte |  | Delayed | No | SOW | No |  | Outbound | Oracle Cloud ERP | Auction Management System* | [9 empty] | Complex |  | 2026-01-30 | [6 empty] | Delayed |  | 2026-02-16 |  | 2026-02-13 |  | 2026-02-13 |  |  | Delayed |  |  |  | Not Started |  |  | Mar 24: Provide the RAID. (JMW SOW) | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  |  | 2026-02-16 |  | Delayed | 2026-01-30 | INT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
SCM-CNV-1039 | Conversion | SCM | 1039 |  |  | RB, IP/Mascus & Others |  |  | CNV-012 | Open Purchase Order | Convert Open Purchase Orders |  | Procurement | Procurement | Deloitte |  | Delayed | No | SOW | No | FBDI | NA | EBS | Oracle Cloud ERP |  |  | Deloitte | [6 empty] | Medium |  | 2026-01-30 |  |  |  |  | Kavitha Sankar |  | Delayed |  | 2026-02-02 |  | 2026-02-18 |  | 2026-02-18 |  |  | Delayed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 117 | 2026-02-02 |  | Delayed | 2026-01-30 | CNV | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Procurement : Sprint 1 | Week 1
FIN-INT-1039 | Integration | FIN | 1039 |  |  | JMW |  |  | INT-004 | Item Master – TBC** | Item Master – TBC** |  | INV | Finance | Deloitte |  | Delayed | No | SOW | No |  | Outbound | Oracle Cloud ERP | Auction Management System* | [9 empty] | Complex |  | 2026-01-30 | [6 empty] | Delayed |  | 2026-02-16 |  | 2026-02-13 |  | 2026-02-13 |  |  | Delayed |  |  |  | Not Started |  |  | Mar 24: Provide the RAID. (JMW SOW) | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  |  | 2026-02-16 |  | Delayed | 2026-01-30 | INT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
SCM-CNV-1040 | Conversion | SCM | 1040 |  |  | IAA (US & Non US) - PitStop |  |  |  | Open Purchase Order from IAA Systems | Convert Open Purchase Orders |  | Procurement | Procurement | RBG |  | #INVALID OPERATION | Yes |  | No | TBD | NA | PitStop/GP | Oracle Cloud ERP | [9 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1040 | Integration | FIN | 1040 |  |  | RB & IAA |  |  |  | AP invoices from ASAP to Oracle Cloud AP and back | Import AP invoices from ASAP and send Payment Status |  | AP | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Inbound & Outbound | ASAP | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Create party if doesn’t exist. In case of Cloud change do we need to take back - need details business process session. | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 153 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
SCM-CNV-1041 | Conversion | SCM | 1041 |  |  | IAA (US & Non US) |  |  |  | Historical PO data from GP (PitStop) | Convert Open Purchase Orders |  | Procurement | Procurement | Deloitte |  | #INVALID OPERATION | No |  | No | TBD | NA | GP | Oracle Cloud ERP |  |  | Deloitte | [6 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | This need further discussion as GP wont be supported by MS going forward. Where do we archive data ? | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1041 | Integration | FIN | 1041 |  |  | IAA |  |  |  | Journal Entries from Vision ( and Frontier) to Oracle Cloud ERP (Manual ADFDi) | Journal Entries from Vision ( and Frontier) to Oracle Cloud ERP (Manual ADFDi) |  | GL | Finance | RBG |  | #INVALID OPERATION | Yes | Discovery | No |  | Inbound | Vision, Frontier (UK) | Oracle ERP Cloud | Sprint 3 | Sprint 3 Sprint 4 | RBG Oracle Team 2 | IAA FINOPS | IAA Team |  |  |  |  | Medium | [7 empty] | 0% - Not Started | #INVALID OPERATION |  | 2026-02-02 |  | 2026-02-16 |  | 2026-02-16 |  | 0% - Not Started | Delayed |  |  |  | Not Started |  |  | 10-nov- (Salvage - Frontier)it is file based interface. Need further discussion -File based design. Create party if doesn’t exist. In case of Cloud change do we need to take back - need details business process session. | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 99 | 2026-02-02 |  | Delayed |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
SCM-CNV-1042 | Conversion | SCM | 1042 |  |  | RB, IP/Mascus & Others |  |  | CNV-013 | Open Receipts | Convert Open Receipts |  | Procurement | Procurement | Deloitte |  | Delayed | No | SOW | No | FBDI | NA | EBS | Oracle Cloud ERP |  |  | Deloitte | [6 empty] | Medium |  | 2026-01-30 |  |  |  |  | Kavitha Sankar |  | Delayed |  | 2026-02-23 |  | 2026-03-11 |  | 2026-03-11 |  |  | Delayed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 117 | 2026-02-23 |  | Delayed | 2026-01-30 | CNV | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Procurement : Sprint 1 | Week 1
FIN-INT-1042 | Integration | FIN | 1042 |  |  | IAA |  |  |  | GL Integration for Vision Canada | GL Integration for Vision Canada |  | GL | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | No |  |  | Vision(CAN) | Oracle ERP Cloud | Sprint 3 | Sprint 3 Sprint 4 | RBG Oracle Team 2 | IAA FINOPS | IAA Team |  |  |  |  | Medium | [7 empty] | 0% - Not Started | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | April 22 - For Phase 2 we will leverage ADFDI for manual upload of the Journal Entries 10 nov - there will be an integration like ASAP | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
SCM-CNV-1043 | Conversion | SCM | 1043 |  |  | IAA (US & Non US) - PitStop |  |  |  | Open Receipts from IAA systems | Convert Open Receipts |  | Procurement | Procurement | Deloitte |  | #INVALID OPERATION | No |  | No | TBD | NA | PitStop/GP | Oracle Cloud ERP |  |  | Deloitte | [6 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Deeper dive needed if we do not have historical data in the future tsate | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1043 | Integration | FIN | 1043 |  |  | IAA |  |  |  | GL Integration for Vision Australia to Oracle Cloud ERP (Manual ADFDi) | GL Integration for Vision Australia |  | GL | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | No |  | Inbound | Vision(AUS) | Oracle ERP Cloud |  |  | RBG Oracle Team 2 | IAA FINOPS | [5 empty] | Medium | [7 empty] | 0% - Not Started | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | April 22 - For Phase 2 we will leverage ADFDI for manual upload of the Journal Entries 10nov - Manual import File based. | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
SCM-CNV-1044 | Conversion | SCM | 1044 |  |  | RB, IP/Mascus & Others | All | Core Modules | CNV-014 | Open Contract and Blanket Agreements | Convert Contract and Blanket Agreements |  | Procurement | Procurement | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | TBD | NA | EBS | Oracle Cloud ERP | Sprint 2 | Sprint 3 | Deloitte |  |  | 2026-08-20 |  | Ian Trost |  | Complex |  | 2026-07-03 | 2026-07-17 |  | 2026-07-17 |  | Deepak Verma | 100% - Approved | Completed | Deepak Verma | [6 empty] | Not Applicable | Not Applicable |  |  |  | Not Applicable | No |  | April 15: No lean spec required, manual conversion (estimated low volume ~ 10-15) | dipriverma@deloitte.ca | 2026-09-10 12:15 |  |  | 180 | 2026-03-16 |  | Not Started | 2026-07-17 | CNV | Procurement : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1044 | Integration | FIN | 1044 |  |  | RB & IAA |  |  |  | AP invoices from Impact to Cloud AP | Import AP Invoices from Impact |  | AP | Finance | Deloitte |  | Delayed |  | Discovery | No |  | Inbound | Impact | Oracle ERP Cloud | [9 empty] | Medium |  | 2026-01-30 | [6 empty] | Delayed |  | 2026-02-16 |  | 2026-03-02 |  | 2026-03-02 |  |  | Delayed |  |  |  | Not Started |  |  | 10 NOV - this VISION CAN.File based design. Create party if doesn’t exist. In case of Cloud change do we need to take back - need details business process session. | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 99 | 2026-02-16 |  | Delayed | 2026-01-30 | INT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
SCM-CNV-1045 | Conversion | SCM | 1045 |  |  | IAA (US & Non US) - PitStop | IAA - ASAP 1 | Core Modules |  | Open Contract and Blanket Agreements - IAA | Convert Contract and Blanket Agreements |  | Procurement | Procurement | Deloitte | Before SIT 1 | Completed | No |  | Yes | TBD | NA | PitStop | Oracle Cloud ERP | Sprint 2 | Sprint 3 |  |  |  | 2026-08-20 |  | Ian Trost |  | Complex |  | 2026-07-03 | 2026-07-17 |  | 2026-07-17 |  | Deepak Verma | 100% - Approved | Completed | Deepak Verma | [6 empty] | Not Applicable | Not Applicable |  |  |  | Not Applicable | No |  |  | raramesh@deloitte.ca | 2026-09-10 14:47 |  |  | 180 |  |  | Not Started | 2026-07-17 | CNV | Procurement : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1045 | Integration | FIN | 1045 |  |  | RB & IAA |  |  |  | AP invoices from IP Web to Cloud AP | Import AP Invoices from IP Web |  | AP | Finance | Deloitte |  | Delayed |  | Discovery | Duplicate |  | Inbound | IP Web | Oracle ERP Cloud | [9 empty] | Medium |  | 2026-01-30 | [6 empty] | Delayed |  | 2026-02-16 |  | 2026-02-13 |  | 2026-02-13 |  |  | Delayed |  |  |  | Not Started |  |  | duplicate of FIN-INT-1024 | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  |  | 2026-02-16 |  | Delayed | 2026-01-30 | INT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
SCM-CNV-1046 | Conversion | SCM | 1046 |  |  | RB, IP/Mascus & Others |  |  | CNV-015 | Requisitions | Convert Open Requisitions |  | Procurement | Procurement | Deloitte |  | Delayed | No | SOW | No | FBDI | NA | EBS | Oracle Cloud ERP |  |  | Deloitte | [6 empty] | Complex |  | 2026-01-30 |  |  |  |  | Ramya Raveendranathan |  | Delayed |  | 2026-02-23 |  | 2026-03-20 |  | 2026-03-20 |  |  | Delayed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 180 | 2026-02-23 |  | Delayed | 2026-01-30 | CNV | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Procurement : Sprint 1 | Week 1
FIN-INT-1046 | Integration | FIN | 1046 |  | DPP | RB | RB DPP | Core - DPP |  | AP invoices from DPP to Oracle Cloud AP | Import AP invoices from DPP |  | AP | Finance | RBG |  | Completed | Yes | Discovery | Yes |  | Inbound | DPP | Oracle Cloud ERP | Sprint 1 | Sprint 1 Sprint 2 | Oracle Team 2 | Oracle Team 2 | DPP Team | 2026-07-17 | 50% - Reviewed | Sharjeel | WIP | Complex | https://ritchiebros.atlassian.net/browse/DIG-3243 | 2026-08-21 | 2026-09-18 | 2026-07-17 | 2026-07-17 |  | Kipshita Desai | 75% - Feedback Incorporated | Completed | Yan Pang | 2026-06-08 | 2026-05-25 | 2026-06-30 |  | 2026-06-16 | 2026-07-17 | 100% - Complete | Completed | 2026-07-17 | 2026-05-05 | 2026-07-08 | Completed |  |  | create if not exist | dipriverma@deloitte.ca | 2026-08-28 08:06 |  |  | 153 | 2025-11-17 |  | Completed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 2 | Week 1 | DPP
SCM-CNV-1047 | Conversion | SCM | 1047 |  |  | IAA (US & Non US) - PitStop |  |  |  | Requisitions from IAA | Convert Open Requisitions |  | Procurement | Procurement | RBG |  | #INVALID OPERATION | No |  | No | TBD | NA | PitStop | Oracle Cloud ERP |  |  |  | Oracle Team 1 | [5 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 180 |  |  | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1047 | Integration | FIN | 1047 |  |  | RB & IAA |  |  |  | AP invoices from AS400 to Oracle Cloud AP and back | Import AP invoices from AS400 and send Payment Status |  | AP | Finance | Deloitte |  | Delayed |  | Discovery | No |  | Inbound & Outbound | AS400 | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Complex |  | 2026-01-30 | [6 empty] | Delayed |  | 2026-02-02 |  | 2026-02-24 |  | 2026-02-24 |  |  | Delayed |  |  |  | Not Started |  |  | NA | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 153 | 2026-02-02 |  | Delayed | 2026-01-30 | INT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-INT-1048 | Integration | FIN | 1048 |  |  | RB & IAA |  |  |  | AP invoices from Pitstop to Oracle Cloud AP | Import AP Invoices from Pitstop |  | AP | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Inbound | PitStop | Oracle ERP Cloud | [9 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Not required | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1049 | Conversion | FIN | 1049 |  |  | B&B |  |  |  | Supplier Conversion for BB | Convert B&B Suppliers |  | AP | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | NA | B&B |  |  |  | Deloitte | [6 empty] | Manual | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1049 | Integration | FIN | 1049 |  |  | RB |  |  |  | Customer from SaleSite to Oracle Cloud AR​ | Import Customers from SaleSite |  | AR | Finance | Deloitte |  | #INVALID OPERATION | Yes | Discovery | No |  | Inbound | SaleSite | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Apr 17 - Not in scope because customer data will flow from CDM DDP release dependent | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 153 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1050 | Conversion | FIN | 1050 |  |  | JMW |  |  |  | Customers | Convert Customers from AMS (JMW) |  | AR | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | NA | JMW |  |  |  | Deloitte | [6 empty] | Manual | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1050 | Integration | FIN | 1050 |  |  | RB & IAA |  |  |  | Customer from DPP to Oracle Cloud AR​ | Import Customers from DPP |  | AR | Finance | Deloitte |  | #INVALID OPERATION | Yes | Discovery | No |  | Inbound | DPP | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Create if does not exist | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 153 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1 | DPP
FIN-CNV-1051 | Conversion | FIN | 1051 |  |  | JMW |  |  |  | AR Open Invoices | Convert AR Open Invoices (JMW) |  | AR | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | NA | JMW |  |  |  | Deloitte | [6 empty] | Manual | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1051 | Integration | FIN | 1051 |  |  | RB & IAA |  |  |  | Customer from IP Web to Oracle Cloud AR​ | Import Customers from IP Web |  | AR | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Inbound | IP Web | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Create if does not exist | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 153 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
SCM-CNV-1052 | Conversion | SCM | 1052 |  |  | DDI |  |  |  | Convert DDI Suppliers - Vertitred? | Convert DDI Suppliers - Vertitred? |  | Procurement | Procurement | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | NA | DDI | Oracle Cloud ERP |  |  | Deloitte | [6 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 180 |  |  | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1052 | Integration | FIN | 1052 |  |  | RBFS | RBFS |  |  | Customer from Salesforce to Oracle Cloud AR​ | Import Customers from Salesforce |  | AR | Finance | Deloitte |  | #INVALID OPERATION | No | Discovery | No |  | Inbound | RB Salesforce | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | only lien holders - AP ONLY | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 153 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1 | Salesforce
FIN-CNV-1053 | Conversion | FIN | 1053 |  |  | JMW |  |  |  | Supplier Conversion for JM Woods | Convert Contract and Blanket Agreements (JMW) |  | AP | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | NA | JMW | Oracle Cloud ERP |  |  | Deloitte | [6 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 180 |  |  | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1053 | Integration | FIN | 1053 |  |  | RB & IAA |  |  |  | AR invoices from SaleSite to Oracle Cloud AR​ | Import AR Invoices from SaleSite |  | AR | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Inbound | SaleSite | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | DDP release dependent | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 99 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1054 | Conversion | FIN | 1054 |  |  | IAA |  |  |  | Open projects, Tasks from IAA |  |  | Projects | Finance | RBG |  | #INVALID OPERATION |  |  | Duplicate | TBD | NA | TBD | Oracle Cloud ERP | [18 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Apr 23: Duplicate of FIN-CNV-1048 | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1054 | Integration | FIN | 1054 |  | DPP | RB | RB DPP | Core - DPP |  | AR invoices from DPP to Oracle Cloud AR​ | Import AR Invoices, Credit Memos from DPP |  | AR | Finance | RBG |  | Completed | Yes | Discovery | Yes |  | Inbound | DPP | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 | Oracle Team 2 | Oracle Team 2 | DPP Team | 2026-07-17 | 50% - Reviewed | Sharjeel | WIP | Complex | https://ritchiebros.atlassian.net/browse/DIG-3243 | 2026-08-28 | 2026-09-18 | 2026-07-13 | 2026-07-17 |  | Krish Sharma | 75% - Feedback Incorporated | Completed | Yan Pang | 2026-06-22 | 2026-06-22 | 2026-07-06 |  | 2026-07-06 | 2026-07-17 | 100% - Complete | Completed | 2026-07-17 | 2026-06-22 | 2026-07-08 | Completed |  |  | Create if does not exist | dipriverma@deloitte.ca | 2026-08-28 08:06 |  |  | 99 |  |  | Completed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1 | DPP
FIN-CNV-1055 | Conversion | FIN | 1055 |  |  | JMW |  |  |  | Fixed Asset Conversion for JM Woods | Convert Fixed Asset (JMW) - Done |  | FA | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | NA | JMW | Oracle Cloud ERP |  |  | Deloitte | [6 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1055 | Integration | FIN | 1055 |  |  | RB & IAA |  |  |  | AR invoices from IP Web to Oracle Cloud AR​ | Import AR Invoices from IP Web |  | AR | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | Duplicate |  | Inbound | IP Web | Oracle ERP Cloud | [9 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | duplicate of FIN-INT-1055 | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 99 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1056 | Conversion | FIN | 1056 |  |  | Mascus | Mascus | Mascus |  | Convert MASCUS Customers, Accounts, Sites, Contacts | Convert MASCUS Customers, Accounts, Sites, Contacts | 2 | AR | Finance | Deloitte | Before SIT 1 | Completed |  | RBG Discovery | Yes | TBD | NA | EBS | Oracle Cloud ERP | Sprint 2 | Sprint 3 | Deloitte | Oracle IFS Team | Jun, Martijn |  |  | Martijn Verhoeff | WIP | Medium |  | 2026-07-03 | 2026-08-21 |  | 2026-09-04 | 2026-09-04 | Venkata Kiran Kumar Pallantla | 100% - Approved | Completed | Saikat Banerjee | 2026-08-17 |  | 2026-09-02 |  | 2026-09-02 |  | Not Applicable | Not Applicable |  |  |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-09-10 12:15 |  |  | 117 |  |  | Delayed | 2026-08-21 | CNV | Finance : Sprint 3 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1056 | Integration | FIN | 1056 |  |  | RB |  |  |  | AR invoices from Salesforce to Oracle Cloud AR​ | Import AR Invoices from Salesforce |  | AR | Finance | RBG |  | #INVALID OPERATION | Yes | Discovery | No |  | Inbound | RB Salesforce | Oracle ERP Cloud | [9 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Apr 29: Only applicable for RB and not needed for Future state Apr 22: We won't need AR Invoices from Salesforce, confirm with RBG. | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 99 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1 | Salesforce
FIN-CNV-1057 | Conversion | FIN | 1057 |  |  | Mascus | Mascus | Mascus |  | Convert Open MASCUS Service Contracts | Convert Open MASCUS Service Contracts |  | SM | Procurement | Deloitte | Before SIT 1 | Delayed |  | RBG Discovery | Yes | TBD | NA | EBS | Oracle Cloud ERP | Sprint 3 | Sprint 3 | Deloitte | Deloitte | Jun, Martijn | 2026-08-21 | 75% - Feedback Incorporated | Jenn Mikalchuk, Martijn Verhoeff | WIP | Medium |  | 2026-07-03 | 2026-08-24 |  |  |  | Deepak Verma | 50% - Reviewed | Delayed | Saikat Banerjee | 2026-08-17 |  | 2026-09-02 |  | 2026-09-02 |  | 25% - Tech Spec - In Progress | In Progress |  |  |  | Not Applicable | No |  | question to Breada team | dipriverma@deloitte.ca | 2026-09-10 12:15 |  |  | 117 |  |  | Delayed | 2026-08-24 | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1057 | Integration | FIN | 1057 |  |  | RB & IAA |  |  |  | AR invoices from Oracle Cloud AR to Buzon E.​ | Send AR invoices Details to Buzon E (Mexico). (Current process Manual Integration ) |  | AR | Finance |  |  | #INVALID OPERATION | No | Discovery | No |  | Outbound | Oracle Cloud ERP | Buzon E |  |  | Deloitte | [6 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | is e-invoicing ? Clarification needed | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 99 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1058 | Conversion | FIN | 1058 | TRUE |  | Mascus | Mascus | Mascus |  | Convert MASCUS Credit cards details for customer with open orders | Convert MASCUS Credit cards details for customer with open orders |  | AR | Finance | Deloitte | After SIT 1 | Delayed |  | RBG Discovery | Yes | TBD | NA | EBS | Oracle Cloud ERP | Sprint 2 | Sprint 3 | Deloitte | Deloitte | Jun, Martijn |  |  | Jenn Mikalchuk, Martijn Verhoeff | WIP | Medium |  | 2026-07-03 | 2026-08-21 |  | 2026-09-04 | 2026-09-04 | Venkata Kiran Kumar Pallantla | 100% - Approved | Completed | Saikat Banerjee | 2026-07-20 |  | 2026-08-05 |  | 2026-08-05 |  | 0% - Not Started | Delayed |  |  |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-09-10 12:15 |  |  | 117 |  |  | Delayed | 2026-08-21 | CNV | Finance : Sprint 3 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-CNV-1058 | Conversion | FIN | 1058 | TRUE |  | Mascus | Mascus |  |  | MASCUS Credit cards details for customer with open orders | MASCUS Credit cards details for customer with open orders | 1 | AR | Finance |  |  | Delayed |  | RBG Discovery | Duplicate | TBD | NA | Mascus | Oracle Cloud ERP | Sprint 2 | Sprint 2 Sprint 3 | Deloitte | Deloitte | MASCUS Team |  |  | Sharjeel | WIP | Medium |  | 2026-07-03 |  |  |  |  | Harsh Rawal | 0% - Not Started | Delayed | Saikat Banerjee | 2026-07-13 |  | 2026-07-29 |  | 2026-07-29 |  | 0% - Not Started | Delayed |  |  |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 117 |  |  | Delayed | 2026-07-03 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-INT-1058 | Integration | FIN | 1058 |  |  | RB & IAA |  |  |  | AR receipts from FIS to Oracle Cloud AR​ | Import AR Receipts from FIS |  | AR | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Inbound | IFS | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | is is FIS ?? | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 99 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1059 | Integration | FIN | 1059 |  |  | RB |  |  |  | AR receipts from Stripe to Oracle Cloud AR​ | Import AR Receipts from Stripe (or DPP?) |  | AR | Finance |  |  | #INVALID OPERATION | Yes | Discovery | No |  | Inbound | Stripe | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | covered in DPP - need low level discussion. | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 99 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1060 | Conversion | FIN | 1060 |  |  | RBG | IAA - ASAP 1 IAA - CAN & UK |  |  | Leases, Schedule from IAA | Leases, Schedule |  | Lease Accounting | Finance | Deloitte |  | Delayed | Yes | RBG Discovery | Duplicate | TBD | NA | Co-star | Oracle Cloud ERP | Sprint 1 | Sprint 2 Sprint 3 |  | Oracle Team 1 |  |  |  | Khaleel |  | Medium |  | 2026-07-10 | 2026-07-17 |  |  |  |  | 0% - Not Started | Delayed | Saikat Banerjee | 2026-07-13 |  | 2026-07-29 |  | 2026-07-29 |  | 0% - Not Started | Delayed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 117 |  |  | Delayed | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-INT-1060 | Integration | FIN | 1060 |  | IP | RB | IronPlanet RB DPP | IP |  | AR receipts from Paysafe (IP Web) to Oracle Cloud AR​ | Import AR Receipts from Paysafe |  | AR | Finance | RBG |  | Dev-In Progress | Yes | Discovery | Yes |  | Inbound | Paysafe | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 2 | Oracle Team 2 | IP Web Team | 2026-09-30 | 25% - Drafted | Sharjeel | Not Started | Medium | https://ritchiebros.atlassian.net/jira/software/projects/IOCM/summary https://ritchiebros.atlassian.net/wiki/spaces/~712020f2d6811a620a4640845080fe8faab33a/pages/3785162822/IronPlanet+Oracle+Cloud+Migration | 2026-09-25 | 2026-10-09 | 2026-08-17 |  |  | Sharjeel | 25% - Drafted | In Progress | Yan Pang | 2026-10-09 |  | 2026-10-23 |  | 2026-10-23 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-12-09 |  | Not Started |  |  | optimal pay - DPP will replace whole. Need further discussion on time line. | dipriverma@deloitte.ca | 2026-08-28 08:06 |  |  | 99 |  |  | Not Started | 2026-10-09 | INT | Finance : SIT 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : SIT 2 | Week 1
FIN-INT-1061 | Integration | FIN | 1061 |  |  | Mascus |  |  |  | AR receipts from Ayden to Oracle Cloud AR​ | Import AR Receipts from Adyen(Fund Capturing process) |  | AR | Finance | RBG |  | #INVALID OPERATION | Yes | Discovery | Duplicate |  | Inbound | Ayden (Mascus) | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | For MASCUS we need deep dive - deisgn session | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 99 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1062 | Conversion | FIN | 1062 |  |  | RB and Mascus | All | Core Modules | CNV-019 | Unreconciled Cash Transactions | Unreconciled Cash Transactions |  | CM | Finance | Deloitte | Before SIT 1 | Completed | No | New Requirement | Yes | FBDI | NA | EBS | Oracle Cloud ERP | Sprint 2 | Sprint 3 | Deloitte |  |  | 2026-08-20 |  |  |  | Medium |  |  | 2026-07-17 |  | 2026-03-31 | 2026-04-22 | Deepankar Gera | 100% - Approved | Completed | Saikat Banerjee | 2026-06-15 | 2026-06-15 | 2026-06-26 |  | 2026-06-26 | 2026-07-03 | 100% - Complete | Completed |  |  |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-09-10 12:15 |  |  | 90 |  |  | Completed | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
SCM-INT-1062 | Integration | SCM | 1062 |  |  | RB & IAA, MARS |  |  |  | Supplier Integration with MARS (to support Purchase Orders & Receipts) | (Supplier search)Send Supplier Details to MARS to support Purchase Orders & Receipts |  | Procurement | Procurement |  |  | #INVALID OPERATION |  | Discovery | No |  | Outbound | Oracle Cloud ERP | MARS |  |  | Deloitte | [6 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Need further discussion about soruce | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 153 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1063 | Conversion | FIN | 1063 |  |  | RBFS | RBFS | Core Modules |  | Convert RBFS Customers | Sync RBFS customers |  | AR | Finance | Deloitte | Before SIT 1 | Completed | No | RBG Discovery | Yes |  | NA | EBS | Oracle Cloud ERP | Sprint 2 | Not Applicable |  |  |  | 2026-08-20 |  | Jenn Mikalchuk |  | Medium |  | 2026-07-10 | 2026-07-17 | 2026-07-17 | 2026-09-04 |  | Syed Imran Waheed | 100% - Approved | Completed | Harsh Rawal | [6 empty] | Not Applicable | Not Applicable |  |  |  | Not Applicable | No |  | Need further discussion - can we create customer until they purchase from RB2.0/Leg | raramesh@deloitte.ca | 2026-09-10 14:47 | [5 empty] | Not Started | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
SCM-INT-1063 | Integration | SCM | 1063 |  |  | RB & IAA, MARS |  |  |  | Two-way data Integrations (Sync Categories, UoM with Oracle, PO Status) | Two way data integration to sync Categories, UoM, PO Status |  | Procurement | Procurement | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Inbound & Outbound | Oracle ERP Cloud | MARS |  |  | Deloitte | [6 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Valid Integration | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 153 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1064 | Conversion | FIN | 1064 |  |  | RB | RB Non-Auction | STAT | CNV-020 | STAT Ledger: Conversion Script | STAT Ledger: Conversion Script |  | GL | Finance | Deloitte | Not Applicable | Completed | No | Business need | Yes | PLSQL | NA | EBS | Oracle Cloud ERP | Sprint 1 | Sprint 1 | Deloitte | Deloitte |  |  |  | Jenn Mikalchuk |  | Medium |  |  | 2026-05-08 |  | 2026-05-08 |  | Deepankar Gera | 100% - Approved | Completed | Piyush Ojha | 2026-05-11 |  | 2026-05-27 |  | 2026-05-27 | 2026-05-29 | 100% - Complete | Completed | 2026-06-01 | 2026-06-12 |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-09-10 12:15 |  |  | 117 |  |  | Completed | 2026-05-08 | CNV | Finance : Gap Sprint | [7 empty] | Finance : Sprint 2
FIN-INT-1064 | Integration | FIN | 1064 |  | IAA ASAP | IAA | IAA - ASAP 1 | IAA |  | ASAP Supplier Creation | Writeback Suppliers to ASAP (Hold Info, supplier ID, banking details) |  | AP | Finance | RBG |  | Dev-In Progress | Yes | Discovery | Yes |  | Outbound | Oracle Cloud ERP | ASAP | Sprint 4 | Sprint 4 Sprint 5 | RBG Oracle Team 1 | Oracle Team 1 | IAA Team | 2026-11-13 | 25% - Drafted | Khaleel | WIP | Complex | https://ritchiebros.atlassian.net/issues/?filter=29016 | 2026-08-21 | 2026-09-25 | 2026-08-17 |  |  | RBG | 50% - Reviewed | In Progress | Michael Ortega | 2026-10-05 |  | 2026-10-27 |  | 2026-10-27 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-12-05 |  | Not Started |  |  | Apr 16 - Need supplier hold information, supplier ID, and banking details status Deep dive req. for defining suppliers and integrating with procurement process | dipriverma@deloitte.ca | 2026-08-28 08:06 |  |  | 153 |  |  | Not Started | 2026-09-25 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : SIT 2 | Week 1
SCM-INT-1065 | Integration | SCM | 1065 |  |  | RB & IAA, MARS |  |  |  | Procurement (Purchase Orders) Integrations with MARS PO | Import Purchase Orders from Mars |  | Procurement | Procurement |  |  | #INVALID OPERATION | Yes | Discovery | Duplicate |  | Inbound | MARS | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Create party if doesn’t exist. | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 99 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
SCM-INT-1066 | Integration | SCM | 1066 |  |  | RB & IAA |  |  |  | Supplier Price Updates to BP Agreements (Hosted Catalog) | Import Supplier Price Update (BPA) |  | Procurement | Procurement | Deloitte |  | #INVALID OPERATION | No | Discovery | No |  | Inbound | TBD | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Need further discussion. | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 99 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
SCM-INT-1067 | Integration | SCM | 1067 |  |  | RB & IAA, MARS |  |  |  | MARS Receipts integrated to Oracle | MARS Receipts integrated to Oracle |  | Procurement | Procurement |  |  | #INVALID OPERATION |  | Discovery | Duplicate |  | Inbound | MARS | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Need further discussion. | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 99 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1068 | Integration | FIN | 1068 |  |  | RBA |  |  |  | Journals Integration | Journals Integration |  |  | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | Duplicate |  | Inbound | DPP | Oracle ERP Cloud | [18 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | duplicate of FIN-INT-1007 (INT-007) | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1 | DPP
FIN-INT-1069 | Integration | FIN | 1069 |  |  | RBA |  |  |  | AR Transactions Integration | AR Transactions Integration |  | AR | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | Duplicate |  | Inbound | DPP | Oracle ERP Cloud | [18 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | duplicate of FIN-INT-1054 | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1 | DPP
FIN-INT-1070 | Integration | FIN | 1070 | TRUE |  | RB |  |  |  | AR Receipts Integration-DPP | AR Receipts Integration-DPP |  | AR | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | Duplicate |  | Inbound | FIS | Oracle ERP Cloud |  |  | Oracle Team 2 | Oracle Team 2/IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1070 | Integration | FIN | 1070 | TRUE | DPP | RB | RB DPP | Core - DPP |  | AR Receipts Integration from DPP | AR Receipts Integration - DPP |  | AR | Finance | RBG |  | Delayed | Yes | RBG Discovery | Yes |  | Inbound | DPP | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 | Oracle Team 2 | Oracle Team 2 | DPP Team | 2026-08-07 | 75% - Feedback Incorporated | Sharjeel | WIP | Complex | https://ritchiebros.atlassian.net/browse/DIG-3243 | 2026-07-17 | 2026-09-18 | 2026-07-17 |  |  | Krish Sharma | 75% - Feedback Incorporated | In Progress | Yan Pang | 2026-07-20 | 2026-07-20 | 2026-07-17 |  | 2026-07-17 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-09-08 |  | Delayed |  |  |  | nivnath@deloitte.com | 2026-09-09 05:36 | [5 empty] | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1 | DPP
FIN-INT-1071 | Integration | FIN | 1071 |  |  | RBA |  |  |  | AP Invoices Integration | AP Invoices Integration |  | AP | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | Duplicate |  | Inbound | DPP | Oracle ERP Cloud | [18 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | duplicate of FIN-INT-1046 | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1 | DPP
FIN-INT-1073 | Integration | FIN | 1073 |  |  | RBA |  |  |  | Common Customer Derivation Utility | Common Customer Derivation Utility |  | AR | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | Duplicate |  | NA | DPP | Oracle ERP Cloud |  |  | RBG Oracle Team 1 | Oracle Team 1 | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Apr 23: Duplicate of FIN-INT-1184 Re-design | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1 | DPP
FIN-INT-1074 | Integration | FIN | 1074 |  | DPP | RB | RB DPP | Core - DPP |  | Update consignor totals to Events Framework | Update consignor totals to Events Framework(rate through historical transaction and published to EBS Event in current system) |  | AP/AR | Finance | RBG |  | Delayed | TBD | RBG Discovery | No |  | Outbound | DPP(Current System EBS) | Yes | Sprint 2 | Sprint 2 Sprint 3 | Oracle Team 2 | Oracle Team 2 | DPP Team |  |  | Sharjeel | WIP | Complex | https://ritchiebros.atlassian.net/browse/DIG-3243 | 2026-05-29 | 2026-07-17 | 2026-05-29 |  |  | Sharjeel | 25% - Drafted | Delayed | Yan Pang | [6 empty] | 25% - Tech Spec - In Progress | In Progress |  |  |  | Not Started |  |  | Re-design - Need to confirm on this whether this is needed or not | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-07-17 | INT | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1 | DPP
FIN-INT-1075 | Integration | FIN | 1075 |  | DPP | RB | RB DPP | Core - DPP |  | Consignor Single Search API for Control Tower | Consignor Single Search API for Control Tower |  | AP | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Outbound | TE | DPP | Sprint 3 | Sprint 3 Sprint 4 |  |  | DPP: Steph Albee, JD; Salesforce: Katie, Edward Chan |  |  | Sharjeel | Not Started | Medium | https://ritchiebros.atlassian.net/browse/DIG-3243 | 2026-08-07 | 2026-09-18 |  |  |  | hganasuni@ritchiebros.com | 50% - Reviewed | In Progress | Kyle | 2026-08-10 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 |  | 25% - Tech Spec - In Progress | In Progress |  |  |  | Not Started |  |  | This will happen through TE. | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1 | DPP
FIN-INT-1076 | Integration | FIN | 1076 |  | DPP | RB | RB DPP | Core - DPP |  | Consignor Bulk Single Search API for Control Tower | Consignor Bulk Single Search API for Control Tower |  | AP | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Outbound | TE | DPP | Sprint 3 | Sprint 3 Sprint 4 |  |  | DPP: Steph Albee, JD; Salesforce: Katie, Edward Chan |  |  | Sharjeel | Not Started | Medium | https://ritchiebros.atlassian.net/browse/DIG-3243 | 2026-08-07 | 2026-09-18 |  |  |  | hganasuni@ritchiebros.com | 50% - Reviewed | In Progress | Kyle | 2026-08-10 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 |  | 25% - Tech Spec - In Progress | In Progress |  |  |  | Not Started |  |  | This will happen through TE. | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1 | DPP
FIN-INT-1077 | Integration | FIN | 1077 |  |  | RB | RB DPP |  |  | Outbound Integration to send the invoices items details for Bid Limits Calculation(Current system EBS to BLA - Subsystem in DPP) | Outbound Integration to send the invoices items details for Bid Limits Calculation(Current system EBS to BLA - Subsystem in DPP) |  | AR | Finance | RBG |  | Delayed | Yes | RBG Discovery | No |  | Outbound | Oracle ERP Cloud | BLA (DPP) | Sprint 3 | Sprint 3 Sprint 4 | Oracle Team 2 | Oracle Team 2 | DPP Team |  |  | Sharjeel | Not Started | Medium | https://ritchiebros.atlassian.net/browse/DIG-3243 | 2026-05-29 | 2026-08-14 | 2026-05-29 |  |  | RBG | 25% - Drafted | Delayed | [7 empty] | 25% - Tech Spec - In Progress | In Progress |  |  |  | Not Started |  |  | Re-design - Still in discussion. EBS is responsible for bid limits. Gavin and Tenny. | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-08-14 | INT | Finance : Sprint 3 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1 | DPP
FIN-INT-1078 | Integration | FIN | 1078 |  | DPP | RB | RB DPP | Core - DPP |  | Two-way integration for Customer Notes between DPP CT and AR (Invoice, Credit & Debit Memos) | Two-way integration for Customer Notes between DPP CT and AR (Invoice, Credit & Debit Memos) |  | AR | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Inbound & Outbound | DPP | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 | Oracle Team 2 | Oracle Team 2 | DPP Team | 2026-09-04 | 0% - Not Started | Sharjeel | WIP | Medium | https://ritchiebros.atlassian.net/browse/DIG-3243 | 2026-08-14 | 2026-09-18 | 2026-08-10 |  |  | Krish Sharma | 25% - Drafted | In Progress | Zakaria Lahdami | 2026-08-17 | 2026-08-24 | 2026-08-14 |  | 2026-08-21 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  | Re-design | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1 | DPP
FIN-INT-1079 | Integration | FIN | 1079 |  | DPP | RB | RB DPP | Core - DPP |  | Interface to Send Consignor Payout Details to DPP CT | Interface to Send Consignor Payout Details to DPP CT |  | AP | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Outbound | Oracle Cloud ERP | DPP | Sprint 3 | Sprint 3 Sprint 4 | Oracle Team 2 | Oracle Team 2 | DPP: Steph Albee, Vineet; | 2026-08-31 | 0% - Not Started | Sharjeel | Not Started | Medium | https://ritchiebros.atlassian.net/browse/DIG-3243 | 2026-08-14 | 2026-09-18 | 2026-07-13 |  |  | Kipshita Desai | 25% - Drafted | In Progress | Yan Pang | 2026-08-17 | 2026-08-24 | 2026-08-14 |  | 2026-08-21 |  | 0% - Not Started | In Progress |  | 2026-09-20 |  | Not Started |  |  | Re-design | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1 | DPP
FIN-INT-1080 | Integration | FIN | 1080 |  | DPP | RB | RB DPP | Core - DPP |  | Interface to Send Out of Band Receipt Applications to DPP CT | Interface to Send Out of Band Receipt Applications to DPP Control Tower |  | AR | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Outbound | Oracle Cloud ERP | DPP | Sprint 3 | Sprint 3 Sprint 4 | Oracle Team 2 | Oracle Team 2 | DPP Team | 2026-08-31 | 0% - Not Started | Sharjeel | Not Started | High | https://ritchiebros.atlassian.net/browse/DIG-3243 | 2026-08-21 | 2026-09-18 |  |  |  | Krish Sharma | 25% - Drafted | In Progress | Yan Pang | 2026-08-24 | 2026-08-24 | 2026-08-21 |  | 2026-08-21 |  | 0% - Not Started | In Progress |  | 2026-09-20 |  | Not Started |  |  | Re-design | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1 | DPP
FIN-INT-1081 | Integration | FIN | 1081 |  | Oracle Core | RB, IAA & IP | All | Core - DPP |  | Common Service to reprocess Failed Messages & Update ATP Staging Tables | OIC process to update processing status in GL/AP/AR Staging tables (Current State - Concurrent Program) |  | GL/AP/AR | Finance | RBG |  | F-Spec-In Progress | Yes | RBG Discovery | Yes |  | NA | Oracle Cloud ERP | Oracle ATP | Sprint 3 | Sprint 3 Sprint 4 | Oracle Team 2 | Oracle Team 2 | Oracle Team |  |  | Sharjeel | Not Started | Medium |  | 2026-07-17 | 2026-09-18 |  |  |  | hganasuni@ritchiebros.com | 25% - Drafted | In Progress | Yan Pang | [6 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Re-design | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1082 | Integration | FIN | 1082 |  | DPP | RB | RB DPP | Core - DPP |  | Build a mechanism/process to SOX reconciliation process for different systems like DPP etc.(GL, AR and AP)(Current process Users generate extract from DPP control tower which uses EBS materialized view) | Build a mechanism/process to SOX reconciliation process for different systems like DPP etc.(GL, AR and AP)(Current process Users generate extract from DPP control tower which uses EBS materialized view) |  | GL/AP/AR | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Outbound | Oracle Cloud ERP | DPP | Sprint 4 | Sprint 4 Sprint 5 | Oracle Team 2 | Oracle Team 2 | DPP Team | 2026-08-31 | 0% - Not Started | Sharjeel | Not Started | Complex | https://ritchiebros.atlassian.net/browse/DIG-3243 | 2026-08-21 | 2026-09-18 |  |  |  | Sharjeel | 25% - Drafted | In Progress | Yan Pang | 2026-08-31 | 2026-08-31 | 2026-08-28 |  | 2026-08-28 |  | 0% - Not Started | In Progress |  | 2026-09-20 |  | Not Started |  |  | this should cover all systems - DPP, ASAP, SFDC etc. for SOX audit | suchisahoo@deloitte.com | 2026-08-30 22:44 | [5 empty] | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1 | DPP
FIN-INT-1083 | Integration | FIN | 1083 |  | CDW | All | All |  |  | Financial Data (GL, AP, AR) import to CDW | Data to sent to CDW to be consumed by Planning & Analytics |  | GL/AP/AR | Finance | RBG |  | Delayed | Yes | RBG Discovery | No |  | Outbound | Oracle Cloud ERP | CDW (Big Data -> Snowflake) | Sprint 4 | Sprint 4 Sprint 5 | TBD | Oracle Team 2 | CDW Team |  |  | Sharjeel |  | High |  | 2026-07-17 | 2026-09-04 | 2026-07-13 |  |  | RBG | 25% - Drafted | Delayed | Khaleel Shaik | [6 empty] | 25% - Tech Spec - In Progress | In Progress |  |  |  | Not Started |  |  | Re-design/Report | nivnath@deloitte.com | 2026-09-06 22:40 | [5 empty] | Not Started | 2026-09-04 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1084 | Integration | FIN | 1084 |  |  | RBA |  |  |  | Marketing AMS Interface | Marketing AMS Interface |  | AR | Finance | RBG |  | #INVALID OPERATION | No | RBG Discovery | Duplicate |  | Outbound | DPP | Oracle ERP Cloud/CDW ( Big Data -> Snowflake) |  |  | Oracle Team 2 | Oracle Team 2 | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Apr 22: To be clarified in the Snowflake/CDW workshops. Re-design | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1 | DPP
FIN-INT-1085 | Integration | FIN | 1085 |  |  | RBA |  |  |  | Updated Materialized Views for CDW Consumption | Updated Materialized Views for CDW Consumption |  | AR | Finance | RBG |  | #INVALID OPERATION | No | RBG Discovery | Duplicate |  | Outbound | DPP | Oracle ERP Cloud/CDW ( Big Data -> Snowflake) |  |  | Oracle Team 2 | Oracle Team 2 | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Apr :29 - duplicate of FIN-INT-1155Apr 22: To be clarified in the Snowflake/CDW workshops. Re-design | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1 | DPP
FIN-INT-1086 | Integration | FIN | 1086 |  |  | RBA |  |  |  | Modified XXRBA - Refresh 5-Year Stats (Current EBS Job send 5 year of DPP data set of Auction Transaction data to Marketing Team EBS -> CDW current system flow) | Modified XXRBA - Refresh 5-Year Stats (Current EBS Job send 5 year of DPP data set of Auction Transaction data to Marketing Team EBS -> CDW current system flow) |  | AR | Finance | RBG |  | #INVALID OPERATION | No | RBG Discovery | No |  | Outbound | DPP | TBD |  |  | Oracle Team 2 | Oracle Team 2 | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Apr-29: Current EBS Job send 5 year of Apr 22: To be clarified in the Snowflake/CDW workshops. Re-design | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1 | DPP
FIN-INT-1088 | Integration | FIN | 1088 |  | IAA ASAP | IAA | IAA - ASAP 1 | IAA |  | AR -Buyer Charges/Invoices (IAA) | AR -Buyer Charges/Invoices (IAA) |  | AR | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Inbound & Outbound | ASAP | Oracle Cloud ERP | Sprint 3 | Sprint 4 Sprint 5 | Oracle Team 2 | IAA FINOPS | IAA Team: Preetham | 2026-12-14 | 25% - Drafted | Sharjeel | Not Started | Medium | https://ritchiebros.atlassian.net/issues?filter=29016 https://rbauction.sharepoint.com/:w:/r/sites/VAN-FINFinanceTransformation-OracleCloud-PHASE2/Shared%20Documents/Oracle%20Cloud%20-%20PHASE%202/6.0%20Technology/RBG_Working_Files/RBG%20Core%20Integrations%20with%20Source%20Systems/ASAP%20to%20Oracle%20Cloud%20Transaction%20Flow/ASAP%20to%20Oracle%20Cloud%20-%20Transaction%20Flow.docx?d=w85345de710104dec96c3ff25c84e8149&csf=1&web=1&e=028RnV ​https://rbauction.sharepoint.com/:x:/r/sites/VAN-FINFinanceTransformation-OracleCloud-PHASE2/Shared%20Documents/Oracle%20Cloud%20-%20PHASE%202/6.0%20Technology/RBG_Working_Files/RBG%20Core%20Integrations%20with%20Source%20Systems/AR%20Transactions%20Integration/IAA/IAA%20AR%20Transaction%20Fusion%20Mapping.xlsx?d=w5995ae6ff9f44971806cd42116ab1406&csf=1&web=1&e=J8tONk | 2026-08-28 | 2026-09-25 | 2026-07-13 |  |  | Stephen Park | 50% - Reviewed | In Progress | Michael Ortega | 2026-09-14 |  | 2026-09-11 |  | 2026-09-11 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-11-14 |  | Not Started |  |  | ASAP get the update back from GP. Need further discussion on the process standardisation. | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-25 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1089 | Integration | FIN | 1089 |  | IAA ASAP | IAA | IAA - ASAP 1 | IAA |  | AR- Receipts (IAA) | AR- Receipts (IAA) |  | AR | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Inbound & Outbound | ASAP | Oracle Cloud ERP | Sprint 3 | Sprint 4 Sprint 5 | Oracle Team 2 | IAA FINOPS | IAA Team: Preetham | 2026-12-14 | 25% - Drafted | Sharjeel | Not Started | Medium | https://ritchiebros.atlassian.net/issues?filter=29016 https://rbauction.sharepoint.com/:x:/r/sites/VAN-FINFinanceTransformation-OracleCloud-PHASE2/Shared%20Documents/Oracle%20Cloud%20-%20PHASE%202/6.0%20Technology/RBG_Working_Files/RBG%20Core%20Integrations%20with%20Source%20Systems/AR%20Receipts%20Integration/IAA/Oracle_AR_Receipt_Creation_Details.xlsx?d=wee1d63114e5f4a36925443ee8b2ffb6e&csf=1&web=1&e=cgx4uV | 2026-08-21 | 2026-09-25 | 2026-07-13 |  |  | Stephen Park | 50% - Reviewed | In Progress | Michael Ortega | 2026-10-05 |  | 2026-10-02 |  | 2026-10-02 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-12-05 |  | Not Started |  |  | ASAP get the update back from GP. Need further discussion on the process standardisation. | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-25 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : SIT 2 | Week 1
FIN-INT-1090 | Integration | FIN | 1090 |  | IAA ASAP | IAA | IAA - ASAP 1 | IAA |  | AR-Credit memo (IAA) | AR-Credit memo (IAA) |  | AR | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Inbound & Outbound | ASAP | Oracle Cloud ERP | Sprint 3 | Sprint 4 Sprint 5 | Oracle Team 2 | IAA FINOPS | IAA Team: Preetham | 2026-12-14 | 25% - Drafted | Sharjeel | Not Started | Medium | https://ritchiebros.atlassian.net/issues?filter=29016 https://rbauction.sharepoint.com/:x:/r/sites/VAN-FINFinanceTransformation-OracleCloud-PHASE2/Shared%20Documents/Oracle%20Cloud%20-%20PHASE%202/6.0%20Technology/RBG_Working_Files/RBG%20Core%20Integrations%20with%20Source%20Systems/AR%20Receipts%20Integration/IAA/Oracle_AR_Receipt_Creation_Details.xlsx?d=wee1d63114e5f4a36925443ee8b2ffb6e&csf=1&web=1&e=cgx4uV | 2026-08-21 | 2026-09-25 | 2026-07-13 |  |  | Stephen Park | 50% - Reviewed | In Progress | Michael Ortega | 2026-09-14 |  | 2026-09-11 |  | 2026-09-11 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-11-14 |  | Not Started |  |  | ASAP get the update back from GP. Need further discussion on the process standardisation. | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-25 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1091 | Integration | FIN | 1091 |  | IAA ASAP | IAA | IAA - ASAP 1 | IAA |  | AR-Debit Memo (IAA) | AR-Debit Memo (IAA) |  | AR | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Inbound & Outbound | ASAP | Oracle Cloud ERP | Sprint 3 | Sprint 4 Sprint 5 | Oracle Team 2 | IAA FINOPS | IAA Team: Preetham | 2026-12-14 | 25% - Drafted | Sharjeel | Not Started | Medium | https://ritchiebros.atlassian.net/issues?filter=29016 https://rbauction.sharepoint.com/:x:/r/sites/VAN-FINFinanceTransformation-OracleCloud-PHASE2/Shared%20Documents/Oracle%20Cloud%20-%20PHASE%202/6.0%20Technology/RBG_Working_Files/RBG%20Core%20Integrations%20with%20Source%20Systems/AR%20Transactions%20Integration/IAA/IAA%20AR%20Transaction%20Fusion%20Mapping.xlsx?d=w5995ae6ff9f44971806cd42116ab1406&csf=1&web=1&e=J8tONk | 2026-08-21 | 2026-09-25 | 2026-07-13 |  |  | Stephen Park | 50% - Reviewed | In Progress | Michael Ortega | 2026-09-14 |  | 2026-09-11 |  | 2026-09-11 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-11-14 |  | Not Started |  |  | ASAP get the update back from GP. Need further discussion on the process standardisation. | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-25 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1092 | Integration | FIN | 1092 |  | IAA ASAP | IAA | IAA - ASAP 1 | IAA |  | AP- Credit Memo (IAA) | AP- Credit Memo (IAA) |  | AP | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Inbound & Outbound | ASAP | Oracle Cloud ERP | Sprint 4 | Sprint 4 Sprint 5 | Oracle Team 2 | IAA FINOPS | IAA Team: Preetham | 2026-11-13 | 25% - Drafted | Sharjeel | WIP | Medium | https://ritchiebros.atlassian.net/issues?filter=29016 https://rbauction.sharepoint.com/:x:/r/sites/VAN-FINFinanceTransformation-OracleCloud-PHASE2/Shared%20Documents/Oracle%20Cloud%20-%20PHASE%202/6.0%20Technology/RBG_Working_Files/RBG%20Core%20Integrations%20with%20Source%20Systems/AP%20Invoices%20Integration/IAA/AP%20Invoice%20Oracle%20mapping%20IAA.xlsx?d=w04b6c33f0d3045358ea3c479b93b07c2&csf=1&web=1&e=pWjEOt | 2026-09-04 | 2026-09-25 | 2026-08-17 |  |  | Stephen Park | 25% - Drafted | In Progress | Michael Ortega | 2026-09-21 |  | 2026-09-18 |  | 2026-09-18 |  | 50% - Build - In Progress | In Progress |  | 2026-11-21 |  | Not Started |  |  | ASAP get the update back from GP. Need further discussion on the process standardisation. | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-25 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1093 | Integration | FIN | 1093 |  | IAA ASAP | IAA | IAA - ASAP 1 | IAA |  | AP- Debit Memo (IAA) | AP- Debit Memo (IAA) |  | AP | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Inbound & Outbound | ASAP | Oracle Cloud ERP | Sprint 4 | Sprint 4 Sprint 5 | Oracle Team 2 | IAA FINOPS | IAA Team: Preetham | 2026-11-13 | 25% - Drafted | Sharjeel | WIP | Medium | https://ritchiebros.atlassian.net/issues?filter=29016 https://rbauction.sharepoint.com/:x:/r/sites/VAN-FINFinanceTransformation-OracleCloud-PHASE2/Shared%20Documents/Oracle%20Cloud%20-%20PHASE%202/6.0%20Technology/RBG_Working_Files/RBG%20Core%20Integrations%20with%20Source%20Systems/AP%20Invoices%20Integration/IAA/AP%20Invoice%20Oracle%20mapping%20IAA.xlsx?d=w04b6c33f0d3045358ea3c479b93b07c2&csf=1&web=1&e=pWjEOt | 2026-09-04 | 2026-09-25 | 2026-08-17 |  |  | Stephen Park | 25% - Drafted | In Progress | Michael Ortega | 2026-09-21 |  | 2026-09-18 |  | 2026-09-18 |  | 50% - Build - In Progress | In Progress |  | 2026-11-21 |  | Not Started |  |  | ASAP get the update back from GP. Need further discussion on the process standardisation. | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-25 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1094 | Integration | FIN | 1094 |  | IAA ASAP | IAA | IAA - ASAP 1 | IAA |  | AP- Vouchers (IAA) | AP- Vouchers (IAA) |  | AP | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Inbound & Outbound | ASAP | Oracle Cloud ERP | Sprint 4 | Sprint 4 Sprint 5 | Oracle Team 2 | IAA FINOPS | IAA Team: Preetham | 2026-11-13 | 25% - Drafted | Sharjeel | WIP | Medium | https://ritchiebros.atlassian.net/issues?filter=29016 https://rbauction.sharepoint.com/:w:/r/sites/VAN-FINFinanceTransformation-OracleCloud-PHASE2/Shared%20Documents/Oracle%20Cloud%20-%20PHASE%202/6.0%20Technology/RBG_Working_Files/RBG%20Core%20Integrations%20with%20Source%20Systems/ASAP%20to%20Oracle%20Cloud%20Transaction%20Flow/ASAP%20to%20Oracle%20Cloud%20-%20Transaction%20Flow.docx?d=w85345de710104dec96c3ff25c84e8149&csf=1&web=1&e=028RnV https://rbauction.sharepoint.com/:x:/r/sites/VAN-FINFinanceTransformation-OracleCloud-PHASE2/Shared%20Documents/Oracle%20Cloud%20-%20PHASE%202/6.0%20Technology/RBG_Working_Files/RBG%20Core%20Integrations%20with%20Source%20Systems/AP%20Invoices%20Integration/IAA/AP%20Invoice%20Oracle%20mapping%20IAA.xlsx?d=w04b6c33f0d3045358ea3c479b93b07c2&csf=1&web=1&e=pWjEOt | 2026-09-04 | 2026-09-25 | 2026-08-17 |  |  | Stephen Park | 25% - Drafted | In Progress | Michael Ortega | 2026-09-21 |  | 2026-09-18 |  | 2026-09-18 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-11-21 |  | Not Started |  |  | ASAP get the update back from GP. Need further discussion on the process standardisation. | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-25 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1095 | Integration | FIN | 1095 |  | IAA ASAP | IAA | IAA - ASAP 1 | IAA |  | AP- Payments (IAA) | AP- Payments (IAA) |  | AP | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Inbound & Outbound | ASAP | Oracle Cloud ERP | Sprint 4 | Sprint 4 Sprint 5 | Oracle Team 2 | IAA FINOPS | IAA Team: Preetham | 2026-11-13 | 25% - Drafted | Sharjeel | Not Started | Medium | https://ritchiebros.atlassian.net/issues?filter=29016 | 2026-09-04 | 2026-09-25 | 2026-08-17 |  |  | Stephen Park | 25% - Drafted | In Progress | Michael Ortega | 2026-10-12 |  | 2026-10-09 |  | 2026-10-09 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-12-12 |  | Not Started |  |  | ASAP get the update back from GP. Need further discussion on the process standardisation. | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-25 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : SIT 2 | Week 1
FIN-INT-1096 | Integration | FIN | 1096 |  |  | RB, IAA & IP |  |  |  | Supplier/Customer import | Supplier/Customer import |  | AP/AR | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | No |  | Inbound | ASAP | Oracle ERP Cloud |  |  | RBG Oracle Team 1 | IAA FINOPS | [5 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Apr 22: Workshop outcome: Vendors, Buyers will be sent to TE. TE will sync these with Oracle Cloud ERP. Buyer,Provider,Storage Location,Tower - ASAP terms. If any attribute is updated in ASAP it will flow to GP but not from GP. | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1097 | Integration | FIN | 1097 |  |  | RB & IAA |  |  |  | AP-Expenses/Provider charges | AP-Expenses/Provider charges |  | AP | Finance | RBG |  | #INVALID OPERATION |  | RBG Discovery | No |  | Inbound & Outbound | ASAP | Oracle ERP Cloud | [18 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | duplicate | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1098 | Integration | FIN | 1098 |  | IAA ASAP | IAA | IAA - ASAP 1 | IAA |  | IAA ASAP GL Journals Integration | IAA ASAP GL Journals Integration |  | GL | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Inbound | ASAP | Oracle Cloud ERP | Sprint 3 | Sprint 4 Sprint 5 | Oracle Team 2 | IAA FINOPS | IAA Team: Preetham | 2026-10-12 | 25% - Drafted | Sharjeel | WIP | Medium | https://ritchiebros.atlassian.net/issues?filter=29016 https://rbauction.sharepoint.com/:w:/r/sites/VAN-FINFinanceTransformation-OracleCloud-PHASE2/Shared%20Documents/Oracle%20Cloud%20-%20PHASE%202/6.0%20Technology/RBG_Working_Files/RBG%20Core%20Integrations%20with%20Source%20Systems/ASAP%20to%20Oracle%20Cloud%20Transaction%20Flow/ASAP%20to%20Oracle%20Cloud%20-%20Transaction%20Flow.docx?d=w85345de710104dec96c3ff25c84e8149&csf=1&web=1&e=028RnV https://rbauction.sharepoint.com/sites/VAN-FINFinanceTransformation-OracleCloud-PHASE2/_layouts/15/download.aspx?UniqueId=00cd7421b08d44a6a58ca5c60c026d6d&e=qVcmtw | 2026-08-21 | 2026-09-25 | 2026-07-13 |  |  | Stephen Park | 75% - Feedback Incorporated | In Progress | Michael Ortega | 2026-09-28 |  | 2026-09-25 |  | 2026-09-25 |  | 50% - Build - In Progress | In Progress |  | 2026-11-28 |  | Not Started |  |  | April 22 - Description update to IAA GL Integration | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-25 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1099 | Integration | FIN | 1099 |  |  | RB & IAA |  |  |  | Concur Travel Expenses - Oracle Cloud | Concur Travel Expenses - Oracle Cloud |  | AP | Finance | RBG |  | #INVALID OPERATION |  | RBG Discovery | No |  | Inbound | Concur | Oracle ERP Cloud |  |  | RBG Oracle Team 1 | IAA FINOPS | [5 empty] | Small | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | 10NOV - Need deep dive if we can extend this to Oracle expense module.File based- deep dive needed with AP team for the furture process. ( its manual today) | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1100 | Integration | FIN | 1100 |  |  | RB & IAA |  |  |  | ImageNow AP | ImageNow AP |  | AP | Finance | RBG |  | #INVALID OPERATION |  | RBG Discovery | No |  | Inbound | ImageNow | Oracle ERP Cloud | [18 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | 10 nov - similar to pitstop. To be replaced by oracle module | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1101 | Integration | FIN | 1101 |  |  | IAA |  |  |  | Frontier AR load | Frontier AR load |  | AR | Finance | RBG |  | #INVALID OPERATION |  | RBG Discovery | No |  | Inbound | Frontier | Oracle ERP Cloud | [9 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1102 | Integration | FIN | 1102 |  |  | RB & IAA |  |  |  | Frontier AP load | Frontier AP load |  | AP | Finance | RBG |  | #INVALID OPERATION |  | RBG Discovery | No |  | Inbound | Frontier | Oracle ERP Cloud | [9 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1103 | Integration | FIN | 1103 |  |  | IAA |  |  |  | GL Integration for Vision (Frontier) UK | GL Integration for Vision (Frontier) UK |  | GL | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | No |  | Inbound | Frontier | Oracle ERP Cloud | [9 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | April 22 - Description and scope updated for Frontier | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1104 | Integration | FIN | 1104 |  |  | RB & IAA |  |  |  | Impact AP Load | Impact AP Load |  | AP | Finance | RBG |  | #INVALID OPERATION |  | RBG Discovery | No |  | Inbound | Impact | Oracle ERP Cloud | [9 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | duplicate | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1105 | Integration | FIN | 1105 |  |  | IAA |  |  |  | Impact Vision(Canada) GL Load | Impact Vision(Canada) GL Load |  | GL | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | Duplicate |  | Inbound | Impact | Oracle ERP Cloud | [9 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | April 22 - duplicate for INT 1042 | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1106 | Integration | FIN | 1106 |  |  | RB & IAA |  | IAA |  | Vision AP Load | Vision AP Load |  | AP | Finance | RBG |  | #INVALID OPERATION |  | RBG Discovery | Yes |  | Inbound | Vision | Oracle ERP Cloud | [9 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | duplicate | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1107 | Integration | FIN | 1107 |  |  | IAA |  |  |  | Vision AR Load | Vision AR Load |  | AR | Finance | RBG |  | #INVALID OPERATION |  | RBG Discovery | No |  | Inbound | Vision | Oracle ERP Cloud | [9 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | duplicate | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1108 | Integration | FIN | 1108 |  |  | IAA |  |  |  | Vision Australia GL Load | Vision Australia GL Load |  | GL | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | Duplicate |  | Inbound | Vision | Oracle ERP Cloud | [9 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | April 22 - duplicate for INT 1042 | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1109 | Integration | FIN | 1109 |  |  | RB & IAA |  |  |  | P Card Integration | JPMC PCARD GP Integration |  | AP | Finance | Deloitte |  | #INVALID OPERATION | No | RBG Discovery | Duplicate |  | Inbound | JPMC | Oracle ERP Cloud |  |  | Deloitte | [15 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | AP Team extracts data from JPMC systems ( AP data) and drops into file share. GP loader modulea read and load. In future state we might need deep dive to standardise the process steps | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1110 | Integration | FIN | 1110 |  |  | IAA |  |  |  | COA used for Transactions. Current System Alert. | Accounting data flow - COA Account code combinations data. Current process is manual. |  | AP/AR/GL | Finance | RBG |  | Delayed | Yes | RBG Discovery | No |  | Inbound | Oracle ERP Cloud | ASAP | Sprint 1 | Sprint 2 Sprint 3 | Deloitte | IAA FINOPS | Oracle Team 1 | [6 empty] | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  |  |  | Delayed | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | FTD - Its is manual in todays's world. Deev dive re. to find out future process | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-06-12 | INT | Finance : Gap Sprint | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-RPT-1111 | Report | FIN | 1111 |  |  | IAA |  |  |  | Current Users use Excel to read data to GP by using Excel ODBC connections | Current Users use Excel to read data to GP by using Excel ODBC connections |  | AR/AP | Finance | RBG |  | Delayed | Yes | RBG Discovery | TBD |  |  | ASAP | Oracle ERP Cloud | Sprint 2 | Sprint 3 | Deloitte | IAA FINOPS | Oracle Team 1 | [6 empty] | 2026-07-17 | 2026-07-17 | 2026-07-17 |  |  |  |  | Delayed | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | 1) Run AR Cash Receipts Apply validations 2) Run Disbursements validation during month end reconciliations | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-07-17 | RPT | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1112 | Integration | FIN | 1112 |  |  | IAA |  |  |  | Impact Canada data import ? | Impact Canada data import ? |  | GL | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | Duplicate |  |  | ASAP | Oracle ERP Cloud |  |  | RBG Oracle Team 2 | IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | April 22 - Duplicate from INT1098 1) Push GL data via smartconnect API to GP 2) Push AP, GL data using Integration Manager to GP | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1113 | Integration | FIN | 1113 |  |  | IAA |  |  |  | Synetiq(Frontier) data import (Current -Manual Process - UK use this tool/Excel to load operational/non operation data to GP) | Synetiq(Frontier) data import (Current -Manual Process - UK use this tool/Excel to load operational/non operation data to GP) |  | AR/AP/GL | Finance | RBG |  | Delayed | Yes | RBG Discovery | No |  |  | ASAP | Oracle ERP Cloud | Sprint 1 | Sprint 2 Sprint 3 | Deloitte | IAA FINOPS | Oracle Team 1 | [6 empty] | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  |  |  | Delayed | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | 1) Push AP, AR transactional data using SmartConnect desktop app using SmartConnect Maps to GP 2) Push AR, AP, GL Master data using IntegrationManager to GP | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-06-12 | INT | Finance : Gap Sprint | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1114 | Integration | FIN | 1114 |  |  | IAA |  |  |  | Pitstop data export, creating invoices to be paid | Pitstop data export, creating invoices to be paid |  |  | Finance | RBG |  | #INVALID OPERATION | No | RBG Discovery | No |  |  | ASAP | Oracle ERP Cloud |  |  | RBG Oracle Team 2 | IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | 1) Read GP SQL server tables via SSIS package and push to Pitstop application 2) Create AP voucher via smartconnect 3) Read GP SQL server tables to know paid vouchers | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1115 | Integration | FIN | 1115 |  |  | IAA |  |  |  | ImageNow | ImageNow |  |  | Finance | RBG |  | #INVALID OPERATION | No | RBG Discovery | No |  |  | ASAP | Oracle ERP Cloud |  |  | RBG Oracle Team 2 | IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | 1) Read GP SQL server tables via SSIS package and push AP,GL data to ImageNow application 2) Import ImageNow data to GP using IntegrationManager | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1116 | Integration | FIN | 1116 |  |  | IAA |  |  |  | Oracle EPM?What wave?(Obsolete for IAA)(Current process GP to EPM) | Oracle EPM?What wave?(Obsolete for IAA)(Current process GP to EPM) |  |  | Finance | RBG |  | #INVALID OPERATION | No | RBG Discovery | No |  |  | ASAP | Oracle ERP Cloud |  |  | RBG Oracle Team 2 | IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Apr 29: This integration is no longer needed as it was to GP to Fusion GL to EPM to FCCS to ARC. 1) Read GP SQL server tables via SSIS package and push AP,GL data to Oracle EPM application 2) Import Oracle EPM data to GP using IntegrationManager | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1117 | Integration | FIN | 1117 |  |  | IAA |  |  |  | EFT Payment | EFT Payment |  | AP | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | Duplicate |  |  | ASAP | Oracle ERP Cloud |  |  | RBG Oracle Team 2 | IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | 1) We have GP Dexterity customization which reads data from SQL tables and update EFT file for custom fields | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1118 | Integration | FIN | 1118 |  |  | IAA |  |  |  | Uploading exchange rate via script | Uploading exchange rate via script |  | AP/AR/GL | Finance | RBG |  | #INVALID OPERATION | No | RBG Discovery | No |  |  | ASAP | Oracle ERP Cloud |  |  | RBG Oracle Team 2 | IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | This will not be needed anymore since Oracle is already getting exchange rates - TBD | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1119 | Integration | FIN | 1119 |  |  | IAA |  |  |  | Updating vendor information via script in GP on Adhoc finance requests(Bulk Update) | Updating vendor information via script in GP on Adhoc finance requests(Bulk Update) |  | AP | Finance | RBG |  | Delayed | Yes | RBG Discovery | No |  |  | ASAP | Oracle ERP Cloud | Sprint 1 | Sprint 2 | Deloitte | IAA FINOPS | Oracle Team 1 | [6 empty] | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  |  |  | Delayed | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-06-12 | INT | Finance : Gap Sprint | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1120 | Integration | FIN | 1120 |  |  | RB, IAA & IP | IAA - ASAP 1 |  |  | BOA & BMO, other banks positive pay | BOA & BMO, other banks positive pay |  | AP | Finance | RBG |  | Delayed | Yes | RBG Discovery | Duplicate |  |  | ASAP | Oracle ERP Cloud | Sprint 2 | Sprint 3 | Deloitte | IAA FINOPS | Oracle Team 1 | [6 empty] | 2026-05-29 | 2026-05-29 | 2026-05-29 |  |  |  |  | Delayed | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Check run is more frequent, Postitive Pay is hourly process 7am to 8pm | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-05-29 | INT | Finance : Gap Sprint | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN\-INT-1121 | Integration | FIN\ | 1121 |  |  | IAA |  |  |  | EPM Integration from IAA systems | EPM Integration from IAA systems |  |  | Finance | RBG |  | #INVALID OPERATION |  | RBG Discovery | No |  | Inbound |  | EPM | [18 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | 10NOV - Not needed as confirmed by Monicka | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1122 | Integration | FIN | 1122 |  |  | RB, IAA & IP |  |  |  | Send remittance notification to supplier | Send remittance notification to supplier |  | AP | Finance | Deloitte |  | #INVALID OPERATION | Yes | RBG Discovery | Duplicate |  | Outbound | Oracle ERP Cloud | Extern email/Systems |  |  | Deloitte | [15 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Redesign/report/externalisation needed | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1123 | Integration | FIN | 1123 |  | Oracle Core | RB | RB DPP | Core - DPP |  | TAX Exemption for Customers (Current Process Party details sent to Avalara from EBS) | TAX Exemption for Customers (Current Process Party details sent to Avalara from EBS) |  | AR | Finance | RBG |  | Delayed | Yes | RBG Discovery | No |  | Outbound | Oracle Cloud ERP | AVALARA | Sprint 2 | Sprint 3 Sprint 4 | Deloitte | Oracle Team 1 | Oracle Team |  |  | Khaleel |  | Medium |  | 2026-07-17 | 2026-07-17 | 2026-07-13 |  |  | RBG | 25% - Drafted | Delayed | RBG | [6 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Need deeper dive for the process flow | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-07-17 | INT | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1124 | Integration | FIN | 1124 |  | CDW | All | All | Core - DPP |  | GL budget data to PA - CPM | GL budget data to PA - CPM |  | GL | Finance | RBG |  | F-Spec-In Progress | Yes | RBG Discovery | Yes |  | Outbound | Oracle Cloud ERP | Planning & Analytics (PA) | Sprint 3 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 1 | Oracle Team 1 | PA Team |  |  | Khaleel |  | Medium |  | 2026-08-21 | 2026-09-18 | 2026-07-13 |  |  |  | 25% - Drafted | In Progress | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Need redesign (INT_FIN313,INT_FIN314) | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1125 | Integration | FIN | 1125 |  |  | RB |  |  |  | exchange rate data to CDH - Switch to snowflake? | exchange rate data to CDH - Switch to snowflake? |  |  | Finance | RBG |  | #INVALID OPERATION | No | RBG Discovery | No - Marked for Tracking |  | Outbound | Oracle ERP Cloud | CDW ( Big Data -> Snowflake) |  |  | RBG Oracle Team 1 | Oracle Team 1 | CDW Team |  |  |  |  | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Apr 28: - CDW needs to pull exhcage rates from KAFKA topic, keeping this only for tracking. Need XE data to go to kafka for cdh consumption/or need future solution. This is needed to support to calculate the Bid limit outside of Oracle. | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1126 | Integration | FIN | 1126 |  |  | RBFS | RBFS | Core Modules |  | Import AR Transactions from RBFS | Manual RBFS AR data upload to cloud |  | AR | Finance | RBG |  | Delayed | No | RBG Discovery | Yes |  | Inbound | RBFS (SalesForce) | Oracle Cloud ERP | Sprint 2 | Sprint 2 Sprint 3 | Deloitte |  |  |  |  | Sharjeel |  | Medium |  |  | 2026-07-17 | 2026-07-13 |  |  | Syed Imran Waheed | 25% - Drafted | Delayed | [7 empty] | 25% - Tech Spec - In Progress | In Progress |  |  |  | Not Started |  |  | its manual process in today's arch. Need further discussion on design or automation needed. | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-07-17 | INT | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1 | Salesforce
FIN-INT-1127 | Integration | FIN | 1127 |  |  | GovPlanet |  |  |  | WAERlinx & NetSuite &IP report generator | WAERlinx & NetSuite &IP report generator |  |  | Finance | RBG |  | #INVALID OPERATION | No | RBG Discovery | No - Marked for Tracking |  | Outbound | NetSuite | TBD |  |  | TBD | TBD | GovPlanet Team |  |  |  |  | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | 05/MAR/2026 - Netsuite team will re-do it on the Netsuite system. We will track it - but no action point on Oracle Team. GovPlanet business team uses this report. Need a design discussion on the future design.INT_FIN370 INT_FIN378 INT_FIN379 | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1128 | Integration | FIN | 1128 |  |  | RB |  | Core - DPP |  | FEDEX - Manual Report (AP Invoice) dropped to SFTP and imported into Oracle Cloud ERP | FEDEX - Manual Report (AP Invoice) dropped to SFTP and imported into Oracle Cloud ERP |  | AP | Finance | RBG |  | Not Started | Yes | RBG Discovery | Yes |  | Inbound | FEDEX | Oracle Cloud ERP | Sprint 2 | Sprint 3 | Deloitte | Oracle Team 1 | Oracle Team |  |  | Sharjeel |  | Medium |  | 2026-07-17 | 2026-09-18 |  |  |  | RBG | 0% - Not Started | Not Started | RBG | [6 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | INT_FIN376 - we uplaod the file on ebs and run concur program/ need dessig discussion | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1129 | Integration | FIN | 1129 |  |  | RBG |  |  |  | Contractor PO automation | Contractor PO automation(Current System approved time from EBS is sent to Hiring Agencies, dependency to see if business process needs to change in Fusion) |  |  | Finance | Deloitte |  | #INVALID OPERATION | No | RBG Discovery | Duplicate |  | Inbound | Oracle ERP Cloud | Hiring Agencies |  |  | Deloitte | [15 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Need discussion | dipriverma@deloitte.ca | 2026-08-31 11:48 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1130 | Integration | FIN | 1130 |  |  | RB |  |  |  | My Time - Contractor time card automation | Contractor time card automation |  | Purchasing | Finance | RBG |  | #INVALID OPERATION | No | RBG Discovery | No |  | Inbound | MyTime (Finland) | OTL(HCM) |  |  | RBG Oracle Team 1 | Oracle Team 1 | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | need disscussion | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1132 | Integration | FIN | 1132 |  | OneSource | ALL | RB Non-Auction | Core Modules |  | Tax data with Onesource (TR) (Tax calculations for Non auction based AR/AP transactions - No OIC/Middleware, Out of box fusion functionality) | Tax data with Onesource (TR) (Tax calculations for Non auction based AR/AP transactions - No OIC/Middleware, Out of box fusion functionality) |  | AP/AR | Finance | RBG |  | Delayed | No | RBG Discovery | Yes |  | Inbound & Outbound | Oracle Cloud ERP | Onesource | Sprint 2 | Sprint 3 Sprint 4 | Deloitte |  | Oracle Team |  |  | Sharjeel |  | Medium |  |  | 2026-07-17 | 2026-07-13 |  |  |  | 25% - Drafted | Delayed | [7 empty] | 25% - Tech Spec - In Progress | In Progress |  |  |  | Not Started |  |  | We will need deeper dive to establish lower level line items for each transactions. Do we need it or TR will do the config? | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-07-17 | INT | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1133 | Integration | FIN | 1133 |  |  | All |  |  |  | Tax Transaction validation | Tax Transaction validation |  | AP/AR | Finance |  |  | #INVALID OPERATION | No | RBG Discovery | Duplicate |  |  | Oracle ERP Cloud | Onesource |  |  | Deloitte | [15 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Need deeper dive for the process flow.Do we need it or TR will do the config? | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1134 | Integration | FIN | 1134 |  | Pagero | RB, Mascus, IP, IAA | RB Non-Auction | Mascus |  | e-invoicing XML Feed to and for Pagero(Current Process EBS brings and send data to Pagero uses CXML format) | eInvocing feed to Pagero for compliance(through XML Gateway used for POLAND/Finland, upcoming Germany/France Sep 2026 /Dubai Jan-27) |  | AP/AR | Finance | RBG |  | Delayed | Yes | RBG Discovery | Yes |  | Inbound & Outbound | Oracle Cloud ERP | Pagero | Sprint 2 | Sprint 3 Sprint 4 | Deloitte | Oracle Team 1 | Oracle Team |  |  | Sharjeel/Gurpreet |  | Medium |  | 2026-07-17 | 2026-07-17 | 2026-07-13 |  |  | RBG | 25% - Drafted | Delayed | RBG | [6 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Need deeper dive on the rocess | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-07-17 | INT | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1135 | Integration | FIN | 1135 |  |  | B&B |  |  |  | Journal entries (AP, AR) from STRIPE to Oracle ERP GL | Import Journal Entries from Stripe |  | GL | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Inbound | Stripe | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Manual | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1136 | Integration | FIN | 1136 |  |  | B&B |  | Core Modules |  | Bank Statements feed from Kyriba to Oracle CM | Import Bank Statements (B&B) from Kyriba and Run Bank Statement Reconciliation |  | CM | Finance | Deloitte |  | FUT-Pending |  | Discovery | No |  | Inbound | Kyriba | Oracle ERP Cloud | [9 empty] | Simple |  | 2025-09-22 |  |  | 2026-08-07 | 2026-07-31 | Deepankar Gera | 100% - Approved | Completed |  | 2025-10-20 |  | 2025-10-29 |  | 2025-10-29 | 2026-07-31 | 100% - Complete | Completed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 72 | 2025-10-20 |  | Completed | 2025-09-22 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1137 | Integration | FIN | 1137 |  |  | B&B |  |  |  | AP Payments from Oracle to Kyriba | Send Electronic Payments to Kyriba |  | AP | Finance | Deloitte |  | Delayed | Yes | Discovery | No |  | Outbound | Kyriba | Oracle ERP Cloud | [9 empty] | Complex |  | 2025-09-23 | [6 empty] | Delayed |  | 2025-09-29 |  | 2025-10-21 |  | 2025-10-21 |  |  | Delayed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 153 | 2025-09-29 |  | Delayed | 2025-09-23 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1138 | Integration | FIN | 1138 |  |  | DDI |  |  |  | DDI Bank Statements Import from Kyriba to Oracle ERP CM | Import Bank Statements (DDI) from Kyriba and Run Bank Statement Reconciliation |  | CM | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Inbound | Kyriba | Oracle ERP Cloud | [9 empty] | Simple | [6 empty] | Deepankar Gera |  | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 72 |  |  | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1139 | Integration | FIN | 1139 |  |  | DDI |  |  |  | Gardener Customer Import into Oracle AR | Import Customers from Gardener |  | AR | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Inbound | Gardener | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | NA | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1140 | Integration | FIN | 1140 |  |  | DDI |  |  |  | Gardener AR Invoices Import to Oracle AR | Import AR Invoices from Gardener |  | AR | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Inbound | Gardener | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | NA | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1141 | Integration | FIN | 1141 |  |  | DDI |  |  |  | Gardener AR Receipts to Oracle AR | Import AR Receipts from Gardener |  | AR | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Inbound | Gardener | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | NA | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1142 | Integration | FIN | 1142 |  |  | DDI |  |  |  | AR accounting entries from Gardener to Oracle GL | Import AR accounting entries from Gardener |  | GL | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Inbound | Gardener | Oracle ERP Cloud |  |  | Deloitte | [6 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1143 | Integration | FIN | 1143 |  |  | JMW |  |  |  | AMS Customer Import into Oracle AR | Import Customers from AMS |  | AR | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Inbound | Auction Management System* | Oracle ERP Cloud | [9 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | NA | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1144 | Integration | FIN | 1144 |  |  | JMW |  |  |  | AMS AR Invoices Import to Oracle AR | Import AR Invoices from AMS |  | AR | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Inbound | Auction Management System* | Oracle ERP Cloud | [9 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | NA | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1145 | Integration | FIN | 1145 |  |  | JMW |  |  |  | AMS AR Receipts to Oracle AR | Import AR Receipts from AMS |  | AR | Finance | Deloitte |  | #INVALID OPERATION |  | Discovery | No |  | Inbound | Auction Management System* | Oracle ERP Cloud | [9 empty] | Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | NA | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1146 | Integration | FIN | 1146 |  |  | IAA |  |  |  | AP - Subledgers - For IAA, Vision AUS is not using AP AR submodule | AP - Subledgers - For IAA, Vision AUS is not using AP AR submodule |  | AP | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | No |  |  | Vision(AUS) | Oracle ERP Cloud |  |  | RBG Oracle Team 2 | IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1147 | Integration | FIN | 1147 |  |  | IAA |  |  |  | AR integration - For IAA, Vision AUS is not using AP AR submodule | AR integration - For IAA, Vision AUS is not using AP AR submodule |  | AR | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | No |  |  | Vision(AUS) | Oracle ERP Cloud |  |  | RBG Oracle Team 2 | IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1148 | Integration | FIN | 1148 |  |  | IAA |  |  |  | Customer/Supplier - For IAA, Vision AUS is not using AP AR submodule | Customer/Supplier - For IAA, Vision AUS is not using AP AR submodule |  | Customer | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | No |  |  | Vision(AUS) | Oracle ERP Cloud |  |  | RBG Oracle Team 1 | IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1149 | Integration | FIN | 1149 |  | IAA ASAP | IAA | IAA - ASAP 1 | IAA |  | AR open invoice data to ASAP for collection processes | AR open invoice data to ASAP for collection processes |  | AR | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Outbound | Oracle Cloud ERP | ASAP | Sprint 4 | Sprint 4 Sprint 5 | Oracle Team 2 | IAA FINOPS | IAA Team | 2026-11-17 | 25% - Drafted | Sharjeel |  | Medium | https://ritchiebros.atlassian.net/issues/?filter=29016 | 2026-09-18 | 2026-09-28 | 2026-08-17 |  |  | RBG | 25% - Drafted | In Progress | Michael Ortega | 2026-09-28 |  | 2026-09-25 |  | 2026-09-25 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-11-28 |  | Not Started |  |  | Apr 16 - Collections out of scope for IAA, but need a separate line item for pulling invoice information from oracle fusion into ASAP AR Aging + Automated statement process ¦¦ KDD - IAA wont be using Advanced collection on Cloud ¦¦ as of today ASAP is having email comm. Only - no dialer sol. Exists | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-28 | INT | Finance : SIT 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1150 | Integration | FIN | 1150 |  |  | IAA |  |  |  | COA mapping - ASAP - It is not integration, Configuration need to be in ASAP | COA mapping - ASAP - It is not integration, Configuration need to be in ASAP |  |  | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | No |  | Inbound | ASAP | Oracle ERP Cloud |  |  | RBG Oracle Team 2 | IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1151 | Integration | FIN | 1151 |  |  | RBG |  |  |  | COA Mapping - IP Web | COA Mapping - IP Web |  | AP/AR/GL | Finance | Deloitte |  | #INVALID OPERATION | Yes | RBG Discovery | No |  | Inbound | IP Web | Oracle ERP Cloud |  |  | Deloitte | [15 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1152 | Integration | FIN | 1152 |  |  | Rouse, RBFS, Veritrade |  |  |  | Upload AP and AR Invoices into Oracle Cloud ERP | Rouse non-auction data load |  | AP/AR | Finance | RBG |  | #INVALID OPERATION | No | RBG Discovery | No |  | Inbound | Rouse | Oracle ERP Cloud |  |  | Deloitte | [15 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Might be manual - need deeper dive | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1153 | Integration | FIN | 1153 |  |  | IP - GovPlanet |  |  |  | Netsuite GL load (Manual - no integration exists for current system) | Netsuite GL load (Manual - no integration exists for current system) |  | GL | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | No |  | Inbound | NetSuite | Oracle ERP Cloud |  |  | RBG Oracle Team 2 | Oracle Team 2 | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | April 30 - Wayne confirmed no existing integration for this system April 22 - RB Team to confirm the sub-entity and overral requirement for this integration 10FEB2026 - Jace/Raquel confirmed that there is a manual data feed from Netsuite that handles GL entries for inventory, collapses, etc… | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1154 | Integration | FIN | 1154 |  |  | RBG |  |  |  | replacement for Marketing list functionality in EBS | replacement for Marketing list functionality in EBS |  |  | Finance | RBG |  | #INVALID OPERATION | No | RBG Discovery | No - Marked for Tracking |  | Outbound | Oracle ERP Cloud | CDW ( Big Data -> Snowflake) |  |  | RBG Oracle Team 1 | RBG Oracle Team 1 | CDW Team | [13 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Apr 28: These are marked out of scope https://ritchiebros.atlassian.net/browse/DD-21 | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1155 | Integration | FIN | 1155 |  | CDW | RBG | All | Core - DPP |  | Replacement for EBS views consumed by CDW (Revised 3 views only) | Replacement for EBS views consumed by CDW |  |  | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Outbound | Oracle Cloud ERP | CDW (Big Data -> Snowflake) | Sprint 2 | Sprint 3 Sprint 4 Sprint 5 | TBD | RBG Oracle Team 1 | CDW Team |  |  | Khaleel |  | Medium |  | 2026-07-17 | 2026-09-18 | 2026-05-29 |  |  | RBG | 25% - Drafted | In Progress | Khaleel Shaik | 2026-08-10 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 |  | 0% - Not Started | In Progress |  | 2026-09-20 |  | Not Started |  |  | Apr 28: Detailed object need to follow from the Excel prepared by Tuhin | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-INT-1156 | Integration | FIN | 1156 |  |  | All |  |  |  | Any Datawarehouse aspects of the new customer/supplier integration design | Any Datawarehouse aspects of the new customer/supplier integration design |  | AP/AR | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | Duplicate |  | Outbound | Oracle ERP Cloud | CDW ( Big Data -> Snowflake) |  |  | RBG Oracle Team 1 | RBG Oracle Team 1 | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Apr 28: This is covered in TE integration lines to CDW. Marking it as Duplicate for SCM-INT-1201 , FIN-INT-1202 | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1157 | Integration | FIN | 1157 |  |  | All |  |  |  | Solutions for history data that will not be converted into Cloud ERP (eg. purchase history) | Solutions for history data that will not be converted into Cloud ERP (eg. purchase history) |  | Purchasing | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | Deferred (Release 3) |  | Outbound | Oracle ERP Cloud | CDW ( Big Data -> Snowflake) | Sprint 2 | Sprint 3 | TBD | RBG Oracle Team 1 | CDW Team |  |  | Wayne |  | Medium |  |  |  | 2026-05-29 |  |  | RBG | 25% - Drafted | #INVALID OPERATION | RBG | [6 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Apr 28: Need to confirm solution for the existing Customer that are not part of conversions. How existing data is going to map with non migrating customers. This might be more a conversion object. | dipriverma@deloitte.ca | 2026-08-31 11:50 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1158 | Integration | FIN | 1158 |  |  | IAA |  |  |  | AR feed from Vision UK | AR feed from Vision UK |  | AR | Finance | RBG |  | #INVALID OPERATION | No | RBG Discovery | No |  |  | Vision, Frontier (UK) | Oracle ERP Cloud |  |  | RBG Oracle Team 2 | IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1159 | Integration | FIN | 1159 |  |  | IAA |  |  |  | AP feed | AP feed |  | AP | Finance | RBG |  | #INVALID OPERATION | No | RBG Discovery | No |  |  | Vision, Frontier (UK) | Oracle ERP Cloud |  |  | RBG Oracle Team 2 | IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1160 | Integration | FIN | 1160 |  |  | IAA |  |  |  | Cust/Supplier Integration with Vision/Frontier (UK) | Cust/Supplier Integration with Vision/Frontier (UK) |  | Customer/Supplier | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | No |  | Inbound | Vision, Frontier (UK) | Oracle ERP Cloud |  |  | RBG Oracle Team 1 | IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | There can be multiple instances within the same country | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1161 | Integration | FIN | 1161 | TRUE |  | RB |  |  |  | AR Transactions Integration-DPP | AR Transactions Integration-DPP |  | AR | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | Duplicate |  | Inbound | FIS | Oracle ERP Cloud |  |  | Oracle Team 2 | Oracle Team 2/IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1161 | Integration | FIN | 1161 | TRUE |  | IAA |  |  |  | AR integration | AR integration |  | AR | Finance | RBG |  | #INVALID OPERATION | No | RBG Discovery | No |  |  | Vision(CAN) | Oracle ERP Cloud |  |  | RBG Oracle Team 2 | IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1162 | Integration | FIN | 1162 | TRUE |  | RB |  |  |  | AP Invoices Integration-DPP | AP Invoices Integration-DPP |  | AP | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | Duplicate |  | Inbound | FIS | Oracle ERP Cloud |  |  | Oracle Team 2 | Oracle Team 2/IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | No Frontier or Vision integrations with Oracle Subledgers in Wave1 & 2. | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1162 | Integration | FIN | 1162 | TRUE |  | IAA |  |  |  | AP integration | AP integration |  | AP | Finance | RBG |  | #INVALID OPERATION | No | RBG Discovery | No |  |  | Vision(CAN) | Oracle ERP Cloud |  |  | RBG Oracle Team 2 | IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1163 | Integration | FIN | 1163 |  |  | IAA |  |  |  | Customer/Supplier with Vision (Can) | Customer/Supplier with Vision (Can) |  | Customer/Supplier | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | No |  | Inbound | Vision(CAN) | Oracle ERP Cloud |  |  | RBG Oracle Team 1 | IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | There can be multiple instances within the same country | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1164 | Integration | FIN | 1164 |  | DPP | RBA | All | Core - DPP |  | Find and Create Supplier to Oracle Cloud | Find and Create Supplier to Oracle Cloud |  | AP | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Inbound & Outbound | TE | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | RBG Oracle Team 1 | Oracle Team | 2026-08-31 | 0% - Not Started | Khaleel/John Russ |  | Medium |  | 2026-08-28 | 2026-09-18 |  |  |  | RBG | 0% - Not Started | Not Started | Kyle Boon | 2026-08-10 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 |  | 0% - Not Started | In Progress |  | 2026-09-20 |  | Not Started |  |  | reply supier ID back to Transacting Entity | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-INT-1165 | Integration | FIN | 1165 |  | DPP | All | All | Core - DPP |  | Find and Create Customer to Oracle Cloud | Find and Create Customer to Oracle Cloud |  | AR | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Inbound & Outbound | TE | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | RBG Oracle Team 1 | Oracle Team | 2026-09-04 | 25% - Drafted | Khaleel/John Russ |  | Medium |  | 2026-07-17 | 2026-09-18 | 2026-07-13 |  |  | RBG | 25% - Drafted | In Progress | Kyle Boon | 2026-08-10 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 |  | 50% - Build - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-INT-1166 | Integration | FIN | 1166 |  | Mascus | Mascus | Mascus | Mascus |  | Import Customer's Authorization Token from MASCUS Salesforce | Create / Update Customer's Authorization Token from MASCUS Salesforce |  | AR | Finance | Deloitte |  | Delayed | Yes | RBG Discovery | Yes |  | Inbound | Mascus/Salesforce | Oracle Cloud ERP | Sprint 2 | Sprint 3 | Deloitte | Deloitte | Jun, Martijn |  |  | Jun/Gurpreet | WIP | Very Complex |  | 2026-07-10 | 2026-08-21 | 2026-08-27 |  |  | Venkata Kiran Kumar Pallantla | 50% - Reviewed | Delayed | Piyush Ojha | 2026-09-09 |  | 2026-10-09 |  | 2026-10-09 |  | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-09 07:19 |  |  | 207 |  |  | Not Started | 2026-08-21 | INT | Finance : Sprint 3 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : SIT 2 | Week 1 | Salesforce
FIN-INT-1167 | Integration | FIN | 1167 |  | DPP | All | All |  |  | Publish merge party to TE ( customer/Supplier) | Publish merge party to TE ( customer/Supplier) |  | Customer | Finance | RBG |  | Delayed | Yes | RBG Discovery | Yes |  | Outbound | Oracle Cloud ERP | TE | Sprint 3 | Sprint 3 Sprint 4 | RBG Oracle Team 1 | RBG Oracle Team 1 | TE | 2026-09-04 | 25% - Drafted | Khaleel |  | Medium |  | 2026-07-17 | 2026-08-28 | 2026-07-13 |  |  | RBG | 25% - Drafted | Delayed | Kyle Boon | 2026-08-10 |  | 2026-08-07 |  | 2026-08-07 |  | 50% - Build - In Progress | In Progress |  | 2026-09-10 |  | Not Started |  |  |  | suchisahoo@deloitte.com | 2026-08-30 22:44 | [5 empty] | Delayed | 2026-08-28 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-INT-1168 | Integration | FIN | 1168 |  |  | RB |  |  |  | EBS to TE bi-drectional interface for Interim | EBS to TE bi-drectional interface for Interim |  | AP/AR | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | No | Oracle ERP Cloud | Inbound & Outbound | EBS | TE | [18 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | this is temporary integration with TE - mandatory for cloud movement Apr 16 -There won't be any integration between EBS and TE | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1169 | Integration | FIN | 1169 |  | DPP | RB & IAA, MARS | RB Non-Auction | Core - DPP |  | MARS - Employee Search | Ability to search Employees in MARS |  | HCM | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  |  | Oracle Cloud ERP | MARS | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Oracle Team 1 | MARS Team | 2026-09-04 | 25% - Drafted | Khaleel |  | Medium |  | 2026-08-21 | 2026-09-18 | 2026-07-13 |  |  | RBG | 25% - Drafted | In Progress | RBG | 2026-08-10 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 |  | 50% - Build - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
SCM-INT-1170 | Integration | SCM | 1170 |  | DPP | RB & IAA, MARS | RB Non-Auction | Core - DPP |  | MARS - Supplier Search | Ability to search Suppliers in MARS |  | Procurement | Procurement | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  |  | Oracle Cloud ERP | MARS | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Oracle Team 1 | MARS Team | 2026-09-04 | 25% - Drafted | Khaleel |  |  |  | 2026-08-21 | 2026-09-18 | 2026-07-13 |  |  | RBG | 25% - Drafted | In Progress | RBG | 2026-08-10 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Delayed | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Procurement : Sprint 3 | Week 1
FIN-INT-1171 | Integration | FIN | 1171 |  |  | RB & IAA |  | ARCS | INT-028 (SOW: INT-026) | Transaction Matching for Source System Reconciliations & Payroll PAR Reconciliations | Transaction matching for source system reconciliations & Payroll PAR reconciliations. Source system integrations for GP, EBS, Sage & QuickBooks Payroll Extracts (From Fusion) |  | ARCS | Finance | Deloitte |  | Completed | No | SOW | Yes |  |  | Oracle Cloud ERP |  |  |  | Deloitte (ARCS) | Deloitte (ARCS) |  |  |  | Markus |  | Medium |  |  |  |  | 2026-04-13 |  | David Koter | 100% - Approved | Completed | Aiden Lee |  | 2026-04-14 |  |  | 2026-04-13 | 2026-04-22 | 100% - Complete | Completed |  |  | 2026-05-08 | Completed |  |  | April 15: Placeholder for Transaction matching for source system reconciliations & Payroll PAR reconciliations. Source system integrations for GP, EBS, Sage & QuickBooks Currently doing POC for GP | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  |  |  | 2026-04-14 | Completed |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Gap Sprint | Week 1
FIN-INT-1172 | Integration | FIN | 1172 |  |  | RB & IAA | RB Non-Auction | Core Modules |  | Journal export from Kyriba to Oracle Cloud for EMEA & NA Treasury Activities | Journal export from Kyriba to Oracle Cloud for EMEA & NA Treasury Activities |  | GL | Finance | Deloitte | Before SIT 1 | Delayed | No | New Requirement | Yes |  |  | Kyriba | Oracle Cloud ERP |  |  | Deloitte | Deloitte |  |  |  | Eric/Gurpreet |  |  |  |  | 2026-04-23 |  | 2026-03-31 |  | Deepankar Gera | 100% - Approved | Completed | Tim Regan | 2026-06-22 |  | 2026-07-06 |  | 2026-07-06 |  | 100% - Complete | Completed |  | 2026-09-07 |  | Delayed |  |  | New Integration based on the oucome of Non-Auction workshops. Added March 18th 2026 | dipriverma@deloitte.ca | 2026-09-10 12:16 |  |  | 99 |  |  | Delayed | 2026-04-23 | INT | Finance : Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-INT-1173 | Integration | FIN | 1173 |  | DPP | All | All | Core - DPP |  | Customer Master Service (Configuration) | Common Service For Customer Gold & Dedupe |  | Customer | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Inbound & Outbound | Oracle Cloud ERP-CDM | TE | Sprint 3 | Sprint 3 Sprint 4 | RBG Oracle Team 1 | RBG Oracle Team 1 | TE | 2026-09-04 | 25% - Drafted | Khaleel |  | Medium | https://ritchiebros.atlassian.net/browse/DIG-3243 | 2026-08-21 | 2026-09-18 | 2026-07-13 |  |  | RBG | 25% - Drafted | In Progress | Khaleel Shaik​ | 2026-08-10 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:06 |  |  |  | 2026-04-20 | 2026-04-20 | In Progress | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-INT-1174 | Integration | FIN | 1174 |  | DPP | RB & IAA | All | Core - DPP |  | Supplier Master Service (Configuration) | Common Service for Supplier Gold & Dedupe |  | Supplier | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  |  | Oracle Cloud ERP | TE | Sprint 3 | Sprint 3 Sprint 4 | TBD | RBG Oracle Team 1 | TE | 2026-09-04 | 25% - Drafted | Khaleel |  | Medium | https://ritchiebros.atlassian.net/browse/DIG-3243 | 2026-07-17 | 2026-09-18 | 2026-07-13 |  |  | RBG | 25% - Drafted | In Progress | Khaleel Shaik​ | 2026-08-10 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 |  | 50% - Build - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:06 |  |  |  | 2026-04-20 | 2026-04-20 | In Progress | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-INT-1175 | Integration | FIN | 1175 |  | Oracle Core | All | All | Core - DPP |  | Common Services - OIC Component ( Logging / Exception / Error Handling) | OIC Component ( Logging / Exception / Error Handling) |  |  | Finance | RBG |  | Dev-In Progress | No |  | Yes |  |  | OIC | OIC | Sprint 2 | Sprint 3 Sprint 4 | Oracle Team 2 |  |  |  |  | Sharjeel |  | Medium |  | 2026-07-17 | 2026-07-24 | 2026-07-20 | 2026-07-24 | 2026-07-24 | RBG | 75% - Feedback Incorporated | Completed | Sharjeel | 2026-07-24 | 2026-07-24 | 2026-07-23 |  | 2026-07-23 | 2026-08-10 | 75% - Unit Testing - In Progress | In Progress |  | 2026-08-10 | 2026-08-10 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Completed | 2026-07-24 | INT | Finance : Sprint 3 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-INT-1176 | Integration | FIN | 1176 |  |  | DPP |  |  |  | RBG_DPP_GL_Journals_Integration | RBG_DPP_GL_Journals_Integration |  | GL | Finance | RBG |  | #INVALID OPERATION | Yes |  | Duplicate |  | Inbound | FIS | Oracle ERP Cloud |  |  | Oracle Team 2 | Oracle Team 2/IAA FINOPS | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | April 22: Duplicate of FIN-INT-1007 (INT-007) | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1177 | Integration | FIN | 1177 |  | IAA ASAP | RBA |  | IAA |  | FAH Integration update | FAH Integration update |  | FAH | Finance | RBG |  | Dev-In Progress |  | RBG Discovery | Yes |  | Inbound | EBS, GP | Oracle Cloud ERP | Sprint 4 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 1 | IAA FINOPS | Oracle Team | 2026-11-17 | 0% - Not Started | Khaleel |  | Medium | https://ritchiebros.atlassian.net/issues/?filter=29016 | 2026-09-18 | 2026-09-18 |  |  |  | RBG | 0% - Not Started | Not Started | Michael Ortega | 2026-09-14 | 2026-09-14 | 2026-09-11 |  | 2026-09-11 |  | 0% - Not Started | In Progress |  | 2026-09-20 |  | Not Started |  |  | Hi Guys I think we need to add a RICE item or items to cover the changes to the GL Accounting Hub integrations that will need to happen as we rollout. For every legal entity that we go-live with we’ll need to modify the GL Accounting Hub integrations to filter that legal entity out. Not a big change but something we should track. Gavin Rooke | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-18 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1178 | Integration | FIN | 1178 |  | HCM | RBG |  | Core Modules |  | Replace the EBS dependency in the HCM to AD interface | Replace the EBS dependency in the HCM to AD interface |  | HCM | Finance | RBG |  | #INVALID OPERATION |  | RBG Discovery | Yes |  | Outbound | HCM | Active Directory | Sprint 4 | Sprint 5 |  |  | HCM Team |  |  | Jay |  | Medium | [6 empty] | RBG | 0% - Not Started | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Replace the EBS dependency in the HCM to AD interface (we’re currently using EBS as a landing area) Group ID does not support ATP database. Infra team also planning to move off Group ID. Need discussion with them on future plans. There are columns in Active Directory (eg. BU, Dept) that are derived by EBS as well. Need to discuss impact of those data elements changing on downstream systems (Salesforce for example). HCM Extract doesn’t need to change. We just need to modify the part of the interface that feeds group id. Cloud ERP can take that on. Action: @Tenny Rajasekarapandian figure out which Cloud ERP team should do the development. Action: @Tenny Rajasekarapandian to identify which fields EBS is deriving for AD. We can then discuss impacts with other systems. Action: @Gavin Rooke to setup call with Infra team on future of Group ID. (Girish/Sara/Umesh) Action: @Tuhin Bera add to RICE list for tracking. Let Garry know for tracking in plan. Timeline: Needs to be done by the Cloud ERP Phase 2 project before EBS retired. Would be wise to move sooner if possible (could be independent of other Cloud ERP releases). It’s hard to debug right now due to the hops involved. Job title sync issues exist today as well. | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1179 | Integration | FIN | 1179 |  | HCM | RBG |  | Core Modules |  | Merit/STI letters are still generated from EBS (estimated values) | Merit/STI letters are still generated from EBS (estimated values) |  | HCM | Finance | RBG |  | #INVALID OPERATION |  | RBG Discovery | No |  | Outbound | HCM | TBD |  |  |  |  | HCM Team |  |  | Jay |  | Medium | [6 empty] | RBG | 0% - Not Started | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Need to move to Cloud ERP before EBS retired. Action: @Jay Koduri and team to investigate options to create something similar in HCM. Action: @Tuhin Bera add to RICE list for tracking with owner being HCM team. Let Garry know for tracking in plan. | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1180 | Integration | FIN | 1180 | [6 empty] | Contact Us page – uses employee data for TMs in EBS | Contact Us page – uses employee data for TMs in EBS |  | Territory Management | Finance | RBG |  | #INVALID OPERATION |  | RBG Discovery | No - Marked for Tracking |  |  | SFDC | TBD |  |  |  |  | Oracle Team |  |  | Tuhin | [8 empty] | RBG |  | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Madan - https://ritchiebros.atlassian.net/browse/SFS-1856 Territory Manager info by location being sent to the web for contact us page. Source of this data will need to be Salesforce once Territory Management moves to Salesforce as only Salesforce will know how TMs are assigned to geographies. Action: @Tuhin Bera - Verify that there is an Epic for this from our Salesforce meetings last week. Action: @Tuhin Bera add to RICE list for tracking with owner being Salesforce team. Let Garry know for tracking in plan. Timeline: Needs to be done before EBS retired. Would be wise to move sooner if possible (could be independent of other Cloud ERP releases). | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1181 | Integration | FIN | 1181 |  | IP | IP | IronPlanet | IP |  | AR Transactions Integration-IP Web | AR Transactions Integration-IP Web |  | AR | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes |  | Inbound | IP Web | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 2 | Oracle Team 2 | IP Web Team | 2026-09-30 | 25% - Drafted | Sharjeel | Not Started | Medium | https://ritchiebros.atlassian.net/jira/software/projects/IOCM/summary https://ritchiebros.atlassian.net/wiki/spaces/~712020f2d6811a620a4640845080fe8faab33a/pages/3785162822/IronPlanet+Oracle+Cloud+Migration | 2026-08-21 | 2026-09-25 | 2026-08-17 |  |  | Sharjeel | 25% - Drafted | In Progress | Yan Pang | 2026-09-25 |  | 2026-09-24 |  | 2026-09-24 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-11-25 |  | Not Started |  |  | Jenn FP&A - RAID in Progress (3rd July) - New Approach. Risk at business process level. | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-25 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1182 | Integration | FIN | 1182 |  |  | IP |  |  |  | AR Receipts Integration-IP | AR Receipts Integration-IP |  | AR | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | No |  | Inbound | IP Web | Oracle ERP Cloud |  |  | Deloitte | Oracle Team 2 | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1183 | Integration | FIN | 1183 |  |  | IP |  |  |  | AP Invoices Integration-IP | AP Invoices Integration-IP |  | AP | Finance | RBG |  | #INVALID OPERATION | Yes |  | Duplicate |  | Inbound | IP Web | Oracle ERP Cloud |  |  | Oracle Team 2 | Oracle Team 2 | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Apri 23: Duplicate of FIN-INT-1024 | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1184 | Integration | FIN | 1184 |  |  | RBA, IAA & IP |  |  |  | Transaction Entity ? | RBG_Common_Customer_Derivation_Utility, Covered under Customer and Master OIC Utility |  | GL/AR/AP | Finance | RBG |  | #INVALID OPERATION | Yes | RBG Discovery | No |  | NA | DPP/ASAP/Vision/Frontier/IPWeb | Oracle ERP Cloud |  |  | Oracle Team 2 | Oracle Team 2 | [14 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | April 29: Covered in INT-1173 and INT-1174 | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1 | DPP
FIN-INT-1185 | Integration | FIN | 1185 |  |  | All |  |  |  | For Planning and Analytics (PA), Finance Data Extract | For Planning and Analytics (PA), Finance Data Extract |  | AP/AR/GL | Finance | RBG |  | #INVALID OPERATION | Yes |  | Duplicate |  | Outbound | Oracle ERP Cloud | Planning & Analytics (PA) | [18 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | May01: Duplicate of FIN-INT-1083 Apr 22: To be clarified in the Snowflake/CDW workshops. Re-design Possible design change - this should go via CDW | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1186 | Integration | FIN | 1186 |  |  | All |  | Core - DPP |  | Planning and Analytics (PA) HR Data Extract | Planning and Analytics (PA) HR Data Extract |  | HCM | Finance | RBG |  | #INVALID OPERATION | Yes |  | Yes |  | Outbound | Oracle ERP Cloud | Planning and Analytics (PA) | [18 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | Possible design change - this should go via CDW | raramesh@deloitte.ca | 2026-09-09 11:56 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1187 | Integration | FIN | 1187 |  | DPP | RB | RB DPP | Core - DPP |  | RB Customers:DPP to TE | RB Customers: DPP to TE |  | AR | Finance | RBG |  | Delayed | Yes | Imagine Sessions | Yes |  |  | DPP | TE | Sprint 3 | Sprint 3 Sprint 4 | TBD | RBG Oracle Team 1 | TE | 2026-09-04 | 25% - Drafted | John Russ | Not Started | Medium | https://ritchiebros.atlassian.net/browse/DIG-3243 | 2026-07-17 | 2026-08-28 | 2026-07-13 |  |  | RBG | 25% - Drafted | Delayed | Yan Pang | 2026-08-10 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 |  | 50% - Build - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  |  | suchisahoo@deloitte.com | 2026-08-30 22:44 | [5 empty] | Delayed | 2026-08-28 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1 | DPP
FIN-INT-1188 | Integration | FIN | 1188 |  | IP | IP | IronPlanet | IP |  | Customer Master: IP Web to TE | IP Customers: IP Web to TE |  | AR | Finance | RBG |  | Dev-In Progress | Yes | Imagine Sessions | Yes |  | Inbound | IP WEB | TE | Sprint 3 | Sprint 3 Sprint 4 | TBD | TBD | TE | 2026-09-30 | 25% - Drafted | John Russ | Not Started | Medium |  | 2026-07-17 | 2026-07-17 | 2026-07-13 | 2026-07-17 |  | Kyle | 100% - Approved | Completed | John Russ | 2026-07-06 | 2026-07-06 | 2026-07-03 |  | 2026-07-03 | 2026-08-06 | 75% - Unit Testing - In Progress | In Progress | 2026-08-06 | 2026-08-06 | 2026-08-06 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Completed | 2026-07-17 | INT | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-INT-1189 | Integration | FIN | 1189 |  | IAA ASAP | IAA | IAA - ASAP 1 | IAA |  | IAA Customers: ASAP to TE | IAA Customers: ASAP to TE |  | AR | Finance | RBG |  | Dev-In Progress | Yes | Imagine Sessions | Yes |  | Outbound | ASAP | TE | Sprint 3 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 1 | RBG Oracle Team 1 | TE | 2026-09-08 | 25% - Drafted | John Russ | WIP | Medium | https://rbauction.sharepoint.com/:w:/r/sites/VAN-FINFinanceTransformation-OracleCloud-PHASE2/Shared%20Documents/Oracle%20Cloud%20-%20PHASE%202/6.0%20Technology/3.0%20Integrations/INT-1022%20TBD%20-%20Oracle%20Cloud%20(Import%20IP%20Web%20Vendors%20from%20Reltio)/RBG_FIN-INT-1022_Transacting%20Entity%20to%20Oracle%20Cloud%20Suppliers%20Integration%20V1.0%201.docx?d=w312dc630df5d4dec9c006bedc8df9b4e&csf=1&web=1&e=V0FgZ7 | 2026-09-25 | 2026-09-25 | 2026-05-29 | 2026-08-18 | 2026-08-18 | Stephen Park | 100% - Approved | Completed | Michael Ortega | 2026-08-10 | 2026-08-17 | 2026-08-07 |  | 2026-08-14 |  | 75% - Unit Testing - In Progress | In Progress |  | 2026-08-17 | 2026-08-17 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Delayed | 2026-09-25 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
SCM-INT-1190 | Integration | SCM | 1190 |  | DPP | RB | RB Non-Auction | Core - DPP |  | RB Suppliers: SFDC to TE | RB Suppliers: SFDC to TE |  | Procurement | Procurement | RBG |  | Delayed | Yes | Imagine Sessions | Yes |  | Inbound | SalesForce | TE | Sprint 2 | Sprint 3 Sprint 4 | TBD | RBG Oracle Team 1 | TE | 2026-08-31 | 25% - Drafted | John Russ/John Wilkinson |  |  | https://ritchiebros.atlassian.net/browse/DIG-3508 | 2026-07-17 | 2026-08-28 | 2026-07-13 |  |  | RBG | 25% - Drafted | Delayed | RBG | 2026-08-10 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 |  | 50% - Build - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  |  | suchisahoo@deloitte.com | 2026-08-30 22:44 | [5 empty] | Delayed | 2026-08-28 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Procurement : Sprint 3 | Week 1 | Salesforce
SCM-INT-1191 | Integration | SCM | 1191 |  | DPP | RB | RB Non-Auction | Core - DPP |  | RB Suppliers: TE to SFDC | RB Suppliers: TE to SFDC |  | Procurement | Procurement | RBG |  | Delayed | Yes | Imagine Sessions | No |  | Outbound | TE | SalesForce | Sprint 2 | Sprint 3 Sprint 4 | Deloitte | TBD | TE |  |  | John Russ/John Wilkinson |  |  |  | 2026-07-17 | 2026-07-17 | 2026-05-29 |  |  | RBG | 50% - Reviewed | Delayed | RBG | [6 empty] | 25% - Tech Spec - In Progress | In Progress |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-07-17 | INT | Procurement : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1 | Salesforce
SCM-INT-1192 | Integration | SCM | 1192 |  | IP | IP | IronPlanet | IP |  | IP Supplier: IP Web to TE | IP Supplier: IP Web to TE |  | Procurement | Procurement | RBG |  | Dev-In Progress | Yes | Imagine Sessions | Yes |  | Inbound | IP WEB | TE | Sprint 3 | Sprint 3 Sprint 4 | TBD | TBD | TE | 2026-09-30 | 25% - Drafted | John Russ | Not Started | Medium |  | 2026-07-17 | 2026-07-17 | 2026-07-13 | 2026-07-17 |  | Kyle | 100% - Approved | Completed | John Russ | 2026-07-06 | 2026-07-06 | 2026-07-03 |  | 2026-07-03 | 2026-08-06 | 75% - Unit Testing - In Progress | In Progress | 2026-08-06 | 2026-08-06 | 2026-08-06 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Completed | 2026-07-17 | INT | Procurement : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Procurement : Sprint 3 | Week 1
SCM-INT-1193 | Integration | SCM | 1193 |  | IAA ASAP | IAA | IAA - ASAP 1 | IAA |  | IAA Suppliers: ASAP to TE | IAA Suppliers: ASAP to TE |  | Procurement | Procurement | RBG |  | Dev-In Progress | Yes | Imagine Sessions | Yes |  | Outbound | ASAP | TE | Sprint 3 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 1 | RBG Oracle Team 1 | TE | 2026-09-08 | 25% - Drafted | John Russ | WIP | Medium | https://rbauction.sharepoint.com/:w:/r/sites/VAN-FINFinanceTransformation-OracleCloud-PHASE2/Shared%20Documents/Oracle%20Cloud%20-%20PHASE%202/6.0%20Technology/3.0%20Integrations/INT-1022%20TBD%20-%20Oracle%20Cloud%20(Import%20IP%20Web%20Vendors%20from%20Reltio)/RBG_FIN-INT-1022_Transacting%20Entity%20to%20Oracle%20Cloud%20Suppliers%20Integration%20V1.0%201.docx?d=w312dc630df5d4dec9c006bedc8df9b4e&csf=1&web=1&e=V0FgZ7 | 2026-09-25 | 2026-09-25 | 2026-05-29 | 2026-08-18 | 2026-08-18 | Stephen Park | 100% - Approved | Completed | Michael Ortega | 2026-08-10 | 2026-08-17 | 2026-08-07 |  | 2026-08-14 |  | 75% - Unit Testing - In Progress | In Progress |  | 2026-08-17 | 2026-08-17 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Delayed | 2026-09-25 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Procurement : Sprint 3 | Week 1
SCM-INT-1194 | Integration | SCM | 1194 |  |  | IAA | IAA - ASAP 1 |  |  | Supplier Master | IAA Supplier: Oracle to ASAP & Supplier Banking Details |  | Procurement | Procurement | RBG |  | Delayed | Yes | Imagine Sessions | Duplicate |  | Outbound | Oracle Cloud ERP | ASAP | Sprint 1 | Sprint 2 Sprint 3 | Deloitte | IAA FINOPS | IAA Team |  |  | Khaleel |  |  |  | 2026-06-12 |  |  |  |  | RBG | 0% - Not Started | Delayed | Michael Ortega | [6 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-06-12 | INT | Procurement : Gap Sprint | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
SCM-INT-1195 | Integration | SCM | 1195 |  |  | All |  |  |  | Supplier Master | Suppliers: TE to Oracle |  | Procurement | Procurement | RBG |  | #INVALID OPERATION | Yes | Imagine Sessions | Duplicate |  | Inbound | TE | Oracle ERP Cloud | [18 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
SCM-INT-1196 | Integration | SCM | 1196 |  |  | All |  |  |  | Supplier Master | Suppliers: Oracle to TE |  | Procurement | Procurement | RBG |  | #INVALID OPERATION | Yes | Imagine Sessions | Duplicate |  | Outbound | Oracle ERP Cloud | TE | [18 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1197 | Integration | FIN | 1197 |  |  | All |  |  |  | Customer Master | Customers: TE to Oracle |  | AR | Finance | RBG |  | #INVALID OPERATION | Yes | Imagine Sessions | Duplicate |  | Inbound | TE | Oracle ERP Cloud | [18 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1198 | Integration | FIN | 1198 |  | DPP | All | All | Core - DPP |  | Customers: Oracle to TE | Customers: Oracle to TE |  | AR | Finance | RBG |  | Delayed | Yes | Imagine Sessions | Yes |  | Outbound | Oracle Cloud ERP | TE | Sprint 3 | Sprint 3 Sprint 4 | RBG Oracle Team 2 | RBG Oracle Team 1 | TE | 2026-08-31 | 50% - Reviewed | Khaleel |  | Medium |  | 2026-07-17 | 2026-08-28 | 2026-05-29 |  |  | RBG | 50% - Reviewed | Delayed | RBG | 2026-08-10 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  |  | suchisahoo@deloitte.com | 2026-08-30 22:44 | [5 empty] | Delayed | 2026-08-28 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
SCM-INT-1199 | Integration | SCM | 1199 |  | CDW | All | All |  |  | Suppliers: Oracle to CDW/SNOWFLAKE | Suppliers: Oracle to CDW/SNOWFLAKE |  | Procurement | Procurement | RBG |  | Delayed | Yes | Imagine Sessions | No |  | Outbound | Oracle Cloud ERP | CDW (Big Data -> Snowflake) | Sprint 2 | Sprint 3 Sprint 4 | Deloitte | RBG Oracle Team 1 | CDW Team |  |  | Khaleel |  |  |  | 2026-07-17 | 2026-07-17 | 2026-05-29 |  |  | RBG | 25% - Drafted | Delayed | Khaleel Shaik | [6 empty] | 25% - Tech Spec - In Progress | In Progress |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-07-17 | INT | Procurement : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
SCM-INT-1201 | Integration | SCM | 1201 |  | CDW | All | All | Core - DPP |  | Suppliers: TE to CDW/SNOWFLAKE | Suppliers: TE to CDW/SNOWFLAKE |  | Procurement | Procurement | RBG |  | Delayed | Yes | Imagine Sessions | Yes |  |  | TE | CDW (Big Data -> Snowflake) | Sprint 2 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 1 | RBG Oracle Team 1 | CDW Team | 2026-08-31 | 50% - Reviewed | John Russ/Chris Rowinski |  |  |  | 2026-07-17 | 2026-08-28 | 2026-05-29 |  |  | RBG | 25% - Drafted | Delayed | John Russ/Chris Rowinski | 2026-09-14 | 2026-09-14 | 2026-09-11 |  | 2026-09-11 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  |  | suchisahoo@deloitte.com | 2026-08-30 22:44 | [5 empty] | Not Started | 2026-08-28 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1202 | Integration | FIN | 1202 |  | CDW | All | All | Core - DPP |  | Customers: TE to CDW/SNOWFLAKE | Customers: TE to CDW/SNOWFLAKE |  | AR | Finance | RBG |  | Delayed | Yes | Imagine Sessions | Yes |  |  | TE | CDW (Big Data -> Snowflake) | Sprint 2 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 1 | RBG Oracle Team 1 | CDW Team | 2026-08-31 | 50% - Reviewed | John Russ/Chris Rowinski |  | Medium |  | 2026-07-17 | 2026-08-28 | 2026-05-29 |  |  | RBG | 25% - Drafted | Delayed | John Russ/Chris Rowinski | 2026-09-14 | 2026-09-14 | 2026-09-11 |  | 2026-09-11 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  |  | suchisahoo@deloitte.com | 2026-08-30 22:44 | [5 empty] | Not Started | 2026-08-28 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1203 | Integration | FIN | 1203 |  | DPP | RB & IP | RB DPP | Core - DPP |  | AE - RB Collection Oracle Upload Contacts to AE [Collections] | AE - RB Collection Oracle Upload Contacts to AE | 1 | CL | Finance | Deloitte | SIT 1 - Wk 5 | Delayed | Yes | Imagine Sessions | Yes |  | Outbound | Oracle Cloud ERP | Acqueon Dialer | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Deloitte | Oracle Team 2 |  |  | Sharjeel | Not Started | Medium |  | 2026-07-03 | 2026-09-04 |  |  |  | Harsh Rawal | 75% - Feedback Incorporated | Delayed | Suchitra Sahoo | 2026-08-26 |  | 2026-09-09 |  | 2026-09-09 |  | 0% - Not Started | Delayed |  | 2026-10-06 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:16 |  |  | 99 |  |  | Delayed | 2026-09-04 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1204 | Integration | FIN | 1204 |  | DPP | RB & IP | RB DPP | Core - DPP |  | AE - RB Contact Results to Oracle [Collections] | AE - RB Contact Results to Oracle | 1 | CL | Finance | Deloitte | SIT 1 - Wk 5 | F-Spec-In Progress | Yes | Imagine Sessions | Yes |  | Inbound | Acqueon Dialer | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Deloitte | Oracle Team 2 |  |  | Sharjeel | Not Started | Medium |  | 2026-07-03 | 2026-09-10 |  |  |  | Harsh Rawal | 25% - Drafted | In Progress | Suchitra Sahoo | 2026-08-31 |  | 2026-09-14 |  | 2026-09-14 |  | 0% - Not Started | Not Started |  | 2026-10-06 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:16 |  |  | 99 |  |  | Not Started | 2026-09-10 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1205 | Integration | FIN | 1205 |  | DPP | RB & IP | RB DPP | Core - DPP |  | AE - RB Contact Failures to Oracle [Collections] | AE - RB Contact Failures to Oracle | 1 | CL | Finance | Deloitte | SIT 1 - Wk 5 | F-Spec-In Progress | Yes | Imagine Sessions | Yes |  | Inbound | Acqueon Dialer | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Deloitte | Oracle Team 2 |  |  | Sharjeel | Not Started | Complex |  | 2026-07-03 | 2026-09-10 |  |  |  | Harsh Rawal | 25% - Drafted | In Progress | Suchitra Sahoo | 2026-09-07 |  | 2026-09-29 |  | 2026-09-29 |  | 0% - Not Started | Not Started |  | 2026-10-06 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:16 |  |  | 153 |  |  | Not Started | 2026-09-10 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : SIT 2 | Week 1
FIN-INT-1206 | Integration | FIN | 1206 |  | DPP | RB & IP | RB DPP | Core - DPP |  | AE - RB Collection AE Phone Calls Status to Oracle [Collections] | AE - RB Collection AE Phone Calls Status to Oracle | 1 | CL | Finance | Deloitte | SIT 1 - Wk 5 | F-Spec-In Progress | Yes | Imagine Sessions | Yes |  | Inbound | Acqueon Dialer | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Deloitte | Oracle Team 2 |  |  | Sharjeel | Not Started | Complex |  | 2026-07-03 | 2026-09-10 |  |  |  | Harsh Rawal | 25% - Drafted | In Progress | Suchitra Sahoo | 2026-09-14 |  | 2026-10-06 |  | 2026-10-06 |  | 0% - Not Started | Not Started |  | 2026-10-06 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:16 |  |  | 153 |  |  | Not Started | 2026-09-10 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : SIT 2 | Week 1
FIN-INT-1207 | Integration | FIN | 1207 |  | IP | IP | IronPlanet | IP |  | Import Journals (GTV) | GTV(Gross Transaction value) - (Current process in EBS, read AR distribution where source is IP Web , build and push Journal to GL) |  | AR/GL | Finance | RBG |  | Delayed | Yes | Imagine Sessions | Yes |  | Inbound | Oracle Cloud ERP | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 2 | Oracle Team 2 |  | 2026-09-30 | 0% - Not Started | Sharjeel | Not Started | Medium | https://ritchiebros.atlassian.net/jira/software/projects/IOCM/summary https://ritchiebros.atlassian.net/wiki/spaces/~712020f2d6811a620a4640845080fe8faab33a/pages/3785162822/IronPlanet+Oracle+Cloud+Migration | 2026-08-21 | 2026-08-28 | 2026-07-13 |  |  | Sharjeel | 25% - Drafted | Delayed | Yan Pang | 2026-09-14 |  | 2026-09-11 |  | 2026-09-11 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-11-14 |  | Not Started |  |  |  | suchisahoo@deloitte.com | 2026-08-30 22:44 | [5 empty] | Not Started | 2026-08-28 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1208 | Integration | FIN | 1208 |  | IP | IP | IronPlanet | IP |  | AP Invoice Status back to IP | Update AP Invoice status back to IP Web |  | AP | Finance | RBG |  | Not Started | Yes | Imagine Sessions | Yes |  | Outbound | Oracle Cloud ERP | IP Web | Sprint 3 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 2 | Oracle Team 2 | IP Web | 2026-09-30 | 0% - Not Started | Sharjeel | Not Started | Medium | https://ritchiebros.atlassian.net/jira/software/projects/IOCM/summary https://ritchiebros.atlassian.net/wiki/spaces/~712020f2d6811a620a4640845080fe8faab33a/pages/3785162822/IronPlanet+Oracle+Cloud+Migration | 2026-08-21 | 2026-09-25 |  |  |  | Sharjeel | 0% - Not Started | Not Started | Yan Pang | 2026-09-25 |  | 2026-09-24 |  | 2026-09-24 |  | 0% - Not Started | Not Started |  | 2026-11-25 |  | Not Started |  |  | Through Kafka Topic. | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-25 | INT
FIN-INT-1210 | Integration | FIN | 1210 |  | IP | IP | IronPlanet | IP |  | IP Inspector Invoice Status back to IP Web | Update IP Inspector AP Invoice status back to IP Web |  | AP | Finance | RBG |  | Not Started | Yes | Imagine Sessions | Yes |  | Outbound | Oracle Cloud ERP | IP Web | Sprint 3 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 2 | Oracle Team 2 | IP Web | 2026-09-30 | 0% - Not Started | Sharjeel | Not Started | Medium | https://ritchiebros.atlassian.net/jira/software/projects/IOCM/summary https://ritchiebros.atlassian.net/wiki/spaces/~712020f2d6811a620a4640845080fe8faab33a/pages/3785162822/IronPlanet+Oracle+Cloud+Migration | 2026-08-21 | 2026-09-25 |  |  |  | Sharjeel | 0% - Not Started | Not Started | Yan Pang | 2026-09-25 |  | 2026-09-24 |  | 2026-09-24 |  | 0% - Not Started | Not Started |  | 2026-11-25 |  | Not Started |  |  | Through Kafka Topic. | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-25 | INT
FIN-INT-1211 | Integration | FIN | 1211 |  |  | RB | RB Non-Auction | Core Modules |  | Positive Pay Template for RBC | Customize Positive Pay Template for RBC | 1 | AP | Finance | Deloitte | Before SIT 1 | Completed | No | Imagine Sessions | Yes | BI | Outbound | Oracle Cloud ERP | Banks | Sprint 1 | Sprint 2 | Deloitte | Deloitte |  |  |  | Sharjeel |  | Medium |  | 2026-05-01 |  |  | 2026-05-01 |  | Lara Chalak | 100% - Approved | Completed | Suchitra Sahoo | 2026-06-02 | 2026-06-02 | 2026-06-16 |  | 2026-06-16 | 2026-06-09 | 100% - Complete | Completed |  |  | 2026-08-14 | Completed |  |  |  | raramesh@deloitte.ca | 2026-09-10 14:47 |  |  | 99 |  |  | Completed | 2026-05-01 | INT | Finance : Sprint 1 | [7 empty] | Finance : Sprint 2
FIN-INT-1212 | Integration | FIN | 1212 |  |  | IAA | IAA - CAN & UK | IAA |  | Positive Pay Template for BMO | Customize Positive Pay Template for BMO |  | AP | Finance | Deloitte | SIT 1 - Wk 3 | Dev-In Progress | Yes | Imagine Sessions | Yes | BI | Outbound | Oracle Cloud ERP | Banks | Sprint 2 | Sprint 2 Sprint 3 | Deloitte | Deloitte |  |  |  | Sharjeel |  | Medium |  | 2026-07-03 | 2026-08-25 |  | 2026-08-28 | 2026-09-01 | Yago Ramos | 100% - Approved | Completed | Nivethitha Nath | 2026-08-03 | 2026-08-31 | 2026-08-17 |  | 2026-09-14 |  | 75% - Unit Testing - In Progress | In Progress |  | 2026-09-11 |  | Not Started | Yes |  |  | dipriverma@deloitte.ca | 2026-09-10 12:32 |  |  | 99 |  |  | Not Started | 2026-08-25 | INT
FIN-INT-1213 | Integration | FIN | 1213 |  | IAA ASAP | IAA | IAA - ASAP 1 | IAA |  | AP Transactions writeback to ASAP | AP Transactions writeback to ASAP |  | AP | Finance | RBG |  | Dev-In Progress | Yes | RBG Discovery | Yes | BI | Outbound | Oracle Cloud ERP | ASAP | Sprint 4 | Sprint 4 Sprint 5 | Oracle Team 2 | IAA FINOPS | IAA Team | 2026-12-14 | 0% - Not Started | Sharjeel |  | Medium | https://ritchiebros.atlassian.net/issues/?filter=29016 | 2026-09-18 | 2026-10-05 |  |  |  | RBG | 0% - Not Started | Not Started | Michael Ortega | 2026-10-05 |  | 2026-10-02 |  | 2026-10-02 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-12-05 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-10-05 | INT | Finance : SIT 1 | [7 empty] | Finance : SIT 2
FIN-INT-1214 | Integration | FIN | 1214 |  | IP | IP | IronPlanet | IP |  | AR Invoice Status back to IP Web | Update AR Invoice status back to IP Web |  | AR | Finance | RBG |  | Not Started | Yes | Imagine Sessions | Yes |  | Outbound | Oracle Cloud ERP | IP Web | Sprint 3 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 2 | Oracle Team 2 | IP Web | 2026-09-30 | 0% - Not Started | Sharjeel | Not Started | Medium | https://ritchiebros.atlassian.net/jira/software/projects/IOCM/summary https://ritchiebros.atlassian.net/wiki/spaces/~712020f2d6811a620a4640845080fe8faab33a/pages/3785162822/IronPlanet+Oracle+Cloud+Migration | 2026-08-21 | 2026-09-25 |  |  |  | Sharjeel | 0% - Not Started | Not Started | Yan Pang | 2026-09-25 |  | 2026-09-24 |  | 2026-09-24 |  | 0% - Not Started | Not Started |  | 2026-11-25 |  | Not Started |  |  | Through Kafka Topic. | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-25 | INT
FIN-INT-1215 | Integration | FIN | 1215 |  |  | RB | RB Non-Auction | STAT |  | STAT Ledger: Integration Changes | STAT Ledger: Integration Changes |  | GL | Finance | Deloitte | Not Applicable | Completed | No | Business need | Yes | OIC | Inbound | Oracle Cloud ERP | EBS | Sprint 1 | Sprint 1 | Deloitte | Deloitte |  |  |  | Khaleel |  | Simple |  | 2026-05-01 | 2026-05-01 |  | 2026-05-01 | 2026-05-06 | Deepankar Gera | 100% - Approved | Completed | Piyush Ojha | 2026-05-07 | 2026-05-07 | 2026-05-11 |  | 2026-05-11 | 2026-05-29 | 100% - Complete | Completed |  | 2026-06-12 | 2026-06-12 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:17 |  |  | 24 |  |  | Completed | 2026-05-01 | INT | Finance : Sprint 1 | [7 empty] | Finance : Sprint 2
FIN-INT-1216 | Integration | FIN | 1216 |  |  | RB | RB Non-Auction | Already Live |  | HCM - Fidelity Interface | HCM - Fidelity Interface |  | HCM | HCM | Deloitte | Not Applicable | Completed | No | Business need | Yes | OIC | Inbound | Oracle Cloud ERP | Fidelity | Sprint 1 | Sprint 1 | Deloitte | Deloitte |  |  |  | Jay |  | Medium |  | 2026-05-01 | 2026-05-01 |  | 2026-05-01 | 2026-05-06 | Diprish Verma | 100% - Approved | Completed | Piyush Ojha | 2026-05-07 | 2026-05-07 | 2026-05-21 |  | 2026-05-21 | 2026-05-22 | 100% - Complete | Completed |  |  | 2026-05-26 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:17 |  |  | 99 |  |  | Completed | 2026-05-01 | INT
FIN-INT-1217 | Integration | FIN | 1217 |  |  | RB |  | ARCS |  | ARCS PAR Reconciliation ADP File Automation | ARCS - Ingest ADP Statements into Oracle ARCS |  | ARCS (ADP) | Finance | Deloitte | Not Applicable | Delayed | No | Business need | Yes | OIC | Inbound | Oracle Cloud ERP | ADP | Sprint 3 | Sprint 2 | Deloitte | Deloitte | ADP (Kathy) |  |  | Markus |  | Medium |  | 2026-06-08 | 2026-08-03 |  |  |  | Aiden Lee | 50% - Reviewed | Delayed | AnuPriya Vellingiri | 2026-08-31 | 2026-09-09 | 2026-09-14 |  | 2026-09-23 |  | 50% - Build - In Progress | In Progress |  | 2026-09-25 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:17 |  |  | 99 |  |  | Not Started | 2026-08-03 | INT | Finance : Sprint 3
SCM-INT-1218 | Integration | SCM | 1218 |  | Mascus | Mascus | Mascus | Mascus |  | Create/Manage Subscriptions in Oracle Cloud ERP | Operation Required, Create / Amend / Renew and Close need to be supported by the integration, need status back |  | SM | Procurement | Deloitte | SIT 1 - Wk 2 | Delayed | Yes | Imagine Sessions | Yes | OIC | Inbound | Mascus/Salesforce | Oracle Cloud ERP | Sprint 2 | Sprint 3 | Deloitte | Deloitte | Jun, Martijn |  |  | Jun/Gurpreet | WIP | Very Complex |  | 2026-07-03 | 2026-08-21 |  |  |  | Deepak Verma | 75% - Feedback Incorporated | Delayed | DK, Anirudh | 2026-08-21 | 2026-08-21 | 2026-09-14 |  | 2026-09-14 |  | 75% - Unit Testing - In Progress | In Progress |  | 2026-09-25 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:17 |  |  | 153 |  |  | Not Started | 2026-08-21 | INT | Procurement : Sprint 3 | [9 empty] | Salesforce
FIN-INT-1219 | Integration | FIN | 1219 |  |  | IAA | IAA - ASAP 1 IAA - CAN & UK | IAA |  | Property Works Integration (Lease Information) | Property Works Integration |  | Lease Accounting | Finance | Deloitte |  | Delayed | Yes | Business need | Yes |  | Inbound | Property Works | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 |  | Deloitte |  |  |  | Khaleel |  | Medium |  | 2026-07-10 | 2026-09-01 |  |  |  | Deshantha Clement Jayasekera | 25% - Drafted | Delayed | Suchitra Sahoo | 2026-08-17 |  | 2026-08-31 |  | 2026-08-31 |  | 0% - Not Started | Delayed |  |  |  | Not Started |  |  |  | nivnath@deloitte.com | 2026-09-02 00:02 |  |  | 99 |  |  | Delayed | 2026-09-01 | INT
FIN-INT-1220 | Integration | FIN | 1220 |  | Mascus | Mascus | Mascus | Mascus |  | Settlement file from Adyen to Oracle CM for reconciliation | scheduled job (push from Adyen) + ad-hoc user download (also triggers Boomi web service). Both routes import to Cash Management. | 1 | AR | Finance | Deloitte | SIT 1 - Wk 1 | Delayed | Yes | Imagine Sessions | Yes |  | Inbound | Adyen | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Deloitte | Jun, Martijn |  |  | Jun/Gurpreet | WIP | Complex |  | 2026-07-10 | 2026-08-21 |  | 2026-08-27 |  | Harsh Rawal | 100% - Approved | Completed | Vidul Kabra | 2026-08-20 | 2026-08-20 | 2026-09-11 | 2026-10-02 | 2026-09-11 |  | 75% - Unit Testing - In Progress | In Progress |  | 2026-09-07 |  | Delayed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:33 |  |  | 153 |  |  | Not Started | 2026-08-21 | INT | Finance : Sprint 3
FIN-INT-1221 | Integration | FIN | 1221 |  | Mascus | Mascus | Mascus | Mascus |  | AR → Salesforce Financial View (Send data to Kafka queues) | Subscribe to Business Events and send enriched information to Kafka queue for Invoices on completion and paid; Credit Memo completion Business Events: Invoice Completed, Invoice Paid, Credit Memo Completed |  | AR | Finance | Deloitte |  | Delayed | Yes | Imagine Sessions | Yes |  | Outbound | Oracle Cloud ERP | Mascus/Salesforce | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Deloitte | Jun, Martijn |  |  | Jun/Gurpreet | WIP | Complex |  | 2026-07-10 | 2026-09-04 |  |  |  | Venkata Kiran Kumar Pallantla | 0% - Not Started | Delayed | Diprish Verma | 2026-08-31 |  | 2026-09-22 |  | 2026-09-22 |  | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | nivnath@deloitte.com | 2026-09-06 22:40 |  |  | 153 |  |  | Not Started | 2026-09-04 | INT | [10 empty] | Salesforce
FIN-INT-1222 | Integration | FIN | 1222 |  | Mascus | Mascus | Mascus | Mascus |  | PayPal Settlement File to Oracle CM | PayPal Settlement CSV to Oracle CM | 1 | AR | Finance | Deloitte | SIT 1 - Wk 1 | Dev-In Progress | Yes | Imagine Sessions | Yes |  | Inbound | Paypal | Oracle Cloud ERP | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Deloitte | Jun, Martijn |  |  | Jun/Gurpreet | WIP | Medium |  | 2026-07-10 | 2026-08-28 |  | 2026-08-28 | 2026-09-02 | Harsh Rawal | 100% - Approved | Completed | Vidul Kabra | 2026-09-07 | 2026-09-07 | 2026-09-21 | 2026-10-02 | 2026-09-21 |  | 75% - Unit Testing - In Progress | In Progress |  | 2026-09-14 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:33 |  |  | 99 |  |  | Not Started | 2026-08-28 | INT
SCM-INT-1223 | Integration | SCM | 1223 |  |  | Mascus | Mascus |  |  | PIM Integration – Place Holder integration | PIM Integration – Place Holder integration |  | PIM |  | Deloitte |  | Delayed | Yes | Imagine Sessions | No |  | Inbound | Mascus/Salesforce | Oracle Cloud ERP | Sprint 2 | Sprint 2 Sprint 3 | Deloitte | Deloitte | MASCUS Team |  |  | Jun/Gurpreet | WIP | Complex |  | 2026-07-10 |  |  |  |  | Rajat Arora | 0% - Not Started | Delayed | Diprish Verma | [6 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 153 |  |  | Not Started | 2026-07-10 | INT | [10 empty] | Salesforce
SCM-INT-1224 | Integration | SCM | 1224 |  | HCM |  | All | Core Modules |  | Create Purchase Orders - OTL | Create Purchase Orders - OTL |  | Procurement | Procurement | Deloitte | SIT 1 - Wk 2 | Delayed | No | Business need | Yes |  | Inbound | Oracle Cloud ERP | Oracle Cloud ERP | Sprint 3 | Sprint 3 | Deloitte | Deloitte |  |  |  | Khaleel | WIP | Medium |  |  | 2026-08-25 |  |  |  | Deepak Verma | 75% - Feedback Incorporated | Delayed | Mohammad Juned | 2026-09-14 | 2026-09-07 | 2026-09-28 | 2026-10-09 | 2026-09-21 |  | 50% - Build - In Progress | In Progress |  | 2026-09-25 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:34 |  |  | 99 |  |  | Not Started | 2026-08-25 | INT
SCM-INT-1225 | Integration | SCM | 1225 |  | HCM |  | All | Core Modules |  | Create Receipts - OTL | Create Receipts - OTL |  | Procurement | Procurement | Deloitte |  | Delayed | No | Business need | Yes |  | Inbound | Oracle Cloud ERP | Oracle Cloud ERP | Sprint 3 | Sprint 3 | Deloitte | Deloitte |  |  |  | Khaleel | WIP | Complex |  |  | 2026-08-25 |  |  |  | Deepak Verma | 25% - Drafted | Delayed | Suchitra Sahoo | 2026-09-21 |  | 2026-10-13 |  | 2026-10-13 |  | 0% - Not Started | Not Started |  | 2026-10-02 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:06 |  |  | 153 |  |  | Not Started | 2026-08-25 | INT | [8 empty] | Procurement : SIT 2
FIN-INT-1226 | Integration | FIN | 1226 |  | IAA ASAP | RB | IAA - ASAP 1 | IAA |  | Oracle ERP Cloud data access to IAA BI system | Oracle ERP Cloud data access to IAA BI system |  | EDW |  | RBG |  | Not Started | Yes | Business need | Yes |  | Inbound | Oracle Cloud ERP | IAA BI | Sprint 3 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 1 | IAA FINOPS | CDW | 2026-12-14 | 0% - Not Started | Khaleel | WIP | Medium | https://ritchiebros.atlassian.net/issues/?filter=29016 | 2026-09-18 | 2026-09-25 |  |  |  | RBG | 0% - Not Started | Not Started | RBG | 2026-10-05 |  | 2026-10-02 |  | 2026-10-02 |  | 0% - Not Started | Not Started |  | 2026-12-05 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-25 | INT
FIN-INT-1227 | Integration | FIN | 1227 |  | DPP | RB | All | Core - DPP |  | COA Data Feed for SFDC - Source - ERP Cloud, Target - CDW | COA Data Feed for SFDC - Source - ERP Cloud, Target - CDW |  | SFDC |  | RBG |  | Delayed | Yes | Business need | Yes |  | Outbound | Oracle Cloud ERP | SalesForce | Sprint 3 | Sprint 3 Sprint 4 | RBG Oracle Team 2 | Oracle Team 2 |  |  | 25% - Drafted | Khaleel | WIP | Medium |  | 2026-08-21 | 2026-08-21 | 2026-05-29 |  |  | RBG | 25% - Drafted | Delayed | RBG | 2026-08-10 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Delayed | 2026-08-21 | INT | [10 empty] | Salesforce
FIN-INT-1228 | Integration | FIN | 1228 |  | CDW | All | All | Core - DPP |  | Management Reporting Hierarchy | Management Reporting Heoarchy |  | All |  | RBG |  | Delayed | No | Discovery | Yes |  | Outbound | Oracle Cloud ERP | CDW | Sprint 2 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 1 | Oracle Team 1 | CDW Team |  | 25% - Drafted | Khaleel | WIP | Medium |  | 2026-07-17 | 2026-08-21 | 2026-07-13 |  |  | Syed Imran Waheed | 25% - Drafted | Delayed | Khaleel Shaik | [6 empty] | 25% - Tech Spec - In Progress | In Progress |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started | 2026-08-21 | INT
FIN-INT-1229 | Integration | FIN | 1229 |  | IAA ASAP | IAA | All | IAA |  | Oracle ERP Cloud data access to IAA BI system | Oracle ERP Cloud data access to IAA BI system |  | All |  | RBG |  | Not Started | No | Discovery | Yes |  | Outbound | Oracle Cloud ERP | IAA BI | Sprint 3 | Sprint 3 Sprint 4 Sprint 5 | RBG Oracle Team 1 | Oracle Team 1 | IAA BI | 2026-12-14 | 0% - Not Started | Khaleel | WIP | Medium | https://ritchiebros.atlassian.net/issues/?filter=29016 | 2026-09-18 | 2026-09-25 |  |  |  | Khaleel Shaik | 0% - Not Started | Not Started | RBG | 2026-10-05 |  | 2026-10-02 |  | 2026-10-02 |  | 0% - Not Started | Not Started |  | 2026-12-05 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Not Started | 2026-09-25 | INT
FIN-INT-1230 | Integration | FIN | 1230 |  |  |  | ARCS | ARCS |  | Send Payroll Account Analysis Report to File Server | Send Payroll Account Analysis Report to OIC File Server for further processing in ARCS Data Integration Pipeline |  | Payroll/GL | Finance | Deloitte | Not Applicable | Completed | No | Business need | Yes |  | Outbound | Oracle Cloud ERP | File Server (OIC) | Sprint 2 | Sprint 2 | Deloitte | Deloitte | [5 empty] | Simple |  | 2026-07-06 |  | 2026-07-06 | 2026-07-10 |  | Aiden Lee | 100% - Approved | Completed | Suchitra Sahoo | 2026-07-13 | 2026-07-14 | 2026-07-27 |  | 2026-07-28 | 2026-07-21 | 100% - Complete | Completed |  |  |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-09-10 12:19 |  |  | 99 |  |  | Completed | 2026-07-06 | INT | Finance : Sprint 2 | [7 empty] | Finance : Sprint 3
FIN-INT-1231 | Integration | FIN | 1231 |  | Mascus |  | All | Core - DPP |  | UI validation for Suppliers and Customers | UI validation for Suppliers and Customers |  | Procurement |  | RBG |  | Delayed | Yes | RBG Discovery | Yes |  | Inbound & Outbound | All Auction Systems | TE | Sprint 3 | Sprint 4 Sprint 5 | Oracle Team 1 |  | All | 2026-08-31 | 0% - Not Started | Kyle |  | Medium |  | 2026-08-21 | 2026-08-21 | 2026-07-13 |  |  | TUHIN BERA | 25% - Drafted | Delayed | Kyle | 2026-08-10 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-09-20 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:06 | [5 empty] | Delayed | 2026-08-21 | INT
FIN-INT-1232 | Integration | FIN | 1232 |  | CDW |  | RB DPP | Core - DPP |  | Marketing List | Marketing List |  | Marketing |  | RBG |  | #INVALID OPERATION | No | RBG Discovery | Yes |  | Outbound |  |  | Sprint 3 | Sprint 4 Sprint 5 | Oracle Team 1 | [6 empty] | Medium | [6 empty] | Mike F | 0% - Not Started | #INVALID OPERATION | Mike F | [6 empty] | 25% - Tech Spec - In Progress | In Progress |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | INT
FIN-INT-1233 | Integration | FIN | 1233 |  |  |  | All | IAA |  | Positive Pay Template for Wells Fargo | Customize Positive Pay Template for Wells Fargo |  | AP | Finance | Deloitte | SIT 1 - Wk 3 | Delayed | No | Business need | Yes |  | Outbound | Oracle Cloud ERP | Banks | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Deloitte |  |  |  | Sharjeel |  | Medium |  | 2026-07-31 | 2026-08-24 |  |  |  | Yago Ramos | 75% - Feedback Incorporated | Delayed | Chinmaya Sahoo | 2026-08-20 | 2026-08-20 | 2026-09-03 |  | 2026-09-03 | 2026-08-27 | 75% - Unit Testing - In Progress | In Progress |  | 2026-09-18 |  | Not Started | Yes |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 99 |  |  | Completed | 2026-08-24 | INT
FIN-INT-1234 | Integration | FIN | 1234 |  |  |  | RB DPP | Core - DPP |  | DPP work SFDC eBS Decoupling | [6 empty] | #INVALID OPERATION | [25 empty] | #INVALID OPERATION | [8 empty] | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-02 11:54 | [5 empty] | Not Started |  | INT
FIN-INT-1235 | Integration | FIN | 1235 |  | DPP | RB & IP | RB DPP | Core - DPP |  | AE – Compliance Real Time Integration (DND) [Collections] | AE – Compliance Real Time Integration (DND) | 1 | CL | Finance | Deloitte |  | F-Spec-In Progress | Yes | Imagine Sessions | Yes |  | Outbound | Oracle Cloud ERP | Acqueon Dialer | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Deloitte | Oracle Team 2 |  |  | Sharjeel | Not Started | Medium |  | 2026-07-10 | 2026-09-11 |  |  |  | Harsh Rawal | 50% - Reviewed | In Progress | Suchitra Sahoo | 2026-11-02 |  | 2026-11-23 |  | 2026-11-23 |  | 0% - Not Started | Not Started |  | 2026-10-06 |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-09 07:25 |  |  | 144 |  |  | Not Started | 2026-09-11 | INT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-INT-1236 | Integration | FIN | 1236 |  | DPP |  | RB DPP | Core - DPP |  | Lien Holder Synchronization b/w Oracle Cloud & Control Tower Liens |  |  |  |  | RBG |  | #INVALID OPERATION |  |  | Yes |  | Inbound & Outbound | Oracle Cloud ERP | Control Tower | [7 empty] | Kyle Boon | Not Started | [9 empty] | #INVALID OPERATION | [8 empty] | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-04 07:29 | [5 empty] | Not Started |  | INT
FIN-RPT-001 | Report | FIN | 001 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-001 | Custom Security Report | Report to provide users and their access to Ledgers, Data Access Sets, etc |  | GL | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP | NA (end user report) | Sprint 1 | Sprint 1 | Deloitte | Deloitte | [5 empty] | Simple |  | 2026-04-10 |  |  | 2026-04-10 |  | Diprish Verma | 100% - Approved | Completed | Nivethitha Nath | 2026-04-13 | 2026-04-13 | 2026-04-20 |  | 2026-04-20 | 2026-04-17 | 100% - Complete | Completed | 2026-04-20 | 2026-04-20 | 2026-04-24 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 54 | 2026-04-13 | 2026-04-13 | Completed | 2026-04-10 | RPT | Finance : Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Gap Sprint | Week 1
FIN-RPT-002 | Report | FIN | 002 |  |  | RB & IAA | RB Non-Auction | Core Modules IAA | RPT-002 | Global Capex Analysis Report | Global Capex Analysis Report | 2 | Projects | Finance | Deloitte |  | Delayed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 2 | Sprint 3 | Deloitte | Deloitte | [5 empty] | Simple |  | 2026-07-10 | 2026-08-25 |  |  |  | Deshantha Clement Jayasekera | 25% - Drafted | Delayed | Nivethitha Nath | 2026-08-31 |  | 2026-09-07 |  | 2026-09-07 |  | 0% - Not Started | Delayed |  |  |  | Not Started |  |  |  | nivnath@deloitte.com | 2026-09-08 03:06 |  |  | 54 | 2026-06-15 |  | Delayed | 2026-08-25 | RPT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-RPT-003 | Report | FIN | 003 |  |  | RB & IAA | RB Non-Auction | Core Modules IAA | RPT-003 | High Detail Cost Summary | High Detail Cost Summary | 2 | Projects | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP | NA | Sprint 2 | Sprint 2 | Deloitte | Deloitte | [5 empty] | Medium |  | 2026-06-30 | 2026-07-03 | 2026-06-30 | 2026-07-08 | 2026-07-09 | Deshantha Clement Jayasekera | 100% - Approved | Completed | Mohanty, Ankita | 2026-07-13 | 2026-07-13 | 2026-08-04 |  | 2026-08-04 | 2026-07-30 | 100% - Complete | Completed | 2026-08-21 | 2026-08-21 | 2026-08-27 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 145 | 2026-06-15 |  | Completed | 2026-07-03 | RPT | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-RPT-004 | Report | FIN | 004 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-004 | RBC CAD Cheque Template | RBC CAD Cheque Template for RBG Rouse CA, RBFS | 1 | AP | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP | RBC | Sprint 1 | Sprint 1 | Deloitte | Deloitte | [5 empty] | Very Complex |  | 2026-02-06 | 2026-04-24 |  | 2026-04-29 | 2026-05-01 | Lara Chalak | 100% - Approved | Completed | Suchitra Sahoo | 2026-04-27 | 2026-06-03 | 2026-05-21 |  | 2026-06-29 | 2026-06-25 | 100% - Complete | Completed |  |  | 2026-08-14 | Completed |  |  | 06/24: Received MICR fond and Digital Signature. Completed the Development. 06/18: Awaiting Digital Signature and Font ttf file. Development is ON HOLD. 06/04: Awaiting MICR details from RBC bank. Development is ON HOLD. | raramesh@deloitte.ca | 2026-09-10 14:47 |  |  | 170 | 2026-05-04 | 2026-05-18 | Completed | 2026-04-24 | RPT | Finance : Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-RPT-005 | Report | FIN | 005 |  |  | RB & IAA, JMW & B&B | RB Non-Auction | Core Modules | RPT-005 | BoFA Cheque Template for JMW, B&B | BoFA Cheque Template for JMW, B&B, Rouse US | 1 | AP | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP | BOFA | Sprint 1 | Sprint 1 | Deloitte | Deloitte | [5 empty] | Complex |  | 2026-02-06 | 2026-04-24 |  | 2026-04-29 | 2026-05-01 | Lara Chalak | 100% - Approved | Completed | Suchitra Sahoo | 2026-04-27 | 2026-05-11 | 2026-05-19 |  | 2026-06-02 | 2026-05-21 | 100% - Complete | Completed |  |  | 2026-08-14 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 145 | 2026-05-18 | 2026-05-04 | Completed | 2026-04-24 | RPT | Finance : Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 2 | Week 1
FIN-RPT-006 | Report | FIN | 006 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-006 | Remittance Template | Supplier Remittance Customization |  | AP | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 1 | Sprint 1 | Deloitte | Deloitte | [5 empty] | Complex |  | 2026-03-20 | 2026-05-08 |  | 2026-04-21 | 2026-04-23 | Lara Chalak | 100% - Approved | Completed | Suchitra Sahoo | 2026-05-04 | 2026-05-04 | 2026-05-26 |  | 2026-05-26 | 2026-05-08 | 100% - Complete | Completed |  |  | 2026-05-12 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 145 | 2026-05-04 | 2026-05-04 | Completed | 2026-05-08 | RPT | Finance : Gap Sprint | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 2 | Week 1
FIN-RPT-007 | Report | FIN | 007 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-007 | ICO transactions processing for AP AR and PO | ICO transactions processing for AP AR and PO |  | IC | Finance | Deloitte | SIT 1 - Wk 3 | F-Spec-In Progress | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 4 | Sprint 5 | Deloitte | Deloitte | [5 empty] | Complex |  | 2026-09-11 |  |  |  |  | Deepankar Gera | 25% - Drafted | In Progress | Nivethitha Nath | 2026-09-14 |  | 2026-10-06 |  | 2026-10-06 |  | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 145 | 2026-05-25 |  | Not Started | 2026-09-11 | RPT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : SIT 2 | Week 1
FIN-RPT-008 | Report | FIN | 008 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-008 | Expense Approval Notification Template | Customize Expense Approval Notification Template |  | Expenses | Finance | Deloitte | Before SIT 1 | FUT-Pending | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 2 | Sprint 2 | Deloitte | Deloitte | [5 empty] | Simple |  | 2026-06-12 |  | 2026-05-25 | 2026-06-15 |  | Noshin Ali Barnagarwala | 100% - Approved | Completed | Suchitra Sahoo | 2026-06-15 | 2026-06-16 | 2026-06-22 |  | 2026-06-23 | 2026-06-19 | 100% - Complete | Completed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 54 | 2026-06-01 |  | Completed | 2026-06-12 | RPT | Finance : Gap Sprint | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-RPT-009 | Report | FIN | 009 |  |  | RB & IAA | RB Non-Auction | ARCS Already Live | RPT-009 | Payroll Account Analysis to ARCS | Payroll Account Analysis to ARCS |  | GL | Finance | Deloitte | Not Applicable | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP | ARCS | Sprint 2 | Sprint 2 | Deloitte | Deloitte | [5 empty] | Simple |  | 2026-07-06 | 2026-07-10 | 2026-07-06 | 2026-07-10 |  | Aiden Lee | 100% - Approved | Completed | Suchitra Sahoo | 2026-07-13 | 2026-07-13 | 2026-07-20 |  | 2026-07-20 | 2026-07-17 | 100% - Complete | Completed | 2026-07-16 | 2026-07-20 | 2026-07-21 | Completed | 54 |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 54 | 2026-06-08 |  | Completed | 2026-07-10 | RPT | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-RPT-010 | Report | FIN | 010 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-010 | ICO Credit Memo for AR | ICO Credit Memo for AR |  | IC | Finance | Deloitte | SIT 1 - Wk 4 | F-Spec-In Progress | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 4 | Sprint 5 | Deloitte | Deloitte | [5 empty] | Complex |  | 2026-09-11 |  |  |  |  | Deepankar Gera | 25% - Drafted | In Progress | Nivethitha Nath | 2026-09-21 |  | 2026-10-13 |  | 2026-10-13 |  | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 145 | 2026-07-27 |  | Not Started | 2026-09-11 | RPT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : SIT 2 | Week 1
FIN-RPT-011 | Report | FIN | 011 |  |  | RB & IAA | RB Non-Auction | Core Modules IAA | RPT-011 | Project Summary Top Task | Project Summary Top Task | 2 | Projects | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 2 | Sprint 3 | Deloitte | Deloitte | [5 empty] | Complex |  | 2026-07-10 |  | 2026-06-30 | 2026-07-08 | 2026-07-09 | Deshantha Clement Jayasekera | 100% - Approved | Completed | Nivethitha Nath | 2026-07-20 | 2026-07-14 | 2026-08-11 |  | 2026-08-05 | 2026-07-21 | 100% - Complete | Completed | 2026-08-21 | 2026-08-21 | 2026-08-27 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 145 | 2026-06-01 |  | Completed | 2026-07-10 | RPT | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-RPT-012 | Report | FIN | 012 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-012 | FA Asset Continuity Report | FA Asset Continuity Report |  | FA | Finance | Deloitte | Before SIT 1 | FUT-Pending | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 1 | Sprint 1 | Deloitte | Deloitte | [5 empty] | Complex |  | 2026-01-07 |  |  | 2026-04-10 |  | Gautam Channa | 100% - Approved | Completed | Suchitra Sahoo | 2026-01-12 | 2026-04-15 | 2026-02-03 |  | 2026-05-07 | 2026-04-29 | 100% - Complete | Completed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 145 | 2026-01-12 | 2026-04-15 | Completed | 2026-01-07 | RPT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 2 | Week 1
FIN-RPT-013 | Report | FIN | 013 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-013 | Expense Account Accrual Analysis Report | Expense Account Accrual Analysis Report |  | GL | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 1 | Sprint 1 | Deloitte | Deloitte | [5 empty] | Complex |  | 2026-02-13 | 2026-02-16 |  | 2026-02-16 |  | Noshin Ali Barnagarwala | 100% - Approved | Completed | Suchitra Sahoo | 2026-02-17 | 2026-02-17 | 2026-03-11 |  | 2026-03-11 | 2026-03-06 | 100% - Complete | Completed |  |  | 2026-03-13 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 145 |  | 2026-03-06 | Completed | 2026-02-16 | RPT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-RPT-014 | Report | FIN | 014 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-014 | Bill Presentment - CA Template | Bill Presentment - CA Template | 1 | AR | Finance | Deloitte | Before SIT 1 | FUT-In Progress | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 1 | Sprint 1 Sprint 2 | Deloitte | Deloitte | [5 empty] | Complex |  | 2026-05-21 | 2026-08-28 |  | 2026-05-21 | 2026-08-28 | Harsh Rawal | 100% - Approved | Completed | Mohanty, Ankita | 2026-06-01 | 2026-06-17 | 2026-06-23 |  | 2026-07-09 | 2026-08-31 | 100% - Complete | Completed | 2026-09-01 | 2026-09-07 |  | In Progress |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 145 | 2026-06-22 |  | Completed | 2026-08-28 | RPT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-RPT-015 | Report | FIN | 015 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-015 | Bill Presentment - US Template | Bill Presentment - US Template | 1 | AR | Finance | Deloitte | Before SIT 1 | FUT-In Progress | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 1 | Sprint 1 Sprint 2 | Deloitte | Deloitte | [5 empty] | Complex |  | 2026-05-21 | 2026-08-28 |  | 2026-05-21 | 2026-08-28 | Harsh Rawal | 100% - Approved | Completed | Mohanty, Ankita | 2026-06-15 | 2026-06-15 | 2026-07-07 |  | 2026-07-07 | 2026-08-31 | 100% - Complete | Completed | 2026-09-01 | 2026-09-07 |  | In Progress |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 145 | 2026-07-13 |  | Completed | 2026-08-28 | RPT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-RPT-016 | Report | FIN | 016 |  |  | RB & IAA | RB Non-Auction | Core Modules IAA | RPT-016 | Project Trial Balance Detail Report Detail & Summary | Project Trial Balance Detail Report Detail & Summary | 2 | Projects | Finance | Deloitte | Before SIT 1 | FUT-Pending | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 2 | Sprint 3 | Deloitte | Deloitte | [5 empty] | Medium |  | 2026-07-10 | 2026-07-22 |  | 2026-07-27 | 2026-07-27 | Deshantha Clement Jayasekera | 100% - Approved | Completed | Galande, Shubham Nanasaheb | 2026-08-10 | 2026-07-29 | 2026-09-01 |  | 2026-08-20 | 2026-08-26 | 100% - Complete | Completed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 145 | 2026-06-22 |  | Completed | 2026-07-22 | RPT | Finance : Sprint 3 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-RPT-017 | Report | FIN | 017 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-017 | Receivables Subledger Period Close Exceptions Report | Receivables Subledger Period Close Exceptions Report | 1 | AR | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 1 | Sprint 1 | Deloitte | Deloitte | [5 empty] | Complex |  | 2026-02-06 |  |  | 2026-05-13 |  | Harsh Rawal | 100% - Approved | Completed | Nivethitha Nath | 2026-05-25 | 2026-05-19 | 2026-06-16 |  | 2026-06-10 | 2026-06-04 | 100% - Complete | Completed |  |  | 2026-07-31 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 145 | 2026-07-13 |  | Completed | 2026-02-06 | RPT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 2 | Week 1
FIN-RPT-018 | Report | FIN | 018 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-018 | Receivables Aging (7 Bucket) by General Ledger Account Report | Receivables Aging (7 Bucket) by General Ledger Account Report | 1 | AR | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 1 | Sprint 1 | Deloitte | Deloitte | [5 empty] | Complex |  | 2026-02-06 |  |  | 2026-05-13 |  | Harsh Rawal | 100% - Approved | Completed | Nivethitha Nath | 2026-06-22 | 2026-06-03 | 2026-07-14 |  | 2026-06-25 | 2026-06-12 | 100% - Complete | Completed |  |  | 2026-07-31 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 145 | 2026-08-03 |  | Completed | 2026-02-06 | RPT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-RPT-019 | Report | FIN | 019 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-019 | FBAR Report | FBAR Report |  | CM | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 1 | Sprint 1 | Deloitte | Deloitte | [5 empty] | Medium |  | 2026-01-30 | 2026-03-05 |  | 2026-03-27 |  | Deepankar Gera | 100% - Approved | Completed | Suchitra Sahoo | 2026-03-16 | 2026-03-27 | 2026-03-27 |  | 2026-04-09 | 2026-03-27 | 100% - Complete | Completed |  |  | 2026-04-08 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-03-16 | 2026-03-16 | Completed | 2026-03-05 | RPT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Gap Sprint | Week 1
FIN-RPT-020 | Report | FIN | 020 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-020 | FX Risk Report | FX Risk Report |  | CM | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 1 | Sprint 1 | Deloitte | Deloitte | [5 empty] | Medium |  | 2026-01-30 | 2026-03-12 |  | 2026-03-12 |  | Deepankar Gera | 100% - Approved | Completed | Suchitra Sahoo | 2026-04-27 | 2026-04-24 | 2026-05-08 |  | 2026-05-07 | 2026-05-08 | 100% - Complete | Completed |  | 2026-04-17 | 2026-03-31 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-04-27 | 2026-04-13 | Completed | 2026-03-12 | RPT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 2 | Week 1
FIN-RPT-021 | Report | FIN | 021 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-021 | RBG Bank Statement Open Items Report | RBG Bank Statement Open Items Report |  | CM | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 1 | Sprint 1 | Deloitte | Deloitte | [5 empty] | Complex |  | 2026-01-30 | 2026-05-08 |  | 2026-05-04 | 2026-05-15 | Deepankar Gera | 100% - Approved | Completed | Suchitra Sahoo | 2026-05-25 | 2026-05-18 | 2026-06-05 |  | 2026-05-29 |  | 100% - Complete | Completed |  |  | 2026-08-21 | Completed |  |  | 06/04: Business Finalization pending for Returned Payment and Direct Debit transaction logic so development is ON HOLD. No tentative date received from functional team yet. | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-05-25 |  | Delayed | 2026-05-08 | RPT | Finance : Gap Sprint | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 2 | Week 1
FIN-RPT-022 | Report | FIN | 022 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-022 | AP Invoice Aging | AP Invoice Aging | 2 | AP | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 2 | Sprint 2 | Deloitte | Deloitte | [5 empty] | Medium |  | 2026-06-12 | 2026-06-26 |  | 2026-06-26 |  | Lara Chalak | 100% - Approved | Completed | Suchitra Sahoo | 2026-06-15 | 2026-06-29 | 2026-06-26 |  | 2026-07-10 | 2026-07-03 | 100% - Complete | Completed |  |  | 2026-08-14 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-06-08 |  | Completed | 2026-06-26 | RPT | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-RPT-023 | Report | FIN | 023 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-023 | Payables Payment Register Report (Supplier Payment History/Outstanding Prepayments) | Payables Payment Register Report (Supplier Payment History/Outstanding Prepayments) | 2 | AP | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 2 | Sprint 2 | Deloitte | Deloitte | [5 empty] | Medium |  | 2026-06-12 | 2026-06-26 |  | 2026-06-26 |  | Lara Chalak | 100% - Approved | Completed | DK, Anirudh | 2026-07-06 | 2026-07-10 | 2026-07-17 |  | 2026-07-23 | 2026-07-28 | 100% - Complete | Completed |  |  | 2026-08-14 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-07-20 |  | Completed | 2026-06-26 | RPT | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-RPT-024 | Report | FIN | 024 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-024 | Credit Card Transactions Report | Print corporate card transactions brought in from JPMC transaction feed to Oracle and their status in Oracle Expenses |  | Expenses | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 1 | Sprint 1 | Deloitte | Deloitte | [5 empty] | Medium |  | 2026-01-21 |  |  | 2026-02-06 |  | Noshin Ali Barnagarwala | 100% - Approved | Completed | Nivethitha Nath | 2026-02-02 | 2026-02-23 | 2026-02-13 |  | 2026-03-06 | 2026-03-06 | 100% - Complete | Completed |  |  | 2026-03-30 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-02-02 | 2026-02-23 | Completed | 2026-01-21 | RPT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-RPT-025 | Report | FIN | 025 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-025 | Cash & Card Transactions Report | Cash & Card Transactions Report |  | Expenses | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 1 | Sprint 1 | Deloitte | Deloitte | [5 empty] | Medium |  | 2026-01-23 |  |  | 2026-02-06 |  | Noshin Ali Barnagarwala | 100% - Approved | Completed | Nivethitha Nath | 2026-03-30 | 2026-02-16 | 2026-04-10 |  | 2026-02-27 | 2026-02-27 | 100% - Complete | Completed |  |  | 2026-03-30 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-03-30 | 2026-02-16 | Completed | 2026-01-23 | RPT | Due before Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 1 | Week 1
FIN-RPT-026 | Report | FIN | 026 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-026 | ICO Debit Memo for AR | ICO Debit Memo for AR |  | IC | Finance | Deloitte | SIT 1 - Wk 4 | F-Spec-In Progress | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 5 | Sprint 5 | Deloitte | Deloitte | [5 empty] | Medium |  | 2026-09-11 |  |  |  |  | Deepankar Gera | 25% - Drafted | In Progress | Nivethitha Nath | 2026-09-21 |  | 2026-10-02 |  | 2026-10-02 |  | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-08-03 |  | Not Started | 2026-09-11 | RPT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : SIT 2 | Week 1
FIN-RPT-027 | Report | FIN | 027 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-027 | Cash Account Balance by Entity Report | Cash Account Balance by Entity Report |  | CM | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 1 | Sprint 1 | Deloitte | Deloitte | [5 empty] | Medium |  | 2026-01-16 | 2026-05-29 |  | 2026-05-14 | 2026-05-20 | Deepankar Gera | 100% - Approved | Completed | Suchitra Sahoo | 2026-06-22 | 2026-06-03 | 2026-07-03 |  | 2026-06-16 | 2026-06-11 | 100% - Complete | Completed |  |  | 2026-08-17 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-06-22 |  | Completed | 2026-05-29 | RPT | Finance : Gap Sprint | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 2 | Week 1
FIN-RPT-028 | Report | FIN | 028 |  |  | RB & IAA | RB Non-Auction | Core Modules | RPT-028 | AP Trial Balance | AP Trial Balance | 2 | AP | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 2 | Sprint 2 | Deloitte | Deloitte | [5 empty] | Medium |  | 2026-06-12 | 2026-06-26 |  | 2026-06-26 |  | Lara Chalak | 100% - Approved | Completed | Galande, Shubham Nanasaheb | 2026-07-13 | 2026-07-10 | 2026-07-24 |  | 2026-07-23 | 2026-07-27 | 100% - Complete | Completed |  |  | 2026-08-14 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-06-29 |  | Completed | 2026-06-26 | RPT | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-RPT-029 | Report | FIN | 029 |  |  | RB & IAA | RB Non-Auction | Core Modules IAA | RPT-029 | CIP Balances with no Project | CIP Balances with no Project | 2 | Projects | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 2 | Sprint 3 | Deloitte | Deloitte | [5 empty] | Medium |  | 2026-07-10 |  | 2026-06-30 | 2026-07-08 | 2026-07-09 | Deshantha Clement Jayasekera | 100% - Approved | Completed | Suchitra Sahoo | 2026-07-20 | 2026-07-17 | 2026-07-31 |  | 2026-07-30 | 2026-07-22 | 100% - Complete | Completed | 2026-08-21 | 2026-08-21 | 2026-08-24 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-08-03 |  | Completed | 2026-07-10 | RPT | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
SCM-RPT-030 | Report | SCM | 030 |  |  | RB & IAA | RB Non-Auction | Core Modules IAA | RPT-030 | PO Details Report | PO Details Report |  | Procurement | Procurement | Deloitte | Before SIT 1 | FUT-Pending | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 1 | Sprint 1 | Deloitte | Deloitte | [5 empty] | Medium |  | 2025-11-13 | 2026-08-28 | 2026-08-17 | 2026-08-27 | 2026-08-28 | Rhythm Sharma | 100% - Approved | Completed | Galande, Shubham Nanasaheb | 2026-08-28 | 2026-08-28 | 2026-09-10 |  | 2026-09-10 | 2026-09-04 | 100% - Complete | Completed |  | 2026-09-11 |  | Not Started |  |  | 08/09/2026- First round of FUT complete, report sent back to tech team for changes. | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2025-11-24 | 2026-03-27 | Completed | 2026-08-28 | RPT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
SCM-RPT-031 | Report | SCM | 031 |  |  | RB & IAA | RB Non-Auction | Core Modules IAA | RPT-031 | PO PDF Report | PO PDF Report |  | Procurement | Procurement | Deloitte | Before SIT 1 | Delayed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 1 | Sprint 1 | Deloitte | Deloitte | [5 empty] | Medium |  | 2025-11-18 | 2026-08-28 |  |  | 2026-03-12 | Deepak Verma | 75% - Feedback Incorporated | Delayed | Chinmaya Sahoo | 2026-08-31 | 2026-08-27 | 2026-09-11 |  | 2026-09-09 | 2026-09-08 | 100% - Complete | Completed |  | 2026-09-08 |  | Delayed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-03-30 | 2026-03-23 | Completed | 2026-08-28 | RPT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-RPT-032 | Report | FIN | 032 |  |  | RB & IAA | RB Non-Auction | Core Modules IAA | RPT-032 | CIP Accounts Continuity | CIP Accounts Continuity | 2 | Projects | Finance | Deloitte | Before SIT 1 | FUT-In Progress | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 2 | Sprint 3 | Deloitte | Deloitte | [5 empty] | Medium |  | 2026-06-29 | 2026-07-22 |  | 2026-07-27 | 2026-07-27 | Deshantha Clement Jayasekera | 100% - Approved | Completed | Mohanty, Ankita | 2026-08-10 | 2026-07-30 | 2026-08-21 |  | 2026-08-12 | 2026-08-12 | 100% - Complete | Completed | 2026-08-21 | 2026-08-21 |  | In Progress |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-07-06 |  | Completed | 2026-07-22 | RPT | Finance : Sprint 3 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-RPT-033 | Report | FIN | 033 |  |  | RB & IAA | RB Non-Auction |  | RPT-033 | Custom Tax Report | Tax Report |  | Tax | Finance | One Source |  | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP | NA | Sprint 2 | Sprint 3 | Deloitte | Deloitte | [5 empty] | Complex |  | 2026-07-03 |  |  | 2026-06-26 |  | Tax Team | 100% - Approved | Completed | Nivethitha Nath | [6 empty] | Not Applicable | Not Applicable |  |  |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 145 | 2026-07-13 |  | Not Started | 2026-07-03 | RPT | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-RPT-034 | Report | FIN | 034 |  |  | RB & IAA | RB Non-Auction |  | RPT-034 | Custom Report for Matching Use Case | Matching Use Case Report |  | ARCS | Finance | Deloitte |  | Completed | No | SOW | Yes | BI | Outbound | Oracle Cloud ERP |  |  |  | Deloitte (ARCS) | Deloitte (ARCS) | [5 empty] | Medium |  | 2026-04-24 | 2026-06-26 |  | 2026-04-24 | 2026-04-24 | David Koter | 100% - Approved | Completed | Aiden Lee | 2026-05-04 |  | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 100% - Complete | Completed | 2026-05-18 | 2026-05-22 | 2026-05-22 | Completed |  |  | April 15: Will be changed to a dashboard | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 90 |  |  | Completed | 2026-06-26 | RPT | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 2 | Week 1
FIN-RPT-035 | Report | FIN | 035 |  |  | RB & IAA |  |  | RPT-035 | Custom Report for Adjustments to send to GL | GL Adjustments Report |  | ARCS | Finance | Deloitte |  | #INVALID OPERATION | No | SOW | No | BI | Outbound | Oracle Cloud ERP |  |  |  | Deloitte (ARCS) | Deloitte (ARCS) | [5 empty] | Medium | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | April 15: Won't be creating a report for adjustments. Can be removed from scope per David Koter email | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | RPT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-RPT-036 | Report | FIN | 036 |  |  | RB & IAA | RB Non-Auction |  | RPT-036 | Report Placeholder | Report Placeholder |  | ARCS | Finance | Deloitte |  | #INVALID OPERATION | No | SOW | No | BI | Outbound | Oracle Cloud ERP |  |  |  | Deloitte (ARCS) | Deloitte (ARCS) | [5 empty] | Simple | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  | April 15: Can be removed from scope per David Koter email | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 54 |  |  | Not Started |  | RPT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-RPT-037 | Report | FIN | 037 |  |  | All Entities | All |  |  | Customer Detail Report | This reports provides all the Customer Attributes mapped for Data Loads to enable easy recon |  | CDM | Finance | RBG |  | #INVALID OPERATION |  | New Requirement | Yes | BI | Outbound | Oracle Cloud ERP | [18 empty] | 0% - Not Started | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | RPT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-RPT-038 | Report | FIN | 038 |  |  | All Entities | All |  |  | Supplier Detail Report | This reports provides all the Supplier Attributes mapped for Data Loads to enable easy recon |  | CDM | Finance | RBG |  | #INVALID OPERATION |  | New Requirement | Yes | BI | Outbound | Oracle Cloud ERP | [18 empty] | 0% - Not Started | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | RPT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-RPT-039 | Report | FIN | 039 |  |  | DDI |  |  |  | Cheque Printing for DDI | Cheque Template Customization - DDI Cheques |  |  | Finance | Deloitte |  | #INVALID OPERATION | No | Discovery | No | BI | Outbound | Oracle Cloud ERP | [10 empty] | Very Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 |  |  | 170 |  |  | Not Started |  | RPT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-RPT-040 | Report | FIN | 040 |  |  | B&B |  |  |  | Cheque Printing for BB | Cheque Template Customization - B&B Cheques |  | AP | Finance | Deloitte |  | #INVALID OPERATION | No | Discovery | No | BI | Outbound | Oracle Cloud ERP | [10 empty] | Very Complex | [8 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | RPT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-RPT-041 | Report | FIN | 041 |  |  | RB & IAA |  |  |  | Placeholder Reports for Conversions | Placeholder for reports required for conversion reconciliation - TBD in RPT/CNV workshops and expanded into a RICE list here |  | All | Finance |  |  | #INVALID OPERATION | No | Imagine Sessions | No | BI | Outbound | Oracle Cloud ERP | [19 empty] | #INVALID OPERATION | [7 empty] | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | RPT |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-RPT-042 | Report | FIN | 042 |  |  | IAA | IAA - ASAP 1 | IAA |  | BMO CAD Cheque Template | BMO CAD Cheque Template for IAA |  | AP | Finance | Deloitte | SIT 1 - Wk 2 | Blocked | Yes | Imagine Sessions | Yes | BI | Outbound | Oracle Cloud ERP | [10 empty] | Complex |  | 2026-07-03 |  |  | 2026-07-15 |  | Yago Ramos | 100% - Approved | Completed | Nivethitha Nath | 2026-07-27 | 2026-07-24 | 2026-08-18 |  | 2026-08-17 | 2026-08-07 | Blocked | Blocked |  | 2026-09-11 |  | Not Started | Yes |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 145 |  |  | Completed | 2026-07-03 | RPT | Finance : Sprint 2 | [7 empty] | Finance : Sprint 3
FIN-RPT-043 | Report | FIN | 043 |  |  | RB & IAA | RB Non-Auction | Core Modules IAA |  | Commitments Detailed & Summary Report | Commitments Detailed & Summary Report | 2 | Projects | Finance | Deloitte | Before SIT 1 | FUT-Pending | No | Business need | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 2 | Sprint 2 | Deloitte | Deloitte | [5 empty] | Medium |  | 2026-07-10 |  | 2026-06-30 | 2026-07-08 | 2026-07-09 | Deshantha Clement Jayasekera | 100% - Approved | Completed | Nivethitha Nath | 2026-07-20 | 2026-07-20 | 2026-07-31 |  | 2026-07-31 | 2026-07-30 | 100% - Complete | Completed |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 |  |  | Completed | 2026-07-10 | RPT | Finance : Sprint 2 | [7 empty] | Finance : Sprint 3
FIN-RPT-044 | Report | FIN | 044 |  |  | RB & IAA | RB Non-Auction | Core Modules IAA |  | Capital Projects Suppliers Retainage | Capital Projects Suppliers Retainage | 2 | Projects | Finance | Deloitte | Before SIT 1 | Completed | No | Business need | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Deloitte | [5 empty] | Complex |  | 2026-07-10 | 2026-08-07 |  | 2026-08-05 |  | Deshantha Clement Jayasekera | 100% - Approved | Completed | Chinmaya Sahoo | 2026-08-31 | 2026-08-06 | 2026-08-28 |  | 2026-08-05 |  | 100% - Complete | Completed | 2026-08-21 | 2026-08-21 | 2026-08-24 | Completed |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 | [5 empty] | Delayed | 2026-08-07 | RPT | Finance : Sprint 3 | [7 empty] | Finance : Sprint 3
FIN-RPT-045 | Report | FIN | 045 |  |  | RB & IAA | RB Non-Auction | Core Modules IAA |  | Project Details with Transaction ID | Project Details with Transaction ID | 2 | Projects | Finance | Deloitte | Before SIT 1 | FUT-In Progress | No | Business need | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 2 | Sprint 3 | Deloitte | Deloitte | [5 empty] | Complex |  | 2026-07-10 |  | 2026-06-30 | 2026-07-08 | 2026-07-09 | Deshantha Clement Jayasekera | 100% - Approved | Completed | Suchitra Sahoo | 2026-08-10 | 2026-07-22 | 2026-08-07 |  | 2026-07-21 | 2026-07-28 | 100% - Complete | Completed | 2026-08-21 | 2026-08-21 |  | In Progress |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 | [5 empty] | Completed | 2026-07-10 | RPT | Finance : Sprint 2 | [7 empty] | Finance : Sprint 3
FIN-RPT-046 | Report | FIN | 046 |  |  | Mascus | Mascus |  |  | Salesforce (Mascus) - Oracle Subscription Reconciliation Report | Report to reconcile the orders sent from Salesforce with the subscriptions created in Oracle as part of the subscription creation integration |  | SM |  | Deloitte |  | Delayed | Yes | Imagine Sessions | No |  | Outbound | Oracle Cloud ERP | Oracle Cloud ERP | Sprint 2 | Sprint 2 | Deloitte | Oracle IFS Team | MASCUS Team |  |  | Sharjeel | WIP | Medium |  | 2026-07-03 | 2026-07-15 |  |  |  | Deepak Verma | 0% - Not Started | Delayed | Diprish Verma | 2026-08-31 |  | 2026-09-11 |  | 2026-09-11 |  | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 90 |  |  | Not Started | 2026-07-15 | RPT
FIN-RPT-047 | Report | FIN | 047 |  |  | RBG | All | Core Modules IAA |  | Quarterly Disclosures Report | Quarterly Disclosures Report |  | Lease Accounting | Finance | Deloitte |  | Delayed | Yes | Business need | Yes |  | Outbound | Oracle Cloud ERP |  | Sprint 3 | Sprint 3 Sprint 4 | [7 empty] | Medium |  | 2026-07-10 | 2026-08-26 |  |  |  | Deshantha Clement Jayasekera | 50% - Reviewed | Delayed | Nivethitha Nath | 2026-08-31 |  | 2026-09-11 |  | 2026-09-11 |  | 0% - Not Started | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 90 |  |  | Not Started | 2026-08-26 | RPT
FIN-RPT-048 | Report | FIN | 048 |  |  | All | All | Core Modules |  | Account Analysis Report | Subledger Account Analysis Report (Fusion AI Data Platform) |  | Multiple | Finance | Deloitte |  | Dev-In Progress | No | Business need | Yes |  | Outbound | Oracle Cloud ERP | Fusion AI Data Platform | Sprint 2 | Sprint 3 | Deloitte | Deloitte | [5 empty] | Medium |  | 2026-06-05 |  |  | 2026-06-12 |  | David Chin | 100% - Approved | Completed | David Chin | 2026-07-15 |  | 2026-07-28 |  | 2026-07-28 |  | 90% - Build - In Progress | In Progress |  |  |  | Not Started |  |  |  | dachin@deloitte.ca | 2026-09-10 08:05 |  |  | 88 |  |  | Delayed | 2026-06-05 | RPT | Finance : Gap Sprint | [7 empty] | Finance : Sprint 3
SCM-RPT-049 | Report | SCM | 049 |  |  | RB & IAA | All | Core Modules IAA |  | Supplier Maintenance Report | Supplier Maintenance Report |  | Procurement |  | RBG |  | #INVALID OPERATION | No | Business need | Yes |  | Outbound | Oracle Cloud ERP |  | Sprint 2 | Sprint 2 Sprint 3 | TBD | TBD | [5 empty] | Medium | [6 empty] | Sahana Srinivas | 25% - Drafted | #INVALID OPERATION | [8 empty] | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | RPT
FIN-RPT-050 | Report | FIN | 050 |  |  |  | All | IAA |  | Wells Fargo Cheque Template | Wells Fargo Cheque Template |  | AP | Finance | Deloitte | SIT 1 - Wk 2 | Delayed | No | Business need | Yes |  | Outbound | Oracle Cloud ERP | Wells Fargo | Sprint 3 | Sprint 3 Sprint 4 | Deloitte | Deloitte | [5 empty] | Very Complex |  | 2026-07-31 | 2026-08-24 |  |  |  | Yago Ramos | 75% - Feedback Incorporated | Delayed | Nivethitha Nath | 2026-08-14 | 2026-08-11 | 2026-09-09 |  | 2026-09-04 |  | 25% - Tech Spec - In Progress | In Progress |  | 2026-09-18 |  | Not Started | Yes |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 170 | 2026-08-17 |  | Delayed | 2026-08-24 | RPT
FIN-RPT-051 | Report | FIN | 051 |  | IAA |  |  | IAA |  | Report Data/Write back from Oracle |  |  | AP |  | RBG |  | #INVALID OPERATION | Yes | Business need | Yes |  | Outbound | Oracle Cloud ERP | IAA | Sprint 5 | Sprint 5 |  | RBG Oracle Team 1 | [14 empty] | #INVALID OPERATION | [8 empty] | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-08-28 08:08 | [5 empty] | Not Started |  | RPT
FIN-RPT-052 | Report | FIN | 052 |  | IAA |  |  | IAA |  | Report Data/Write back from Oracle |  |  | AR |  | RBG |  | #INVALID OPERATION | Yes | Business need | Yes |  | Outbound | Oracle Cloud ERP | IAA | Sprint 5 | Sprint 5 |  | RBG Oracle Team 1 | [14 empty] | #INVALID OPERATION | [8 empty] | Not Started |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-01 13:00 | [5 empty] | Not Started |  | RPT
FIN-RPT-053 | Report | FIN | 053 |  |  |  | All | Core Modules |  | Bill Presentment - Dubai Auctions & Dubai Services | Bill Presentment - Dubai Actions & Dubai Services |  | AR |  | Deloitte | Before SIT 1 | FUT-In Progress | Yes | Business need | Yes | BI | Outbound | Oracle Cloud ERP |  | Sprint 4 | Sprint 5 | Deloitte | Deloitte | [5 empty] | Medium |  | 2026-09-04 | 2026-09-02 | 2026-08-11 | 2026-09-02 |  | Harsh Rawal | 100% - Approved | Completed | Nivethitha Nath | 2026-09-14 | 2026-08-31 | 2026-09-25 |  | 2026-09-11 | 2026-09-04 | 100% - Complete | Completed | 2026-09-07 |  |  | In Progress |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 |  |  | Completed | 2026-09-02 | RPT
SCM-CNV-1004A | Conversion | SCM | 1004A |  |  | RB, IP/Mascus & Others | All | Core Modules IAA | CNV-001 | Vendor/Supplier Master Data | Vendor/Supplier Master Data |  | Procurement | Procurement | RBG |  | Delayed | Yes | SOW | Yes | FBDI | NA | EBS | Oracle Cloud ERP | Sprint 2 | Sprint 3 | Sahana Srinivas | RBG Oracle Team 1 | RBG Oracle Team 1 |  |  | Ian Trost, Jenn Mikalchuk |  | Medium |  | 2026-05-22 | 2026-07-17 |  |  |  | Sahana Srinivas | 50% - Reviewed | Delayed | Khaleel Shaik | 2026-06-12 |  | 2026-06-30 |  | 2026-06-30 |  | 50% - Build - In Progress | In Progress |  |  |  | Not Started |  |  | April 15: Accountability changed to RBG | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 117 | 2025-11-24 |  | Delayed | 2026-07-17 | CNV | Procurement : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Procurement : Sprint 3 | Week 1
SCM-CNV-1004B | Conversion | SCM | 1004B |  |  | IAA (US & Non US) | All | Core Modules IAA | CNV-001 | Vendor/Supplier Master Data | Vendor/Supplier Master Data |  | Procurement | Procurement | RBG |  | Delayed | Yes | SOW | Yes | FBDI | NA | GP | Oracle Cloud ERP | Sprint 2 | Sprint 3 |  | RBG Oracle Team 1 | RBG Oracle Team 1 |  |  | Ian Trost, Jenn Mikalchuk |  | Medium |  | 2026-05-22 | 2026-07-17 |  |  |  | Sahana Srinivas | 25% - Drafted | Delayed | Khaleel Shaik | 2026-06-12 |  | 2026-06-30 |  | 2026-06-30 |  | 50% - Build - In Progress | In Progress |  |  |  | Not Started |  |  | April 15: Accountability changed to RBG | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 117 | 2025-11-24 |  | Delayed | 2026-07-17 | CNV | Procurement : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Procurement : Sprint 3 | Week 1
FIN-CNV-1009A | Conversion | FIN | 1009A |  |  | RB, IP/Mascus & Others | All | DPP IP Mascus | CNV-002 | Vendors/Suppliers Banks and Accounts (external bank accounts) | Convert Vendor/Supplier Banks and their Bank Accounts (External Bank Accounts) |  | AP | Finance | RBG |  | Delayed | Yes | SOW | Yes | FBDI | NA | EBS | Oracle Cloud ERP | Sprint 2 | Sprint 3 | Sahana Srinivas | RBG Oracle Team 1 | RBG Oracle Team 1 |  |  | Ian Trost, Jenn Mikalchuk |  | Simple |  | 2026-05-22 | 2026-07-17 |  |  |  | Sahana Srinivas | 50% - Reviewed | Delayed | Khaleel Shaik | 2026-06-12 |  | 2026-06-25 |  | 2026-06-25 |  | 50% - Build - In Progress | In Progress |  |  |  | Not Started |  |  | April 15: Accountability changed to RBG | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 90 | 2025-11-24 |  | Delayed | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-CNV-1009B | Conversion | FIN | 1009B |  |  | IAA (US & Non US) | All | IAA | CNV-002 | Vendors/Suppliers Banks and Accounts (external bank accounts) | Convert Vendor/Supplier Banks and their Bank Accounts (External Bank Accounts) |  | AP | Finance | RBG |  | Delayed | Yes | SOW | Yes | FBDI | NA | GP | Oracle Cloud ERP | Sprint 2 | Sprint 3 | Sahana Srinivas | RBG Oracle Team 1 | RBG Oracle Team 1 |  |  | Ian Trost, Jenn Mikalchuk |  | Simple |  | 2026-05-22 | 2026-07-17 |  |  |  | Sahana Srinivas | 50% - Reviewed | Delayed | Khaleel Shaik | 2026-06-12 |  | 2026-06-25 |  | 2026-06-25 |  | 50% - Build - In Progress | In Progress |  |  |  | Not Started |  |  | April 15: Accountability changed to RBG | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 90 | 2025-11-24 |  | Delayed | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
SCM-CNV-1013A | Conversion | SCM | 1013A |  |  | RB, IP/Mascus & Others | All | Core Modules IAA | CNV-003 | Convert Supplier's/Vendors Addresses, Sites and Contacts | Convert Supplier's/Vendors Addresses, Sites and Contacts |  | Procurement | Procurement | RBG |  | Delayed | Yes | SOW | Yes | FBDI | NA | EBS | Oracle Cloud ERP | Sprint 2 | Sprint 3 | Sahana Srinivas | RBG Oracle Team 1 | RBG Oracle Team 1 |  |  | Ian Trost, Jenn Mikalchuk |  | Medium |  | 2026-05-22 | 2026-07-17 |  |  |  | Sahana Srinivas | 50% - Reviewed | Delayed | Khaleel Shaik | 2026-06-12 |  | 2026-06-25 |  | 2026-06-25 |  | 50% - Build - In Progress | In Progress |  |  |  | Not Started |  |  | April 15: Accountability changed to RBG | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 90 | 2025-11-24 |  | Delayed | 2026-07-17 | CNV | Procurement : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Procurement : Sprint 3 | Week 1
SCM-CNV-1013B | Conversion | SCM | 1013B |  |  | IAA (US & Non US) | All | Core Modules IAA | CNV-003 | Convert Supplier's/Vendors Addresses, Sites and Contacts | Convert Supplier's/Vendors Addresses, Sites and Contacts |  | Procurement | Procurement | RBG |  | Delayed | Yes | SOW | Yes | FBDI | NA | GP | Oracle Cloud ERP | Sprint 2 | Sprint 3 |  | RBG Oracle Team 1 | RBG Oracle Team 1 |  |  | Ian Trost, Jenn Mikalchuk |  | Medium |  | 2026-05-22 | 2026-07-17 |  |  |  | Sahana Srinivas | 25% - Drafted | Delayed | Khaleel Shaik | 2026-06-12 |  | 2026-06-25 |  | 2026-06-25 |  | 50% - Build - In Progress | In Progress |  |  |  | Not Started |  |  | April 15: Accountability changed to RBG | dipriverma@deloitte.ca | 2026-08-27 06:26 |  |  | 90 | 2025-11-24 |  | Delayed | 2026-07-17 | CNV | Procurement : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Procurement : Sprint 3 | Week 1
FIN-CNV-1034A | Conversion | FIN | 1034A |  |  | RB, IP/Mascus & Others | All | Core Modules | CNV-009 | Bank and branch master data | Convert Internal Bank Accounts |  | CM | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | FBDI | NA | EBS | Oracle Cloud ERP | Sprint 1 | Not Applicable |  |  |  | 2026-08-20 | 75% - Feedback Incorporated | Eric DeLau |  | Simple |  | 2026-01-30 | 2026-04-23 |  | 2026-03-31 |  | Deepankar Gera | 100% - Approved | Completed |  |  | 2026-08-18 |  |  | 2026-08-31 |  | 100% - Complete | Completed |  |  |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-03-23 |  | Delayed | 2026-04-23 | CNV | Finance : Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1034B | Conversion | FIN | 1034B |  |  | IAA (US & Non US) | All | Core Modules | CNV-009 | Bank and branch master data | Convert Internal Bank Accounts |  | CM | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | FBDI | NA | GP | Oracle Cloud ERP | Sprint 2 | Not Applicable |  |  |  | 2026-08-20 |  | Eric DeLau |  | Simple |  | 2026-01-30 | 2026-07-17 |  | 2026-03-31 |  | Deepankar Gera | 100% - Approved | Completed |  |  | 2026-08-18 |  |  | 2026-08-31 |  | 100% - Complete | Completed |  |  |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-03-23 |  | Delayed | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 |  | Week 1
FIN-CNV-1036A | Conversion | FIN | 1036A |  |  | RB, IP/Mascus & Others | All | Core Modules | CNV-010 | Fixed Assets | Convert Fixed Assets |  | FA | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | FBDI | NA | EBS | Oracle Cloud ERP | Sprint 1 | Sprint 2 | Deloitte | Deloitte | RBG Oracle Team 1 | 2026-08-20 |  | Benjamin Kraus |  | Medium |  | 2026-01-07 | 2026-04-10 |  | 2026-04-10 |  | Gautam Channa | 100% - Approved | Completed | Saikat Banerjee | 2026-05-04 | 2026-06-17 | 2026-05-20 |  | 2026-07-03 | 2026-07-03 | 100% - Complete | Completed |  |  |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 117 | 2026-05-04 |  | Completed | 2026-04-10 | CNV | Finance : Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-CNV-1036B | Conversion | FIN | 1036B |  |  | IAA (US & Non US) | All | Core Modules | CNV-010 | Fixed Assets | Convert Fixed Assets |  | FA | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | FBDI | NA | Sage | Oracle Cloud ERP | Sprint 2 | Sprint 3 | Deloitte | Deloitte | RBG Oracle Team 1 | 2026-08-20 |  | Benjamin Kraus |  | Medium |  | 2026-01-07 | 2026-07-17 |  | 2026-04-10 |  | Gautam Channa | 100% - Approved | Completed | Saikat Banerjee | 2026-05-04 | 2026-06-17 | 2026-05-20 |  | 2026-07-03 | 2026-07-03 | 100% - Complete | Completed |  |  |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 117 | 2026-05-04 |  | Completed | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-CNV-1048A | Conversion | FIN | 1048A |  |  | RBG | All | Core Modules | CNV-016 | Open Projects, Tasks | Convert Open Projects & Tasks |  | Projects | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | FBDI | NA | EBS | Oracle Cloud ERP | Sprint 1 | Sprint 2 | Deloitte | Deloitte | RBG Oracle Team 1 | 2026-08-20 |  | Benjamin Kraus |  | Complex |  | 2026-01-07 | 2026-04-10 |  | 2026-04-10 | 2026-04-10 | Deshantha Clement Jayasekera | 100% - Approved | Completed | Saikat Banerjee | 2026-05-18 | 2026-06-08 | 2026-06-12 |  | 2026-07-03 | 2026-07-03 | 100% - Complete | Completed |  |  |  | Not Applicable | No |  | Need deeper dive on IT Projects, Property projects etc. and conversion requirement around those | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 180 | 2026-05-18 |  | Completed | 2026-04-10 | CNV | Finance : Sprint 1 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-CNV-1048B | Conversion | FIN | 1048B |  |  | IAA | All | Core Modules | CNV-016 | Open Projects, Tasks | Convert Open Projects & Tasks |  | Projects | Finance | Deloitte | Before SIT 1 | Completed | No | SOW | Yes | FBDI | NA | Pitstop | Oracle Cloud ERP | Sprint 2 | Sprint 2 | Deloitte | Deloitte | RBG Oracle Team 1 | 2026-08-20 |  | Benjamin Kraus |  | Complex |  | 2026-01-07 | 2026-07-17 |  | 2026-04-10 | 2026-04-10 | Deshantha Clement Jayasekera | 100% - Approved | Completed | Saikat Banerjee | 2026-05-18 | 2026-06-08 | 2026-06-12 |  | 2026-07-03 | 2026-07-03 | 100% - Complete | Completed |  |  |  | Not Applicable | No |  | Need deeper dive on IT Projects, Property projects etc. and conversion requirement around those | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 180 | 2026-05-18 |  | Completed | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-CNV-1059A | Conversion | FIN | 1059A |  |  | RBG | IAA - ASAP 1 IAA - CAN & UK IronPlanet RB Non-Auction | Core Modules |  | Leases, Schedule | Leases, Schedule | 1 | Lease Accounting | Finance | Deloitte | Before SIT 1 | Delayed | Yes | RBG Discovery | Yes | TBD | NA | EBS | Oracle Cloud ERP | Sprint 3 | Sprint 3 | Oracle Team 1 | Oracle Team 2 |  |  |  | Benjamin Kraus |  | Medium |  | 2026-07-10 | 2026-08-26 |  |  |  | Deshantha Clement Jayasekera | 25% - Drafted | Delayed | Saikat Banerjee | 2026-07-13 |  | 2026-08-07 |  | 2026-08-07 |  | 0% - Not Started | Delayed |  |  |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 180 |  |  | Delayed | 2026-08-26 | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-CNV-1059B | Conversion | FIN | 1059B |  |  | IAA | IAA - ASAP 1 IAA - CAN & UK IronPlanet RB Non-Auction | IAA |  | Leases, Schedule | Leases, Schedule | 1 | Lease Accounting | Finance | Deloitte | Before SIT 1 | Delayed | Yes | RBG Discovery | Yes | TBD | NA | CoStar | Oracle Cloud ERP | Sprint 3 | Sprint 3 | Oracle Team 1 | Oracle Team 2 |  |  |  | Benjamin Kraus |  | Medium |  | 2026-07-10 | 2026-08-26 |  |  |  | Deshantha Clement Jayasekera | 25% - Drafted | Delayed | Saikat Banerjee | 2026-07-20 |  | 2026-08-14 |  | 2026-08-14 |  | 0% - Not Started | Delayed |  |  |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 180 |  |  | Delayed | 2026-08-26 | CNV |  | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-CNV-1060A | Conversion | FIN | 1060A |  |  | RB | All | Core Modules | CNV-017 | Open Project Costs | Open Project Costs |  | Projects | Finance | Deloitte | Before SIT 1 | Completed | No | New Requirement | Yes | FBDI | NA | EBS | Oracle Cloud ERP | Sprint 1 | Sprint 2 | Deloitte | Deloitte |  | 2026-08-20 |  | Benjamin Kraus |  | Medium |  |  | 2026-05-08 |  | 2026-05-22 | 2026-05-22 | Deshantha Clement Jayasekera | 100% - Approved | Completed | Saikat Banerjee | 2026-05-25 |  | 2026-06-05 |  | 2026-06-05 | 2026-07-03 | 100% - Complete | Completed |  |  |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-05-25 |  | Completed | 2026-05-08 | CNV | Finance : Gap Sprint | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 2 | Week 1
FIN-CNV-1060B | Conversion | FIN | 1060B |  |  | IAA | All | Core Modules | CNV-017 | Open Project Costs | Open Project Costs |  | Projects | Finance | Deloitte | Before SIT 1 | Completed | No | New Requirement | Yes | FBDI | NA | Pitstop | Oracle Cloud ERP | Sprint 2 | Sprint 3 | Deloitte | Deloitte |  | 2026-08-20 |  | Benjamin Kraus |  | Medium |  |  | 2026-07-17 |  | 2026-05-22 | 2026-05-22 | Deshantha Clement Jayasekera | 100% - Approved | Completed | Saikat Banerjee | 2026-05-25 |  | 2026-06-05 |  | 2026-06-05 | 2026-07-03 | 100% - Complete | Completed |  |  |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-05-25 |  | Completed | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 2 | Week 1
FIN-CNV-1061A | Conversion | FIN | 1061A |  |  | RB | All | Core Modules | CNV-018 | Open Project Budgets | Open Project Budgets |  | Projects | Finance | Deloitte | Before SIT 1 | Completed | No | New Requirement | Yes | FBDI | NA | EBS | Oracle Cloud ERP | Sprint 1 | Sprint 2 | Deloitte | Deloitte |  | 2026-08-20 |  | Benjamin Kraus |  | Medium |  |  | 2026-05-08 |  | 2026-05-22 | 2026-05-22 | Deshantha Clement Jayasekera | 100% - Approved | Completed | Saikat Banerjee | 2026-06-15 |  | 2026-06-26 |  | 2026-06-26 | 2026-07-03 | 100% - Complete | Completed |  |  |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-06-15 |  | Completed | 2026-05-08 | CNV | Finance : Gap Sprint | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-CNV-1061B | Conversion | FIN | 1061B |  |  | IAA | All | Core Modules | CNV-018 | Open Project Budgets | Open Project Budgets |  | Projects | Finance | Deloitte | Before SIT 1 | Completed | No | New Requirement | Yes | FBDI | NA | Pitstop | Oracle Cloud ERP | Sprint 2 | Sprint 3 | Deloitte | Deloitte |  | 2026-08-20 |  | Benjamin Kraus |  | Medium |  |  | 2026-07-17 |  | 2026-05-22 | 2026-05-22 | Deshantha Clement Jayasekera | 100% - Approved | Completed | Saikat Banerjee | 2026-06-15 |  | 2026-06-26 |  | 2026-06-26 | 2026-07-03 | 100% - Complete | Completed |  |  |  | Not Applicable | No |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 90 | 2026-06-15 |  | Completed | 2026-07-17 | CNV | Finance : Sprint 2 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Technology : Sprint 1.5 | Week 1 | Finance : Sprint 3 | Week 1
FIN-RPT-054 | Report | FIN | 054 |  |  | All | All | Core Modules |  | OBN Invoice Processing - Template Modifications | OBN Invoice Processing - Template Modifications |  | AP |  | Deloitte | Before SIT 1 | Delayed |  |  | Yes |  | Inbound | Suppliers | Oracle Cloud ERP | Sprint 4 | Sprint 4 | [9 empty] | 2026-08-31 | 2026-09-04 |  |  |  | Yago Ramos | 50% - Reviewed | Delayed | Piyush Ojha | 2026-09-07 | 2026-09-07 | 2026-09-14 |  | 2026-09-14 |  | 75% - Unit Testing - In Progress | In Progress |  |  |  | Not Started |  |  |  | dipriverma@deloitte.ca | 2026-09-10 12:23 |  |  | 54 |  |  | Not Started | 2026-09-04 | RPT

## Comments
Row 2 | Vikranth: This is being discussed with Jenn and will be de-scoped | Diprish Verma | 09/09/26 2:23 PM
Row 5 | Additional template created to handle JPMC Payments. There might be a few changes to incorporate the large entities | Diprish Verma | 04/30/26 11:41 AM
Row 7 | Kyriba driven integration. | Diprish Verma | 04/30/26 11:43 AM
Row 9 | Transferred to RBG as part of Mascus scope | Diprish Verma | 06/11/26 8:00 AM
Row 9 | Adyen is used to Charge Customers through Credit Card details saved against them in Adyen. | Piyush Ojha | 05/07/26 7:53 AM
Row 12 | @djayasekera@deloitte.ca - Could you please provide the revised lean spec approval date? | Diprish Verma | 04/15/26 11:19 AM
Row 44 | @lchalak@deloitte.ca - Do you have the revised date for the lean spec completion? | Diprish Verma | 04/15/26 12:49 PM
| Revised Date updated | Deshantha Clement Jayasekera | 04/17/26 9:37 AM
Row 118 | Marked 75% based on call from Imran | Piyush Ojha | 08/13/26 8:59 AM
Row 120 | Pending on Sample Files from Functional. | Piyush Ojha | 08/17/26 6:27 AM
Row 120 | Spec is shared on 14-Aug-2026. | Piyush Ojha | 08/17/26 6:26 AM
Row 120 | Marked it to 75% based on call from Imran | Piyush Ojha | 08/13/26 8:58 AM
Row 122 | This one is blocked based on Oracle SR open. | Piyush Ojha | 08/17/26 6:24 AM
Row 122 | marked it to 75% based on Call with Imran | Piyush Ojha | 08/13/26 8:58 AM
Row 122 | This token information can be merged with Mascus Customer Integration. | Piyush Ojha | 06/18/26 7:48 AM
Row 131 | Existing EBS Integration: INT_FIN325: AR RBFS Transaction Import. | Diprish Verma | 04/28/26 1:24 PM
Row 131 | Followup with Jenn if it can be done manually. | Diprish Verma | 04/28/26 1:15 PM
Row 131 | RBFS is not an operational system. It would me a manual conversion. Followup with Gavin/Gary on the ownership. | Diprish Verma | 04/28/26 1:14 PM
Row 236 | SR: 4-0003275463 | Diprish Verma | 09/09/26 7:11 AM
Row 236 | This is blocked until SR from Oracle is resolved to enable Payment Tokenization in Oracle | Piyush Ojha | 08/17/26 6:33 AM
Row 242 | There is no development required to ingest the file from Kyriba. As of 25Aug26, Kyriba is working on mapping changes requested from RBG to align with the requirements. Once Kyriba has implemented their changes, we are good to continue with FUT. Until then we are blocked with Kyriba dependency. | Deepankar Gera | 08/26/26 7:45 AM
Row 242 | Only Kyriba development. No custom integration is required. | Diprish Verma | 05/29/26 11:12 AM
Row 280 | Awaiting bank specification mapping document. | Suchitra Sahoo | 08/24/26 6:19 AM
Row 280 | This is only applicable for cheques that are being printed out of GP for BMO. No cheques are required to be printed for IAA - UK | Diprish Verma | 06/16/26 1:47 PM
Row 280 | Planned to be added as part of the June 2026 CR | Diprish Verma | 06/10/26 1:45 PM
Row 285 | Follow up on this spec, if need to extend ARCS team. ETA 9/18 | Diprish Verma | 09/09/26 7:32 AM
Row 285 | Please update as below: Spec Completion Date - Revised: 4th September 2026 Dev + UT Completion Date - Planned: 25th September 2026 | Aiden Lee | 08/24/26 12:51 PM
Row 286 | Development Dependency- Due to SR - 4-0003721960 testing has been blocked Payment Terms mapping still pending on functional team Token generation looks to be new scope for this interface. Awaiting confirmation from functional team should we add that or not. | Suchitra Sahoo | 09/09/26 5:54 AM
Row 286 | Build is in progress, pending on few open items as spec is not signed off. | Piyush Ojha | 08/17/26 6:34 AM
Row 288 | Marked to 50% based on call from Imran | Piyush Ojha | 08/13/26 9:00 AM
Row 289 | Marked Spec completion date to 21st August as per call from Imran | Piyush Ojha | 08/13/26 9:14 AM
Row 290 | Modified Spec completion date as per call from Imran | Piyush Ojha | 08/13/26 9:02 AM
Row 290 | Marked to 25% based on call from Imran | Piyush Ojha | 08/13/26 9:01 AM
Row 293 | Deepak to send to RB for feedback on Aug 27 | Raksha Malangi | 08/26/26 8:31 AM
Row 301 | RAID-364 created to get clarification on ASAP printed checks. | Suchitra Sahoo | 08/26/26 3:04 AM
Row 301 | Pending confirmation from Yago on Payee position and BankID logic. | Suchitra Sahoo | 08/24/26 6:17 AM
Row 301 | Pending Payer Conditional Requirement confirmation from Functional | Piyush Ojha | 08/20/26 6:28 AM
Row 303 | This one is to let Acqueon Dialer to know about Do not Disturb details. | Piyush Ojha | 05/07/26 7:59 AM
Row 306 | Desh: RAID to be logged to de-scope this report | Diprish Verma | 07/30/26 11:19 AM
Row 311 | New report added by Vikranth | Diprish Verma | 09/02/26 5:09 AM
Row 311 | Moving this to Not in Scope based on the comments above | Raksha Malangi | 08/20/26 9:23 AM
Row 311 | Removed from Deloitte scope and will be developed by RBG | Diprish Verma | 07/15/26 1:52 PM
Row 311 | Blocked and waiting confirmation from RBG, RAID-215 | Diprish Verma | 07/15/26 6:44 AM
Row 311 | Originally this object was Remittance Template 2. It is confirmed that it is no longer needed. | Diprish Verma | 04/30/26 12:54 PM
Row 313 | Go-live is scheduled on 21st September 2026. | Aiden Lee | 08/24/26 12:56 PM
Row 314 | New report added by Vikranth | Diprish Verma | 09/02/26 5:16 AM
Row 314 | Moving this to Not in Scope based on the comments above | Raksha Malangi | 08/20/26 9:23 AM
Row 314 | Blocked for Payables Key Indicator Report. No longer required. | Diprish Verma | 07/30/26 11:09 AM
Row 314 | Blocked and waiting confirmation from RBG, RAID-215 | Diprish Verma | 07/15/26 6:44 AM
Row 318 | Awaiting for TEST data to complete the unit testing. Dev completed. | Suchitra Sahoo | 08/24/26 6:11 AM
Row 318 | Pending FS to be updated from FUnctional | Piyush Ojha | 08/20/26 6:13 AM
Row 318 | Changed the module to AR, and updated the Placeholder to Bill Presentment | Diprish Verma | 05/25/26 8:36 AM
Row 319 | Awaiting for TEST data to complete the unit testing. Dev completed. | Suchitra Sahoo | 08/24/26 6:11 AM
Row 319 | Changed the module to AR, and updated the Placeholder to Bill Presentment | Diprish Verma | 05/25/26 8:52 AM
Row 320 | Updated the complexity of this report to Medium from Complex to adjust updated RPT-021 complexity (Medium -> Complex) | Diprish Verma | 05/25/26 6:12 AM
Row 325 | RAID: 259 | Diprish Verma | 08/28/26 6:21 AM
Row 325 | Updated the complexity of this report to Complex from Medium based on the requirement. Reduced the complexity of RPT-016 from Complex to Medium. | Diprish Verma | 05/25/26 6:12 AM
Row 330 | New report added by Vikranth | Diprish Verma | 09/02/26 5:16 AM
Row 330 | Khaleel: RBG will handle this requirement internally. | Diprish Verma | 08/28/26 6:20 AM
Row 330 | Blocked: RAID: RAID-264 | Diprish Verma | 07/02/26 7:12 AM
Row 334 | Awaiting new CR | Suchitra Sahoo | 08/24/26 6:13 AM
Row 335 | New RICE component has been requested by business to change Email body. Awaiting CR | Suchitra Sahoo | 08/24/26 6:14 AM
Row 346 | Open questions on the Cheque Template is preventing the development to complete. | Diprish Verma | 09/02/26 9:04 AM
Row 346 | Waiting Sign off on the Spec. updated status. | Piyush Ojha | 08/11/26 2:00 PM
Row 349 | RAID-366 created to get clarification on accounting class code for finally accounted transactions. Until get that FUT issue fix is blocked. | Suchitra Sahoo | 08/26/26 3:25 AM
Row 354 | Pending Logo and Signature for the Template | Piyush Ojha | 08/20/26 6:30 AM
Row 354 | Updated Status to 50% , Spec is sent for approval on 24th July 2026. Based on discussion with Yago. | Piyush Ojha | 08/11/26 1:57 PM
Row 357 | Added as a new CR, awaiting RBG's approval. | Diprish Verma | 09/01/26 1:04 PM

## Summary
Total RICE Items | 192
Deloitte Owned - Total RICE Objects | 105
RBG Owned - Total RICE Objects | 86
Obj Status : Not Started - Deloitte | #INVALID OPERATION
Obj Status : F-Spec In Progress - Deloitte | #INVALID OPERATION
Obj Status : Dev In Progress - Deloitte | #INVALID OPERATION
Obj Status : FUT In-Progress - Deloitte | #INVALID OPERATION
Obj Status : Completed - Deloitte | #INVALID OPERATION
Obj Status : Not Started - RBG | #INVALID OPERATION
Obj Status : F-Spec In Progress - RBG | #INVALID OPERATION
Obj Status : Dev In Progress - RBG | #INVALID OPERATION
Obj Status : FUT In Progress - RBG | #INVALID OPERATION
Obj Status : Completed - RBG | #INVALID OPERATION